## Summary
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
Proposed- 5-Year Bond Review
Direct Costs |  |  |  | Post - 1974 Areas |  | Pre- 1974 Areas
| Item 1 Earthwork - YDTI Embankments |  |  | 12876808.9117 |  | 213000
| Item 2 Earthwork - YDTI Beach at Closure |  |  | 20399956.2561 |  | 239000
| Previous Item 3 (Earthwork for Associated RDS) |  |  | Removed
North RDS would not exist in 2025, Great Northern RDS is under Dump Areas tab
| Item 3 Exploration- West Ridge Wells brought into OP |  |  | 28465 |  | -
| Item 6 Interim Management |  |  | 1068730.4 |  | -
| Item 9 Earthwork - Dump Areas |  |  | 8922476.7389 |  | 78500
| Item 10 Earthwork - Leach Pads |  |  | 286816.3352 |  | 81000
| Item 11 Earthwork - Continental Pit |  |  | 5220322.1673 |  | 29500
| Item 12 Pre-Law Areas |  |  |  | See tab details
| Item 13 Miscellaneous Areas |  |  | 8342952.7718 |  | 185500
| Item 14 Improve Clearwater Ditch |  |  | 57720
|  | Subtotal |  | 57204248.5811 |  | 826500
Indirect Costs
| Mobilization |  | 4% | 2288169.9432 |  | N/A
| Engineering & Redesign |  | 5% | 2860212.4291 |  | N/A
| Contingency |  | 10% | 5720424.8581 |  | N/A
| Administration |  | 10% | 5720424.8581 |  | N/A
| Inflation Cost Adjustment @ 2% Per Year for 5 Years |  | 10.4% | 5949241.8524 |  | N/A
|  | Subtotal |  | 22538473.941 |  | -
Post-Closure Costs
| Item 4 WED Water Treatment at Closure |  |  | - | Not required in 2025, see tab details
| Item 5 Post Closure Reclamation |  |  | 15701235.023 |  | 17000
| Item 7 A&E Closure Reclamation Management |  |  | 4274921.6 |  | -
| Item 8 A&E Post Closure Management |  |  | 11838562.1964 |  | -
| Item 15 Construct Spillway at Closure |  |  | 4076559.1044 |  | -
|  | Subtotal |  | 35891277.9237 |  | 17000
|  | Total |  | 115634000.4458 |  | 843500 | Pre-1974
Montana Resources 5-Year Bond Review Total Reclamation Cost | [5 empty] | 116477500.4458
|  |  | Amount Currently Held |  |  | 114602575
|  |  | Additional Amount Required |  |  | 1874925.4458

## References
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
References:
Montana Resources Final EIS, August 2019
Montana Resources Annual Report 2019, June 3, 2020
Montana Resources Continental Mine Operations Plan, January 2019
Montana Resources Amendment to Operating Permit, May 2018
Montana Resources Yankee Doodle Tailings Impoundment Design Basis Report, September 2017
Great Falls Coal Fields Water Treatment Assessment, March 2012, Prepared for DEQ by Hydrometerics
EquipmentWatch Cost Reference Guide, Online Version
Montana Davis Macon Prevailing Wage Rates for Heavy Construction Services 2019, Effective January 26, 2019
RS Means/Gordian Heavy Construction Costs 2019, 33rd Edition
State of Nevada Standardized Reclamation Cost Estimator (SRCE), Version 1.4.1
YDTI Embankment Acreage by Permit, Westech December 28, 2019
YDTI Bench/Pond by Permit, Westech December 28, 2019
Projected Supernatant Pond Water Level Trends during 2020-2029, Knight Piesold, February 6, 2020
Conceptual Spillway Memo, Knight Piesold, September 22, 2020
Bond review response letter, 2025 Site Plan- Map and Acreage Table, MR/Westech, October 2, 2020

## Inputs
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
ACREAGES FROM 2025 SITE PLAN MAP
Feature | Bond Calc Tab | OP 00030A | OP 00041 | OP 00108 | OP 00030 | Grand Total
Alluvium Stockpile | 14-Misc |  | 10.4504 | 8.6964 |  | 19.1467
Berkeley Pit (BMFOU) | 13-PreLaw |  |  |  | 237.6357 | 237.6357
Berkeley Pit Water (BMFOU) | 13-PreLaw |  |  |  | 446.348 | 446.348
Concentrator Area (EXEMPT) | 13-PreLaw |  |  |  | 75.7872 | 75.7872
Concentrator Area Partially Reclaimed/Released (EXEMPT) | 13-PreLaw |  |  |  | 19.3481 | 19.3481
Continental Pit - Highwall | 12-Pits | 65.6282 | 233.112 | 47.9682 | 37.3341 | 384.0425
Continental Pit - Reclaimable Area | 12-Pits | 30.2972 | 112.8353 | 27.726 | 22.2613 | 193.1198
Continental Pit below 5410' NGVD29 (BMFOU) | 12-Pits | 103.7573 | 194.9103 | 1.8885 | 3.4125 | 303.9686
Exploration Permit | 4-Explo |  | 1.3147 |  |  | 1.3147
Exploration Permit Partially Reclaimed/Released | 4-Explo |  | 0.46489 |  |  | 0.46489
HB Water Treatment Plant (BMFOU) | 13-PreLaw | 1.9567 |  |  | 6.9449 | 8.9016
Historic Preservation (GMMIA) | 13-PreLaw |  |  |  | 16.9238 | 16.9238
Leach Pad | 11- Leach Pads | 8.9833 |  |  | 161.6074 | 170.5908
McQueen Townsite | 14-Misc | 22.641 |  |  | 10.0971 | 32.7381
Misc | 14-Misc | 154.6127 | 18.4419 | 23.8396 | 262.551 | 459.4451
Misc Berkeley Pit Overlook | 14-Misc |  |  |  | 2.9349 | 2.9349
Misc Partially Reclaimed/Released | 14-Misc |  | 10.7816 | 3.7109 | 22.4164 | 36.9089
Office | 14-Misc |  |  |  | 1.8159 | 1.8159
Precipitation Plant Area (EXEMPT) | 13-PreLaw |  |  |  | 73.1102 | 73.1102
Precipitation Plant RR | 13- PreLaw + 14-Misc | 0.87204 | 0.11921 |  | 1.0538 | 2.0451
Primary Crusher (EXEMPT) | 13-PreLaw |  |  |  | 30.4857 | 30.4857
Primary Crusher Partially Reclaimed/Released (EXEMPT) | 13-PreLaw |  |  |  | 13.7476 | 13.7476
RDS Access | 10-Dumps | 18.8664 |  |  | 16.545 | 35.4113
RDS East | 10-Dumps |  | 11.3901 | 37.7439 |  | 49.134
RDS East Crest | 10-Dumps |  | 23.2692 | 16.7231 |  | 39.9924
RDS East Partially Reclaimed/Released | 10-Dumps |  | 12.8588 | 73.6069 |  | 86.4657
RDS Great Northern | 10-Dumps |  |  |  | 66.7961 | 66.7961
RDS Hillcrest Partially Reclaimed/Released | 10-Dumps |  |  | 47.5128 |  | 47.5128
RDS Nalley Valley | 10-Dumps | 33.7909 |  |  | 49.3405 | 83.1314
RDS North East Partially Reclaimed/Released | 10-Dumps |  | 32.205 | 0.013236 |  | 32.2183
RDS Pittsmont | 10-Dumps | 64.138 |  |  | 19.4215 | 83.5595
RDS Pittsmont Crest | 10-Dumps | 23.3856 |  |  | 5.0759 | 28.4614
RDS Pittsmont Road | 14-Misc | 10.6583 |  |  | 1.6461 | 12.3044
RDS South Continental Pit | 10-Dumps | 3.1791 | 7.5987 |  |  | 10.7778
RDS South Continental Pit Crest | 10-Dumps | 6.1391 | 8.3681 |  |  | 14.5073
RDS Woodville Partially Reclaimed/Released | 10-Dumps |  |  | 2.1781 |  | 2.1781
Road | 13-PreLaw + 14-Misc | 61.237 | 1.8261 | 0.98616 | 65.5324 | 129.5817
Soil Stockpile | 14-Misc | 24.5671 |  |  | 1.6458 | 26.2129
Spillway Cut | 16-Spillway | 4.7359 |  |  |  | 4.7359
Undisturbed | 14-Misc | 343.4335 | 33.6947 | 162.5227 |  | 539.6509
YDTI Beach | 2-Beach | 541.1089 |  |  | 478.2165 | 1019.3254
YDTI East-West Crest | 1-Embankment | 5.6983 |  |  | 48.9809 | 54.6792
YDTI East-West Crest Road | 1-Embankment | 0.61558 |  |  | 4.9499 | 5.5654
YDTI East-West Embankment 2.7:1 | 1-Embankment | 1.7365 |  |  | 104.4165 | 106.153
YDTI East-West Embankment 2:1 | 1-Embankment |  |  |  | 41.9666 | 41.9666
YDTI East-West Embankment Riprap | 1-Embankment |  |  |  | 9.3814 | 9.3814
YDTI East-West Embankment Upstream 2.7:1 | 1-Embankment | 2.6159 |  |  | 23.8599 | 26.4759
YDTI North Transition Zone | 6-PostClosure | 80.68 |  |  |  | 80.68
YDTI North-South Crest | 1-Embankment | 26.6261 |  |  | 15.4604 | 42.0865
YDTI North-South Crest Road | 1-Embankment | 5.3819 |  |  | 2.028 | 7.41
YDTI North-South Embankment 2.7:1 | 1-Embankment | 68.438 |  |  | 107.7193 | 176.1572
YDTI North-South Embankment 2:1 | 1-Embankment |  |  |  | 28.0073 | 28.0073
YDTI North-South Embankment Riprap | 1-Embankment |  |  |  | 4.6484 | 4.6484
YDTI North-South Embankment Road | 1-Embankment | 2.999 |  |  | 3.5744 | 6.5734
YDTI North-South Embankment Upstream 2.7:1 | 1-Embankment | 17.2741 |  |  | 17.9422 | 35.2164
YDTI Equilibrium Pond | 6-PostClosure | 83.8807 |  |  |  | 83.8807
YDTI Tailings Transition Zone | 6-PostClosure | 369.5179 |  |  | 34.0652 | 403.5831
YDTI West Crest | 1-Embankment | 68.9719 |  |  | 6.2954 | 75.2673
YDTI West Crest Road | 1-Embankment | 7.7409 |  |  | 0.63298 | 8.3739
YDTI West Embankment 2.5:1 | 1-Embankment | 6.2517 |  |  | 0.98147 | 7.2332
YDTI West Embankment 2.7:1 | 1-Embankment | 2.6485 |  |  | 0.0001617 | 2.6486
YDTI West Embankment 3:1 | 1-Embankment | 22.0333 |  |  |  | 22.0333
YDTI West Embankment Upstream 2.7:1 | 1-Embankment | 55.1605 |  |  | 5.0767 | 60.2371
YDTI West Embankment WED | 6-PostClosure | 4.5749 |  |  |  | 4.5749
Grand Total |  | 2356.834 | 713.6411 | 455.1165 | 2610.0223 | 6135.6138
|  |  |  | EXEMPT | 212.4787
|  |  |  | BMFOU | 996.854
|  |  |  | GMMIA | 17
|  |  | Areas to bond at $500/acre |  | 1687.2699 | 843500 |  | (CONFIRMED ON SUMMARY PAGE)
Schedule
Post Closure Management and Monitoring
Capping Materials Volume Required
Material Inventory (based on 2018 Annual Report)
|  | Soil |  |  | LCY
|  |  | Moulton Road |  | 474700
|  |  | Bunker (Four Corners) |  | 90100
|  |  | East Continental |  | 0
|  |  |  | Total | 564800
Alluvium
|  |  | Cental Zone |  | 20000000
|  |  | Lunch Room |  | 1551000
|  |  |  | Total | 21551000
|  | Leach Capping |  |  | 0
Capping and Topsoil Balance (Table 9-3)
Reclamation Material Needed for Reclamation
MCY
| West Embankment |  |  | topsoil | 0.02
| Beach (at equilibrum) |  |  | topsoil | 0.59
0.61
| YDTI (at equilibrium) |  |  | capping | 9.61
| Rest of Mine |  |  | capping | 7.2
16.81
| Reclamation Material Available | [5 empty] | Required for Reclamation | Surplus
| Moulton Road |  |  | topsoil | 0.61 |  | 0.61 | 0
| Lunch Room |  |  | capping | 1.77
| Central Zone |  |  | capping | 20
[5 empty] | 21.77 |  | 16.81 | 4.96
Table 7-1 Estimated Annual YDTI Tailings Beach, Transition Zone, and Pond Areas
| Year | Closure Area1
|  | Reclaimable Tailings Beach (acres) | Pond (acres) | Transition Zone (acres)
| 2031 | 1122 | 462 | 220
| 2032 | 1122 | 462 | 220
| 2033 | 1179 | 411 | 213
| 2034 | 1206 | 387 | 211
| 2035 | 1216 | 378 | 209
| 2036 | 1225 | 371 | 208
| 2037 | 1233 | 363 | 207
| 2038 | 1244 | 354 | 206
| 2039 | 1251 | 347 | 206
| 2040 | 1262 | 336 | 206
| 2041 | 1269 | 329 | 206
| 2042 | 1279 | 319 | 206
| 2043 | 1296 | 304 | 204
| 2044 | 1305 | 297 | 202
| 2045 | 1318 | 286 | 200
| 2046 | 1325 | 279 | 199
| 2047 | 1337 | 269 | 197
| 2048 | 1351 | 258 | 195
| 2049 | 1363 | 248 | 193
| 2050 | 1370 | 242 | 192
| 2051 | 1383 | 231 | 189
| 2052 | 1385 | 229 | 189
| 2053 | 1418 | 210 | 176
| 2054 | 1485 | 173 | 145
| 2055 | 1560 | 133 | 111
| 2056 | 1600 | 110 | 93
| 2057 | 1648 | 85 | 71
| 2058 | 1672 | 71 | 60
| 2059 | 1692 | 61 | 51
| 20602 | 1682 | 66 | 56
| 2061 | 1701 | 56 | 47
| 2062 | 1710 | 51 | 43
| 2063 | 1705 | 53 | 45
| 2064 | 1710 | 51 | 43
| 2065 | 1710 | 51 | 42
| 2066 | 1710 | 51 | 43
| 2067 | 1711 | 51 | 42
| 2068 | 1710 | 51 | 43
| 2069 | 1725 | 43 | 36
| 2070 | 1729 | 40 | 34
| 2071 | 1727 | 41 | 35
| 2072 | 1729 | 41 | 34
| 2073 | 1740 | 34 | 29
| 2074 | 1738 | 36 | 30
| 2075 | 1738 | 36 | 30
| 2076 | 1737 | 36 | 30
| 2077 | 1743 | 33 | 27
| 2078 | 1745 | 32 | 27
| 2079 | 1743 | 33 | 28
| 2080 | 1738 | 36 | 30
| 2081 | 1745 | 32 | 27
| 2082 | 1743 | 33 | 28
1Based on a freshwater input of 1 MGPD. 2Equlibrium at 2060 is based on a modeled pond volume of 500 acre-feet .
Equipment Selection
Based on the location of the Montana Resources Mine, and the relative size of the reclamation project, it is assumed that the contractor would have
the following equipment and support personnel available:
1 - CAT 6020B Hydraulic Shovel
4 - CAT D10T Bulldozers
2 - CAT D8T Bulldozer
3 - CAT 740, 40 Ton Articulating Haul Trucks
10 - CAT 777, 100 Ton Haul Trucks
1 - CAT 14H Motor Grader
1 - CAT 980 Wheel Loader
1 - Cat 992G Wheel Loader
1 - Cat 330 Hydraulic Excavator
1 - Tractor Truck w/ Equipment Trailers
1 - 2,500 Gal Water Truck
1- CAT D6R Dozer
Note, equipment use is site specific and not all used at once
It's assumed reclamation work would be conducted in two shifts, 12 hours per day each, 5 days per week, 50 weeks per year
In addition, the following support equipment will be with the alluvium haul operation full time
Cat 16H Grader
2,500 Gal Water Truck
CAT D8T Bulldozer
Labor Related Costs
Third Party Construction Management Cost Reconciliation
| Category1 |  | CDM | Tetra Tech | Ch2M Hill | Envirocon | Avg2
| Project Manager |  | 182.13 | 177.3 | 165.83 | 116.48 | 160.435
| Project Engineer |  | 146.96 | 162.23 | 144.17 | 101.58 | 138.735
| Clerical and Administration |  | 83.26 | 52.38 | 60.31 | 90.26 | 71.5525
| Water Treatment Plant Operator/Field Engineer |  | 137.92 | 130.83 | 124.26 | 101.6 | 123.6525
Mechanic
| Laborers |  | 62
Security Personnel
Footnotes:
1. GSA Federal Supply Contractor Price List (2013-2014)
2. Eliminate high and low rates, average the balance
Care & Maintenance & Water Quality Sampling Oversight Team_3rd Party A&E
|  |  |  | Hourly Rate ($/hr) |  | Annual Salary ($/yr)
|  | Project Manager |  | 160.435 |  | 333704.8
|  | Project Engineer |  | 138.735 |  | 288568.8
|  | Clerical and Administration |  | 71.5525 |  | 148829.2
|  | Water Treatment Plant Operator |  | 123.6525 |  | 257197.2
|  | Mechanic |  | 46 |  | 95680
|  | Laborers |  | 62 |  | 128960
|  | Security Personnel |  | 40 |  | 83200
General Contractor (Earth Works) Management Personnel
|  | Prinicpal in Charge |  | 160225
|  | Project Manager |  | 132600
|  | Clerical and Administration |  | 60775
|  | Site Engineer |  | 116025
|  | Health and Safety Officer |  | 104975
|  | Laborer |  | 83200
|  | Superintendent |  | 0
|  | Service Mechanic |  | 0

## Rates 2020
2020 Reclamation Bond Equipment Rates
|  |  |  | Equipment |  | Labor |  |  |  | Increase
| Enter Profit: | 10% |  | EquipmentWatch | Profit | State Wages | O & P | Total | Total | over 1997
|  |  |  | (1) | (2) | (3) | (4) |  |  | rates
WHEEL AND CRAWLER TRACTORS
| Manufacturer | Model | Blade
| CAT | D11T | U | 602.82 | 60.282 | 53.35 | 26.3656 | 742.8176 | 742.82 | 13.21%
| CAT | D10T2 | Semi-U | 380.56 | 38.056 | 53.35 | 26.3656 | 498.3316 | 498.33 | 14.85%
| CAT | D9T | Semi-U | 306.09 | 30.609 | 53.35 | 26.3656 | 416.4146 | 416.41 | 15.85%
| CAT | D8T | Semi-U | 229.9 | 22.99 | 53.35 | 26.3656 | 332.6056 | 332.61 | 17.43%
| CAT | D7E LGP | Semi-U | 136.93 | 13.693 | 53.35 | 26.3656 | 230.3386 | 230.34 | 21.05%
| CAT | D6T LGP | Semi-U | 149.05 | 14.905 | 53.35 | 26.3656 | 243.6706 | 243.67 | 20.39%
WHEEL AND CRAWLER LOADERS
| Manufacturer | Model | Bucket (CY)
| CAT | 992K | 16 | 452.75 | 45.275 | 53.35 | 26.3656 | 577.7406 | 577.74 | 14.16%
| CAT | 988K | 8 | 211.72 | 21.172 | 53.35 | 26.3656 | 312.6076 | 312.61 | 17.93%
| CAT | 980K | 7 | 104.25 | 10.425 | 53.35 | 26.3656 | 194.3906 | 194.39
| CAT | 950K | 4 | 86.24 | 8.624 | 53.35 | 26.3656 | 174.5796 | 174.58
EXCAVATORS
| Manufacturer | Model | Bucket (CY)
| CAT | 6040B | 16 | 500 | 50 | 53.35 | 26.3656 | 629.7156 | 629.72
| CAT | 374 DL | 5 | 275.47 | 27.547 | 53.35 | 26.3656 | 382.7326 | 382.73 | 16.39%
| CAT | 349F | 2.5 | 226.87 | 22.687 | 53.35 | 26.3656 | 329.2726 | 329.27 | 17.5%
| CAT | 336F | 1.6 | 166.66 | 16.666 | 53.35 | 26.3656 | 263.0416 | 263.04 | 19.56%
| CAT | 323F | 1.5 | 98.47 | 9.847 | 53.35 | 26.3656 | 188.0326 | 188.03 | 23.85%
| CAT | 320F | 1.2 | 76.83 | 7.683 | 53.35 | 26.3656 | 164.2286 | 164.23
| CAT | 315F | 0.8 | 93.27 | 9.327 | 53.35 | 26.3656 | 182.3126 | 182.31
BACKHOES LOADERS
| Manufacturer | Model | Bucket (CY)
| CAT (2WD) | 416F | 1 | 40.59 | 4.059 | 53.35 | 26.3656 | 124.3646 | 124.36 | 32.38%
| CAT (4WD) | 430E | 1.3 | 63.36 | 6.336 | 53.35 | 26.3656 | 149.4116 | 149.41 | 28.02%
| CAT (4WD) | 450F | 1.75 | 77.34 | 7.734 | 53.35 | 26.3656 | 164.7896 | 164.79 | 26.09%
SCRAPERS
| Manufacturer | Model | Capacity (CY)
| CAT | 631K | 24/34 | 265.19 | 26.519 | 53.35 | 26.3656 | 371.4246 | 371.42 | 16.6%
| CAT | 627K | 16/22 | 289.41 | 28.941 | 53.35 | 26.3656 | 398.0666 | 398.07 | 16.14%
| CAT | 637K | 24/34 | 265.19 | 26.519 | 53.35 | 26.3656 | 371.4246 | 371.42 | 16.6%
| CAT | 657G | 32/44 | 534.25 | 53.425 | 53.35 | 26.3656 | 667.3906 | 667.39
MOTOR-GRADERS
| Manufacturer | Model | Blade (FT)
| CAT | 16M3 | 16 | 139.43 | 13.943 | 53.35 | 26.3656 | 233.0886 | 233.09 | 20.91%
| CAT | 14M3 | 14 | 104.49 | 10.449 | 53.35 | 26.3656 | 194.6546 | 194.65 | 23.32%
| CAT | 12M3 | 12 | 97.48 | 9.748 | 53.35 | 26.3656 | 186.9436 | 186.94 | 23.94%
WATER TRUCKS
| Manufacturer | Model | Capacity (Gal)
| ON-HWY (DIESEL) | Water | 2500 | 27.88 | 2.788 | 50.05 | 24.7347 | 105.4527 | 105.45 | 35.31%
| OFF-HWY (DIESEL) | Water | 3500 | 43.49 | 4.349 | 50.05 | 24.7347 | 122.6237 | 122.62 | 31.09%
| OFF-HWY (DIESEL) | Water | 4000 | 51.13 | 5.113 | 50.05 | 24.7347 | 131.0277 | 131.03 | 29.5%
HAUL TRUCKS
| Manufacturer | Model | Capacity (LCY)
| Diesel Powered | 6x4 | 10-12 | 62.56 | 6.256 | 50.05 | 24.7347 | 143.6007 | 143.6 | 27.52%
| Diesel Powered | 8x4 | 15-18 | 80.71 | 8.071 | 50.05 | 24.7347 | 163.5657 | 163.57
| CAT | 770G | 40 | 123.6 | 12.36 | 50.05 | 24.7347 | 210.7447 | 210.74 | 21.36%
| CAT | 772G | 60 | 127.58 | 12.758 | 50.05 | 24.7347 | 215.1227 | 215.12 | 21.11%
| CAT | 777G | 100 | 357.82 | 35.782 | 50.05 | 24.7347 | 468.3867 | 468.39 | 14.84%
| CAT | 725C | 14-19 | 108.07 | 10.807 | 50.05 | 24.7347 | 193.6617 | 193.66
| CAT | 730C | 17-22 | 123.96 | 12.396 | 50.05 | 24.7347 | 211.1407 | 211.14
| CAT | 735C | 19-26 | 151.77 | 15.177 | 50.05 | 24.7347 | 241.7317 | 241.73
| CAT | 740C EJ | 24-31 | 158.97 | 15.897 | 50.05 | 24.7347 | 249.6517 | 249.65
MISC
| Truck Tractor w/Equipment Trailer |  |  | 125 | 12.5 | 50.05 | 24.7347 | 212.2847 | 212.28
LABOR FORCE W/PU |  |  | Capacity (Tons)
| Service Truck w/Laborer | 4X4 Crew Cab | 1 1/2 | 20.06 | 2.006 | 46.805 | 23.131 | 92.002 | 92
| Superintendent w/PU | 4x4 Conventional | 1 | 14.73 | 1.473 | 95 | 46.949 | 158.152 | 158.15
| Laborer |  |  |  |  | 46.805 | 23.131 | 69.936 | 69.94
|  | NOTES: | [7 empty] | 22.46%
(1) This rate is internal rate charge - total ownership, overhead and operating cost from EquipmentWatch's
Cost Reference Guide for Construction Equipment
(1) Assumes +/- 1,300 annual use hours
(2) Profit of 10 percent of the base rate is assumed.
(3) Wages are derived from the prevailing wage plus fringe benefits obtained from the
Montana Prevailing Wage for Heavy Construction Services
Montana Department of Labor and Industry, Effective January 2, 2020
It is assumed that the operation will work 5 days a week 10 hours per day (40 reg hrs +10 overtime hours @ 1.5 the hourly rate)
To account for the overtime pay, a payroll cost factor of 110% is applied (ref. RS Means Heavy Construction Cost Data for 2019, page 705)
(4) An overhead and profit of 49.42% has been applied to the wage rate. This
percentage was obtained from RS Means Heavy Construction Cost Data for 2019
This includes average worker's compensation of 7.12%, (ref. MT State Fund Code 6217) an average fixed
overhead of 18.3%, overhead of 14%, and a profit of 10%.
(5) O & O costs based on price of diesel = $2.25/gal
The diesel price accounts for an increase in crude prices or delivery cost

## ITEM 1 YDTI Embankment Closure
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
Item 1 Cost Summary for YDTI Embankment
Direct Costs |  | Task 1 | Task 2 | Task 3
|  | N-S Embankment | E-W Embankment | West Embankment
| Reslope Embankment | 1337291.3424 | 24099.2922 | 137098.1954
| Construct Rip Rap Slope by Precipitation Plant | - | pre-1974 | -
| Rip Crest | 26537.127 | 5679.2704 | 68741.5597
| Construct Surface Water Collection Ditches | 74587.7925 | 63112.7475 | -
| Haul & Spread Alluvium and Soil | 2612664.591 | 261176.3855 | 6511555.8068
| Alluvium Testing & Amendments | 520332.7119 | 45594.8 | 755148.2395
| Establish Vegetation & Weed Control | 177062.85 | 15261.3 | 240864.9
| Total | 4748476.4148 | 414923.7955 | 7713408.7014
| Item 1- YDTI Embankments Total Cost |  |  | 12876808.9117
| Pre-1974 Bond |  |  | 213000
ACREAGES FROM 2025 SITE PLAN MAP
| Feature | OP 00030A | OP 00041 | OP 00108 | OP 00030 | Grand Total
| YDTI North-South Crest | 26.6261 |  |  | 15.4604 | 42.0865
| YDTI North-South Crest Road | 5.3819 |  |  | 2.028 | 7.41
| YDTI North-South Embankment 2.7:1 | 68.438 |  |  | 107.7193 | 176.1572
| YDTI North-South Embankment 2:1 |  |  |  | 28.0073 | 28.0073
| YDTI North-South Embankment Riprap |  |  |  | 4.6484 | 4.6484
| YDTI North-South Embankment Road | 2.999 |  |  | 3.5744 | 6.5734
| YDTI North-South Embankment Upstream 2.7:1 | 17.2741 |  |  | 17.9422 | 35.2164
| YDTI East-West Crest | 5.6983 |  |  | 48.9809 | 54.6792
| YDTI East-West Crest Road | 0.61558 |  |  | 4.9499 | 5.5654
| YDTI East-West Embankment 2.7:1 | 1.7365 |  |  | 104.4165 | 106.153
| YDTI East-West Embankment 2:1 |  |  |  | 41.9666 | 41.9666
| YDTI East-West Embankment Riprap |  |  |  | 9.3814 | 9.3814
| YDTI East-West Embankment Upstream 2.7:1 | 2.6159 |  |  | 23.8599 | 26.4759
| YDTI West Crest | 68.9719 |  |  | 6.2954 | 75.2673
| YDTI West Crest Road | 7.7409 |  |  | 0.63298 | 8.3739
| YDTI West Embankment 2.5:1 | 6.2517 |  |  | 0.98147 | 7.2332
| YDTI West Embankment 2.7:1 | 2.6485 |  |  | 0.0001617 | 2.6486
| YDTI West Embankment 3:1 | 22.0333 |  |  |  | 22.0333
| YDTI West Embankment Upstream 2.7:1 | 55.1605 |  |  | 5.0767 | 60.2371
| GRAND TOTAL | 294.1922 |  |  | 425.9218 | 720.114
| PRE-1974 BOND |  |  |  | 213000
| ACRES FOR BOND CALCULATIONS BELOW | 294.1922
Task 1 Reclaim N-S Embankment
Task 2 Reclaim E-W Embankment
Task 3 Reclaim West Embankment
Reslope Embankments
Assumptions/Observations:
The downstream face of N-S Embankment will not be covered by the North RDS in 2025, so the surface must be resloped prior to capping and revegetation
The downstream face of E-W Embankment must be resloped prior to capping and revegetation
The downstream West Embankment slopes were constructed to either 3H:1V or 2.5H:1V, therefore no resloping is required
The tailings beach would not reach its full extent (under Amendment 010) in year 2025.
The upstream face (between beach surface and dam crest) will need to be considered for each embankment, an elevation difference of 50 feet is assumed
The access road (50 ft wide) along the top of each crest will remain for post closure monitoring
The N-S Embankment is approximately 6,500 feet long, in 2025 it will be constructed to the 6,450 ft elevation
The embankment is constructed using downstream construction method with heavy rock fill
The N-S Embankment is constructed in 50 to 100-ft lifts of waste rock at the angle of repose
As the embankment height increases to the 6450 foot crest elevation, a new ramp will be constructed, aiding in North RDS construction
The E-W Embankment is approximately 5,500 feet long, in 2025 it will be constructed to the 6,450 ft elevation
The West Embankment is approximately 6,800 feet long, in 2025 it will be constructed to the 6,450 ft elevation
The reclamation plan calls for downstream embankment slope to be reduced to either a 2H:1V or 2.7H:1V slope and capping with 20 inches of amended alluvium
The section of the embankment adjacent to the Precipitation Plant will be resloped to 2H:1V and capped with 20 inches of alluvium
The section very close to the Precipitation Plant will be covered with course rockfill (riprap) that is nonacid generating sourced from off-site
There are no slopes within OP 00030A that need to be reduced to 2H:1V
The grading calculations only apply to the slopes which occur within OP 00030A
See 2025 Site Plan Map for permit boundaries and the defined boundaries for each embankment limb
Based on the 2025 Site Plan Map and measurements on satellite imagery, the following dimensions are assumed for bonding:
|  | N-S Embankment | E-W Embankment | West Embankment
| Downstream (D/S) Area (ac) | 68.4 | 1.7 | N/A (30.9) | West D/S is at final grade
| Upstream (U/S) Area (ac) | 17.3 | 2.6 | 55.2
Crest Length Estimates:
| Total Crest Length | 6500 | 5500 | 6800
Crest Length within OP#00030A:
| D/S Face | 4800 | 500 | N/A (6800) | West D/S is at final grade
| U/S Face | 4000 | 1000 | 6400
Embankment Height Estimates: |  | N-S Embankment | E-W Embankment | West Embankment
| U/S Face (from crest to tailings in 2025) | 50 | 50 | 50
| D/S Face | see below | see below | N/A | West D/S is at final grade
Entire Facility- Amend 010 Design Report
|  | N-S Embankment |  |  |  | E-W Embankment
|  | From Crest to ground surface |  |  |  | From Crest to ground surface
|  | D/S Face, X-Section (from Amend 010 Design Report, 10/6/17) |  |  |  | D/S Face, X-Section (from Amend 010 Design Report, 10/6/17)
|  | X-Section | Height (ft) |  |  | X-Section | Height (ft)
| inside OP#00030 | 8+00 N | 0 |  | West Embank | 53+00 NW | 175
| inside OP#00030 | 13+00 N | 350 |  |  | 48+00 NW | 175
| inside OP#00030 | 18+00 N | 350 |  | inside OP#00030 | 43+00 NW | 175
| inside OP#00030 | 23+00 N | 350 |  | inside OP#00030 | 38+00 NW | 250
|  | 28+00 N | 400 |  | inside OP#00030 | 33+00 NW | 275
|  | 33+00 N | 400 |  | inside OP#00030 | 28+00 NW | 250
|  | 38+00 N | 400 |  | inside OP#00030 | 23+00 NW | 250
|  | 43+00 N | 400 |  | inside OP#00030 | 18+00 NW | 250
|  | 48+00 N | 450 |  | inside OP#00030 | 12+00 W | 625
|  | 53+00 N | 650 |  | inside OP#00030 | 08+00 W | 725
|  | 58+00 N | 775 |  | inside OP#00030 | 03+00 W | 800
|  | 63+00 N | 775 |  | inside OP#00030 | 0+00 W | 775
|  | Average | 441.6667 |  |  | Average | 359.0909
OP#00030A Only- 2025 Site Plan Map
|  | N-S Embankment |  |  |  | E-W Embankment
|  | From Crest to mid-level bench, remaining roads, or spillway edge |  |  |  | From Crest to lower road near WED extraction pond
|  | D/S Face, X-Section (from Amend 010 Design Report, 10/6/17) |  |  |  | D/S Face, X-Section (from Amend 010 Design Report, 10/6/17)
|  | X-Section | Height (ft) |  |  | X-Section | Height (ft)
|  | 23+00 N | 200 |  |  | 48+00 NW | 25
|  | 28+00 N | 200 |  |  | Average | 25
|  | 33+00 N | 200
|  | 38+00 N | 200 |  |  | All other sections contained within OP#00030
|  | 43+00 N | 200
|  | 48+00 N | 200
|  | 53+00 N | 150
|  | 58+00 N | 120
|  | 63+00 N | 100
|  | Average | 174.4444
|  |  | Task 1 | Task 1 | Task 2 | Task 2 | Task 3 | Task 3
|  |  | N-S Embank D/S | N-S Embank U/S | E-W Embank D/S | E-W Embank U/S | West Embank D/S | West Embank U/S
Crest length (length of Slope Reduction) in OP#00030A (FT) |  |  | 4800 | 4000 | 500 | 1000 | Resloping N/A | 6400
The cut, fill, and rehandle volume per foot of crest length from AOR(LCY/FT) |  |  | 439.726 | 36.125 | 9.0312 | 36.125 | - | 36.125 | (Ref Exhibit 3)
The total cut, fill, and rehandle volume is (LCY) |  |  | 2110684.7407 | 144500 | 4515.625 | 36125 | - | 231200
Dump-Slope Dozer Production Calculation |  |  | Task 1 | Task 1 | Task 2 | Task 2 | Task 3 | Task 3
Machine Properties |  |  | N-S Embankment D/S | N-S Embankment U/S | E-W Embankment D/S | E-W Embankment U/S | West Embankment D/S | West Embankment U/S
| Machine |  | D10T | D10T | D10T | D10T |  | D10T
| Blade |  | SU | SU | SU | SU |  | SU
| Dual Tilt |  | Yes | Yes | Yes | Yes |  | Yes
| % Availability |  | 90% | 90% | 90% | 90% |  | 90%
| Wt (LBS) |  | 146950 | 146950 | 146950 | 146950 |  | 146950
| Shoe Width (IN) |  | 28 | 28 | 28 | 28 |  | 28
| Density (LBS/LCY) |  | 3300 | 3300 | 3300 | 3300 |  | 3300
| Dozeability |  | 1 | 1 | 1 | 1 |  | 1
Derating Factors
| Attitude |  | 6450 | 6450 | 6450 | 6450 |  | 6450
| Visibility |  | 1 | 1 | 1 | 1 |  | 1
| Job Effi |  | 83% | 83% | 83% | 83% |  | 83%
| Skill Level |  | 75% | 75% | 75% | 75% |  | 75%
Input Values
| Push Distance (FT) |  | 100 | 100 | 100 | 100 |  | 100
| Push Slope |  | 0% | 0% | 0% | 0% |  | 0%
| Volume of Material (LCY) |  | 2110684.7407 | 144500 | 4515.625 | 36125 |  | 231200
Output Values
| Productivity (LCY/HR) |  | 1500 | 1500 | 1500 | 1500 |  | 1500
| Adjusted Productivity (LCY/HR) |  | 840.375 | 840.375 | 840.375 | 840.375 |  | 840.375
| Total Hours (1 machine) |  | 2511.5987 | 171.947 | 5.3733 | 42.9868 |  | 275.1153
| Total Hours (4 machines) |  | 627.8997 | 42.9868 | 1.3433 | 10.7467 |  | 68.7788
| Total Cost (4 machines) |  | 1251604.9702 | 85686.3722 | 2677.6991 | 21421.593 |  | 137098.1954
| $/CY |  | 0.59299 | 0.59299 | 0.59299 | 0.59299 |  | 0.59299
| Reslope Embankments, subtotal |  | 1251604.9702 | 85686.3722 | 2677.6991 | 21421.593 |  | 137098.1954
|  |  | Task 1 | Task 2 | Task 3
|  |  | N-S Embankment | E-W Embankment | West Embankment
Reslope Embankments, Total Cost |  |  | 1337291.3424 | 24099.2922 | 137098.1954
Construct Rip Rap Slope by Precipitation Plant
Assumptions/Observations:
To reclaim the angle-of-repose slope adjacent to the Precipitation Plant, DEQ assumes rip rap would be placed along the toe (see Amendment 10, Exhibit 3)
The rip rap slope protection would be placed just along the toe of the embankment 2,000 feet long by 200 feet high by 3 feet thick
The rip rap would be 18 inch diameter minimum, non-acid generating rock, and would not be covered with topsoil after placement
Rip rap with these characteristics is not available at MR, therefore it will likely have to be trucked in possibly from the Pipestone Quarry
The rip rap is placed by end dumping, with bulldozer assistance and machine placed with a clamsheel bucket
Estimated Volume of Rip Rap Required (LCY) |  | 44444.4444
|  | Task 1 | Task 2 | Task 3
|  | N-S Embankment | E-W Embankment | West Embankment | Total
Riprap Area (AC) (not slope corrected) |  | 4.6484 | 9.3814 | - | 14.0298
All riprap acres occur within Permit 00030 (Pre-1974), which is limited to a bond of $500/acre
This Pre-1974 cost is accounted for at the top of this tab, no additional calculations related to this task
Construct Rip Rap Slope by Precipitation Plant, Total Cost |  | 0 | 0 | 0
Rip Crests
Assumptions/Observations:
The N-S Embankment is approximately 6,500 feet long, in 2025 it will be constructed to the 6,450 ft elevation
The embankment is constructed using downstream construction method with heavy rock fill
The N-S Embankment is constructed in 50 to 100-ft lifts of waste rock at the angle of repose
As the embankment height increases to the 6450 foot crest elevation, a new ramp will be constructed, aiding in North RDS construction
The E-W Embankment is approximately 5,500 feet long, in 2025 it will be constructed to the 6,450 ft elevation
The West Embankment is approximately 6,800 feet long, in 2025 it will be constructed to the 6,450 ft elevation
The crest on each embankment limb will require ripping prior to soil placement
The access road (50 ft wide) along the top of each crest will remain for post closure monitoring
Assume a D10T dozer ripping production of 1/2 acre per hour
|  | Task 1 | Task 2 | Task 3
|  | N-S Embankment | E-W Embankment | West Embankment
Road Remaining (not reclaimed) (AC) |  | 8.3809 | 0.61558 | 7.7409
Estimated Crest Area to Reclaim (AC) |  | 26.6261 | 5.6983 | 68.9719
D10T Ripping Production (AC/HR) |  | 0.5 | 0.5 | 0.5
Job Hours (HR) |  | 53.2521 | 11.3966 | 137.9439
Total Cost |  | 26537.127 | 5679.2704 | 68741.5597
Rip Crest, Total Cost |  | 26537.127 | 5679.2704 | 68741.5597
Construct Surface Water Collection Ditches
Assumptions/Observations:
To breakup the long reclaimed slopes, benches or drainage swales will be cut every 100 feet
After the slopes are recontoured to the final configuration, a survey party will locate the surface water ditches
To construct the ditches along the slope, a D8T dozer would walk back out to the slopes, and using the blade push the muck downslope creating a berm with a "U" bottom
For the N-S Embankment, approximately 19,500 feet (6,500 X 3)of ditches would need to be constructed (assuming ~350 ft high slope)
For the E-W Embankment, approximately 16,500 feet (5,500 X 3)of ditches would need to be constructed (assuming ~360 ft high slope)
The downstream West Embankment abuts against (toes into) native ground , therefore no surface water ditches will be necessary
Based on discussion with another mining company, a D8T dozer can cut, shape, and finish blading 100 feet of ditch per hour
A survey party fee of 15% is also included
|  | Task 1 | Task 2 | Task 3
|  | N-S Embankment | E-W Embankment | West Embankment
Estimated Length of Surface Water Ditches (FT) |  | 19500 | 16500 | NA
D8T Production Rate (FT/HR) |  | 100 | 100 | -
Job Hours (HR) |  | 195 | 165 | -
Total Construction Cost |  | 64858.95 | 54880.65 | -
15% Survey Party Fee |  | 9728.8425 | 8232.0975 | -
Total Cost |  | 74587.7925 | 63112.7475 | -
Construct Surface Water Collection Ditches, Total Cost |  | 74587.7925 | 63112.7475 | 0
Haul & Spread Alluvium and Soil
Assumptions:
According to the amendment application, alluvium will be sourced from the Central Zone.
Soil will be sourced from the Central Zone, Lunch Room Stockpile, or the Moulton Road Stockpiles
The N-S embankment would be covered with alluvium (20 inches 2.7H:1V slopes, 36 inches 2H:1V slopes, 28 inches on crest)
The E-W embankment would be covered with alluvium (20 inches 2.7H:1V slopes, 36 inches 2H:1V slopes, 28 inches on crest)
The West Embankment would be covered with 36 inches of alluvium + 6 inches of soil on 3H:1V slopes, per the Amendment 010 Reclamation Plan
Permit 00030A Embankment and Crest acreage, soil thickness, and volume are as follows:
|  | Task 1 | Task 1 | Task 1 | Task 2 | Task 2 | Task 2 | Task 3 | Task 3 | Task 3 | Task 3 | Task 3
|  | N-S Embankment | N-S Embankment | N-S Embankment | E-W Embankment | E-W Embankment | E-W Embankment | West Embankment | West Embankment | West Embankment | West Embankment | West Embankment
|  | Acreage | Alluv Thick (Inches) | Alluv Volume (LCY) | Acreage | Alluv Thick (Inches) | Alluv Volume (LCY) | Acreage | Soil Thick (Inches) | Soil Volume (LCY) | Alluv Thick (Inches) | Alluv Volume (LCY)
2H:1V Slope Area (Corrected for slope) |  | 0 | - | - | 0 | 36 | - | 0 | - | - | 36 | 0
2.5H:1V Slope Area (Corrected for slope) |  | 0 | - | - | 0 | - | - | 6.804 | - | - | 36 | 32931.36
2.7H:1V Slope Downstream Area (Corrected for slope) |  | 72.9828 | 20 | 196242.64 | 1.7 | 20 | 4571.1111 | 2.7742 | - | - | 36 | 13427.128
2.7H:1V Slope Upstream Area (Corrected for slope) |  | 18.4591 | 20 | 49634.4689 | 2.7742 | 20 | 7459.5156 | 58.8984 | - | - | 36 | 285068.256
3H:1V Slope Area (Corrected for slope) |  | 0 | - | - | 0 | - | - | 23.1 | 6 | 18634 | 36 | 111804
Crest Area (Not corrected for slope) |  | 26.6 | 28 | 100134.2222 | 5.7 | 28 | 21457.3333 | 69 | - | - | 28 | 259746.6667
| TOTAL | 118.0419 |  | 346011.3311 | 10.1742 |  | 33487.96 | 160.5766 |  | 18634 |  | 702977.4107
|  | Task 1 | Task 2 | Task 3
|  | N-S Embankment | E-W Embankment | West Embankment
Area of Embankments and Crests getting alluvium (AC) |  | 118.0419 | 10.1742 | 160.5766
Alluvium volume to cover embankments and crests (LCY) |  | 346011.3311 | 33487.96 | 702977.4107
Contingency Volume (15% extra)(LCY) |  | 397913.0308 | 38511.154 | 808424.0223
Density of alluvium (LBS/LCY) |  | 3300 | 3300 | 3300
Weight of alluvium to cover the embankment (TONS) |  | 656556.5008 | 63543.4041 | 1333899.6367
Alluvium Haul Distance(4% grade, 10% resist) (FT) |  | 13200 | 14250 | 19535 | (to Central Zone)
Area of Embankments and Crests getting soil (AC) |  | 0 | 0 | 23.1
Soil volume to cover embankments and crests (LCY) |  | 0 | 0 | 18634
Contingency Volume (15% extra)(LCY) |  | 0 | 0 | 21429.1
Density of soil (LBS/LCY) |  | 2800 | 2800 | 2800
Weight of soil to cover the embankment (TONS) |  | 0 | 0 | 30000.74
HAULING ALLUVIUM
DEQ assumes that the Cat 6020B Hydraulic Excavator and 10-Cat 777 Haul Trucks will be used to mine, load, and haul the alluvium
With respect to spreading the alluvium, assume two Cat 10T are with the hauling operation, spreading the alluvium takes twice the hauling hours
Cat Edition 45 p.10-55 Cat 777G Haul Truck Rimpull-Speed-Gradeability Curve Loaded Speed (MPH) |  |  |  | 12
Cat Edition 45 p.10-55 Cat 777G Haul Truck Rimpull-Speed-Gradeability Curve Empty Speed (MPH) |  |  |  | 20
|  | Task 1 | Task 2 | Task 3
|  | N-S Embankment | E-W Embankment | West Embankment
Hauler Cycle Time (MIN)
Load with Exchange |  | 2.45 | 2.45 | 2.45
Haul |  | 12.5 | 13.4943 | 18.4991
Dump and Maneuver |  | 1.6 | 1.6 | 1.6
Return |  | 7.5 | 8.0966 | 11.0994
Potential Cycle Time |  | 24.05 | 25.6409 | 33.6485
Wait on Slow Hauler |  | 0 | 0 | 0
Wait to Load, Bunching AVG |  | 0 | 0 | 0
Total Cycle Time (MIN) |  | 24.05 | 25.6409 | 33.6485
Cycles per 60 min Hour (CYCLES/HR) |  | 2.4948 | 2.34 | 1.7831
Bunching Calc |  | 21.6 | 23.1909 | 31.1985
# of Trucks (hauler capabilities) |  | 8.8163 | 9.4657 | 12.7341
Cat 777G Average Capacity (LCY) |  | 77 | 77 | 77
Hauler Potential Production Per Hour (LCY/HR) |  | 192.0998 | 180.1808 | 137.3019
6020B Passes per Hauler |  | 5 | 5 | 5 | 5.1333
Loader Cycle Time (MIN) |  | 0.7 | 0.7 | 0.7
Load Time Truck (MIN) |  | 3.5 | 3.5 | 3.5
Number of Trucks Required (EA) |  | 6.8714 | 7.326 | 9.6139 | # of Trucks (loader capabilities)
Production Rate (LCY/MIN) |  | 22 | 22 | 22
Hourly Production (LCY/HR) |  | 1320 | 1320 | 1320
Efficiency Factor |  | 0.83 | 0.83 | 0.83
Availability |  | 0.9 | 0.9 | 0.9
Adjusted Hourly Production (LCY/HR) |  | 986.04 | 986.04 | 986.04
Hours Required (HR) |  | 403.5465 | 39.0564 | 819.8694
Task 1 | N-S Embankment
| Qty | Model | Hourly Cost Each Unit | Operating Hours | Total Cost | $ per Ton | $ per LCY
Loaders: | 1 | 6020B | 629.72 | 403.5465 | 254121.3275 | 0.38705 | 0.63864
Haulers: | 6.8714 | 777D | 468.39 | 2772.9412 | 1298817.9419 | 1.9782 | 3.2641
Support: | 1 | 14H Motor Grader | 194.65 | 403.5465 | 78550.3341 | 0.11964 | 0.19741
| 1 | D8T | 332.61 | 403.5465 | 134223.6148 | 0.20444 | 0.33732
| 1 | 2,500 gal Water Truck | 105.45 | 403.5465 | 42553.9827 | 0.064814 | 0.10694
Fleet Totals | 10.8714 |  |  | 4387.1274 | 1808267.201 | 2.7542 | 4.5444
Task 2 | E-W Embankment
| Qty | Model | Hourly Cost Each Unit | Operating Hours | Total Cost | $ per Ton | $ per LCY
Loaders: | 1 | 6020B | 629.72 | 39.0564 | 24594.5843 | 0.38705 | 0.63864
Haulers: | 7.326 | 777D | 468.39 | 286.126 | 134018.5728 | 2.1091 | 3.48
Support: | 1 | 14H Motor Grader | 194.65 | 39.0564 | 7602.3246 | 0.11964 | 0.19741
| 1 | D8T | 332.61 | 39.0564 | 12990.5429 | 0.20444 | 0.33732
| 1 | 2,500 gal Water Truck | 105.45 | 39.0564 | 4118.4954 | 0.064814 | 0.10694
Fleet Totals | 11.326 |  |  | 442.3516 | 183324.5199 | 2.885 | 4.7603
Task 3 | West Embankment
| Qty | Model | Hourly Cost Each Unit | Operating Hours | Total Cost | $ per Ton | $ per LCY
Loaders: | 1 | 6020B | 629.72 | 819.8694 | 516288.158 | 0.38705 | 0.63864
Haulers: | 9.6139 | 777D | 468.39 | 7882.1037 | 3691898.5658 | 2.7677 | 4.5668
Support: | 1 | 14H Motor Grader | 194.65 | 819.8694 | 159587.5785 | 0.11964 | 0.19741
| 1 | D8T | 332.61 | 819.8694 | 272696.7608 | 0.20444 | 0.33732
| 1 | 2,500 gal Water Truck | 105.45 | 819.8694 | 86455.2281 | 0.064814 | 0.10694
Fleet Totals | 13.6139 |  |  | 11161.5813 | 4726926.2913 | 3.5437 | 5.8471
SPREADING ALLUVIUM
With respect to spreading the alluvium, assume two Cat D10T are with the hauling operation, spreading the alluvium takes twice the hauling hours
|  | Task 1 | Task 2 | Task 3
|  | N-S Embankment | E-W Embankment | West Embankment
Hauling Hours (HR) |  | 403.5465 | 39.0564 | 819.8694
Spreading Job Hours (HR) |  | 807.0931 | 78.1128 | 1639.7388
Equipment Cost (Cat D10T) |  | 804397.3901 | 77851.8655 | 1634262.0706 |  | GRAND TOTAL
| Total | 804397.3901 | 77851.8655 | 1634262.0706 |  | 2516511.3262
HAULING SOIL (WEST EMBANKMENT ONLY)
Since the topsoil stockpiles are close to the West Embankment, smaller equipment can be used
Assume a Cat 980G loader and three Cat 740 Articulating trucks are used to load and transfere the soil to the embankment
With respect to spreading the topsoil, assume one Cat D8T is with the hauling operation at twice the hauling hours
The estimated haul distance at a 0% grade (FT) |  | 7920 | (Moulton RoadTopsoil)
Cat Edition 45 p.1-24 Cat 740 Haul Truck Rimpull-Speed-Gradeability Curve Loaded Speed (MPH) |  |  |  | 20
Cat Edition 45 p.1-24 Cat 740 Haul Truck Rimpull-Speed-Gradeability Curve Empty Speed (MPH) |  |  |  | 20
Task 3
Hauler Cycle Time (MIN) |  | West Embankment
Load with Exchange |  | 2.45
Haul |  | 4.5
Dump and Maneuver |  | 1.6
Return |  | 4.5
Potential Cycle Time |  | 13.05
Wait on Slow Hauler |  | 0
Wait to Load, Bunching AVG |  | 0
Total Cycle Time (MIN) |  | 13.05
Cycles per 60 min Hour (CYCLES/HR) |  | 4.5977
Bunching Calc |  | 10.6
# of Trucks (hauler capabilities) |  | 4.3265
Cat 740 Average Capacity (LCY) |  | 31
Hauler Potential Production Per Hour (LCY/HR) |  | 142.5287
Cat 980 Passes per Hauler |  | 4 | 4.4286
Loader Cycle Time (MIN) |  | 0.6
Load Time Truck (MIN) |  | 2.4
Number of Trucks Required (EA) |  | 5.4375 | 3 | Contractor only has 3 trucks available, see Inputs tab
Production Rate (LCY/MIN) |  | 7.1264
Hourly Production (LCY/HR) |  | 427.5862
Efficiency Factor |  | 0.83
Availability |  | 0.9
Adjusted Hourly Production (LCY/HR) |  | 319.4069
Hours Required (HR) |  | 67.0903
Task 3 | West Embankment
| Qty | Model | Hourly Cost Each Unit | Operating Hours | Total Cost | $ per Ton | $ per LCY
Loaders: | 1 | 980 | 194.39 | 67.0903 | 13041.6807 | 0.43471 | 0.6086
Haulers: | 3 | 740 | 249.65 | 201.2709 | 50247.2696 | 1.6749 | 2.3448
Support: | 1 | 14H Motor Grader | 194.65 | 67.0903 | 13059.1241 | 0.43529 | 0.60941
| 1 | D8T | 332.61 | 67.0903 | 22314.9 | 0.74381 | 1.0413
| 1 | 2,500 gal Water Truck | 105.45 | 67.0903 | 7074.6706 | 0.23582 | 0.33014
Fleet Totals | 7 |  |  | 469.632 | 105737.6451 | 3.5245 | 4.9343
SPREADING SOIL
With respect to spreading the soil, assume one Cat 8T is with the hauling operation, spreading the alluvium takes twice the hauling hours
|  | Task 1 | Task 2 | Task 3
|  | N-S Embankment | E-W Embankment | West Embankment
Hauling Hours (HR) |  | - | - | 67.0903
Spreading Job Hours (HR) |  | - | - | 134.1806
Equipment Cost (Cat D10T) |  | - | - | 44629.8
| Total |  |  | 44629.8
|  | Task 1 | Task 2 | Task 3
|  | N-S Embankment | E-W Embankment | West Embankment
Haul & Spread Alluvium and Soil, Total Cost |  | 2612664.591 | 261176.3855 | 6511555.8068
Alluvium Testing & Amendment
Assumptions:
MR submitted a plan on 8/23 & 9/20/02 to DEQ for a 2002 reclamation program of the Woodville Dump
The plan was a modification to the Reclamation Plan and given minor revision number (MR 02-001)
MR's reclamation cover soil recipe can be found in Table 9-2 of the application
That recipe is used on the Yankee Doodle Tailings Impoundment reclamation
Based on the Application, very little soil has been stockpiled, it is assumed the Central Zone alluvium will be salvaged for reclamation material
DEQ assumes the following Central Zone alluvium sampling and analysis schedule
|  | Task 1 | Task 2 | Task 3
|  | N-S Embankment | E-W Embankment | West Embankment
| Analyses | Volume of Alluv. (LCY) | Volume of Alluv. (LCY) | Volume of Alluv. (LCY) | Frequency (LCY) | Cost ($) | Shipping ($)
| Paste pH | 397913.0308 | 38511.154 | 808424.0223 | 2500 | 0 | in house
| Total Metals ICP Scan | 397913.0308 | 38511.154 | 808424.0223 | 30000 | 225 | 10
| Cu & Zn | 397913.0308 | 38511.154 | 808424.0223 | 10000 | 45 | 10
| Organic Content | 397913.0308 | 38511.154 | 808424.0223 | 2500 | 15 | 10
| Total Analytical Cost | 9284.6374 | 898.5936 | 18863.2272
And 1.5% organic matter by weight or 23 tons per acre is also require
Based on recent sampling data, the Central Zone alluvium will not required a lime amendment
Assume the compost would come Western Reclamation Inc. in Butte at a cost of $20/CY
The compost is stored at a central location, assume $5/CY extra to move it to where it will be spread
|  | Task 1 | Task 2 | Task 3
The Estimated Compost Cost |  | N-S Embankment | E-W Embankment | West Embankment
Area of Embankment and Crest (AC) (Corrected for slope) |  | 118.0419 | 10.1742 | 160.5766
Density of Compost (LBS/CY) |  | 1000 | 1000 | 1000
Cost per CY delivered to Butte ($/CY) |  | 25 | 25 | 25
Total Cost of Compost |  | 135748.185 | 11700.33 | 184663.09
DEQ requests a qualified soils scientist (with a pickup truck) will be with the alluvium salvage operation full time for lab work, QA/QC and record keeping
The estimated cost for a qualified soil scientist (with a pickup), from a Consulting Firm, is $150 per hour
The number of work hours for the soil scientist is equal to the scheduled hours for the alluvium spreading operation
A portable soil testing trailer will be rented for laboratory space, sampling equipment storage, and record keeping
The estimated cost for a soil trailer rental is $200 per month
|  | Task 1 | Task 2 | Task 3
|  | N-S Embankment | E-W Embankment | West Embankment
Estimate for Full Time Soil Scientist
Soil Scientist Hourly Rate ($/HR) |  | 150 | 150 | 150
Number of Hours (HR) |  | 403.5465 | 39.0564 | 819.8694
Total Cost of Soils Scientist |  | 60531.9811 | 5858.4572 | 122980.4099
Estimate for a Soils Trailer
Soils Trailer Monthly Rate ($/MO) |  | 200 | 200 | 200
Number of Months (MO) |  | 3.3629 | 0.32547 | 6.8322
Total Cost for Trailer |  | 672.5776 | 65.094 | 1366.449
To spread the compost, piles are built up along the embankment crest and pushed down slope with a D8T dozer
DEQ assume two-Cat D8T dozers will be used to spread the compost at a production rate of 1/4 acre per hour
After spreading, the compost will be incorporated into the top 4 inches using a harrow that is drag along behind the seeder
The Estimated Cost Spreading Compost
Area of Embankment and Crest (AC) |  | 118.0419 | 10.1742 | 160.5766
2 - Cat D8T Dozer Production (AC/HR) |  | 0.25 | 0.25 | 0.25
Job Hours - 2 Cat D8T (HR) |  | 472.1676 | 40.6968 | 642.3064
Total Cost D8T |  | 314095.3309 | 27072.3253 | 427275.0634
Alluvium Testing & Amendment, Total Cost |  | 520332.7119 | 45594.8 | 755148.2395
Establish Vegetation & Weed Control
Assumptions:
The estimated revegetation and weed spraying cost for a 5-year period is $1,500 per acre, which includes minor erosion repair and seeding,
applying fertilizer, BMPs, etc.
The seeding is accomplished using a small dozer with a seeder attached to the front and a harrow pulled behind.
|  | Task 1 | Task 2 | Task 3
|  | N-S Embankment | E-W Embankment | West Embankment
Area of Embankment and Crest (AC) |  | 118.0419 | 10.1742 | 160.5766
Estimated Vegetation & Weed Control Cost ($/AC) |  | 1500 | 1500 | 1500
Total Cost |  | 177062.85 | 15261.3 | 240864.9
Establish Vegetation & Weed Control, Total Cost |  | 177062.85 | 15261.3 | 240864.9
|  | Task 1 | Task 2 | Task 3
|  | N-S Embankment | E-W Embankment | West Embankment
Item 1 Embankment, Total Cost |  | 4748476.4148 | 414923.7955 | 7713408.7014
Note on C87: Garrett Smith: Includes slope directly below the crest and the lower segment of slope near the Leach Pad and Misc. area

## ITEM 2 YDTI Beach Closure
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
Item 2 Cost Summary for Earthwork - YDTI Beach At Closure
Direct Costs | Task 1 Monitor Tailings Surface During Drying |  |  | 0 | (see Interim Maintenance and Post Closure Task)
| Task 2 Dust Control |  |  | 0 | (see Interim Maintenance and Post Closure Task)
| Task 3 Reclaim Tailings Beach (OP 00030) |  |  | 0 | (478 acres bonded at $500/acre)
Task 4 Reclaim Tailings Beach (OP 00030A)
|  | Backfill and Shape Settlement Areas |  | 500000
|  | Haul & Spread Alluvium |  | 16611882.635
|  | Alluvium Testing & Amendments |  | 2476573.6211
|  | Establish Vegetation & Weed Control |  | 811500
20399956.2561
|  | Item 2- YDTI Beach at Closure Total Cost |  | 20399956.2561
|  | Pre-1974 Bond |  | 239000
ACREAGES FROM 2025 SITE PLAN MAP
| Feature | OP 00030A | OP 00041 | OP 00108 | OP 00030 | Grand Total
| YDTI Beach | 541.1089 |  |  | 478.2165 | 1019.3254
| PRE-1974 BOND |  |  |  | 239000
| ACRES FOR BOND CALCULATIONS BELOW | 541.1089
Task 1 Monitor Tailings Surface During Drying
Task 2 Dust Control
Task 3 Reclaim Tailings Beach
Task 1 Monitor Tailings Surface During Drying
Assumptions:
Closure includes dewatering the impoundment via seepage to the WED and Horseshoe Bend, as well as evaporation
The tailings beach and Transition Zone would incrementally exposed by dewatering as the pond is reduced
Reclamation of beach and Transition Zone would be incrementally capping and revegetation as areas become accessible
To identify areas suitable for capping, a LiDAR or Aerial Platform Mapping survey will be performed every 5 years
Those mapping cost are included in the Interim Management and Post Closure segment of this bond
Inaddition to the LiDAR or Aerial Platform mapping, the Beach, Transition Zone, and water level are monitored monthly to assess the potential to disperse dust
If dust is detected, MR is required to implement it dust control plan (see Task 2)
Task 1 Monitor Tailings Surface During Drying, Total Cost |  |  | 0
Task 2 Dust Control
Assumptions:
At shut down, all the processing fluids and remaining tailings from the mill circuit are discharged to the impoundment
The tailings are allowed to dry naturally and consolidate, therefore are susceptible to wind erosion
To prevent wind erosion, the full cap is placed over the CLOSURE tailings surface
Based on the 2025 site plan map, approximately 512 acres and can be capped immediately with 28 inches of alluvium and 6 inches of topsoil
The cost to place the full cap is include in "Haul & Spread Alluvium" task located below
In the interim shut down period, the magnesium chloride will be applied according to their DEQ approved Dust Control Plan
The cost to apply magnesuim chloride are included in Interim Management and Post Closure segment of this bond
Task 2 Dust Control, Total Cost |  | 0
Task 3 Reclaim Tailings Beach (OP 00030)
Assumptions/Observations:
According to the application soil will be sourced from the Central Zone, Lunch Room Stockpile, or the Moulton Road Stockpiles
Most of the tailings beach would be covered with 28 inches of alluvium and 6 inches of topsoil
Tailings Beach at CLOSURE, soil thickness, and volume are as follows:
|  | 2025 Acreage | Alluvium Thickness (Inches) | Topsoil Thickness (inches) | Volume of Topsoil (LCY) | Volume of Alluvium (LCY)
Tailings Beach Alluvium (OP 00030) |  | 478 | 28 |  |  | 1799404.4444
Tailings Beach Topsoil (OP 00030)** |  | 365.5 |  | 6 | 294836.6667 |  | (Ref: Application Section 7.4.1.2, page 7-7)
[5 empty] | 294836.6667 | 1799404.4444
(2025 Site Plan map)
**This cell is 731 acres divided by 2, since half of the topsoil can be placed in both OP 00030 & 30A.
**366 acres of OP 00030 get additional 6 inches of topsoil on top of the alluvium
The 478 acres of beach are located in OP 00030, which is limited to bonding at $500/acre
This total is accounted for at the top of this tab
Task 3 Reclaim Tailings Beach (OP 00030), Total Cost |  |  | 239000 | PRE-1974 BOND
Task 4 Reclaim Tailings Beach (OP 00030A) AT CLOSURE
Backfill and Shape Settlement Areas (OP 00030A)
Assumptions:
The tailings beach will gradually slope away from the embankment to the north at a typical slope of one percent
Some topographic diversity will be created by final spigot placement
While no final grading is anticipated, it will be necessary to backfill and shape settlement areas BEFORE SOIL IS PLACED
The extra volume of waste rock or alluvium is based on experiences at Golden Sunlight Mine
DEQ estimates 5% to 10% of the tailings beach will required extra waste rock or alluvium backfill
To reshape the settlement area a low ground pressure Cat D6T dozer would be used
The Cat D6T would chisel off the sides, push tailings or fill into the settlement void
Since the volume of backfill and D6T reshaping is unknown assume a lump sum cost of $500,000 is necessary
Backfill and Shape Settlement Areas (OP 00030A), Total Cost |  |  | 500000
Haul & Spread Alluvium & Topsoil (OP 00030A)
Assumptions:
According to the application soil will be sourced from the Central Zone, Lunch Room Stockpile, or the Moulton Road Stockpiles
Most of the tailings beach would be covered with 28 inches of alluvium and 6 inches of topsoil
Tailings Beach at 2025 CLOSURE, soil thickness, and volume are as follows: |  |  | (see Application, Table 9-2 & 9-3)
|  | 2025 Acreage | Alluvium Thickness (Inches) | Topsoil Thickness (inches) | Volume of Topsoil (LCY) | Volume of Alluvium (LCY)
Tailings Beach Alluvium (OP 00030A) |  | 541 | 28 |  |  | 2036564.4444
Tailings Beach Topsoil (OP 00030A)** |  | 365.5 |  | 6 | 294836.6667 |  | (Ref: Application Section 7.4.1.2, page 7-7)
|  | (2025 Site Plan Map) |  |  | 294836.6667 | 2036564.4444
**This cell is 731 acres divided by 2, since half of the topsoil can be placed in both OP 00030 & 30A.
The area of Tailings Beach to get alluvium at closure(AC) |  |  | 541
The estimated volume of alluvium to cover beach (LCY) |  |  | 2036564.4444
Contingency Volume (15% extra)(LCY) |  |  | 2342049.1111
The density of the alluvium (LBS/LCY) |  |  | 3300
The estimated weight of alluvium to cover the embankment (TONS) |  |  | 3864381.0333
The area of Tailings Beach to get 6 inches of topsoil (AC) |  |  | 365.5
The estimated volume of topsoil to cover the alluvium (LCY) |  |  | 294836.6667
Contingency Volume (0% extra)(LCY) |  |  | 294836.6667 | (limited by topsoil volume, no extra for contingency)
The density of the topsoil (LBS/LCY) |  |  | 2800
The estimated weight of topsoil to cover the embankment (TONS) |  |  | 412771.3333
DEQ assumes that a Cat 6020B Hydraulic Excavator and 10-Cat 777 Haul Trucks will be used to mine, load, and haul the alluvium
to the top of the embankment where it would be dumped, creating a pile of capping material
The capping material would then be loaded into the three smaller Cat 740, 40 ton trucks and transported out on the beach
The smaller trucks would be loaded by the Cat 980 Wheel Loader
It is assumed the job hours second load-haul operation (Cat 980 loader & 3 Cat 740 trucks) is dependent upon, and equal to the larger
(Cat 6020B Front Shovel & 10 - Cat 777 Haul Trucks) operation, therefore the operating hours will be equal
With respect to spreading the alluvium, assume two Cat 10T are with the hauling operation equal to the hauling hours
Spreading the alluvium:
The estimated haul distance at a 4% grade (FT) |  | 13200 | (Central Zone Alluvium)
Haul 13,200 feet One Way, Total Resistance 10%
Cat Edition 45 p.10-55 Cat 777G Haul Truck Rimpull-Speed-Gradeability Curve Loaded Speed (MPH) |  |  |  | 12
Cat Edition 45 p.10-55 Cat 777G Haul Truck Rimpull-Speed-Gradeability Curve Empty Speed (MPH) |  |  |  | 20
Hauler Cycle Time (MIN)
Load with Exchange |  | 2.45
Haul |  | 12.5
Dump and Maneuver |  | 1.6
Return |  | 7.5
Potential Cycle Time |  | 24.05
Wait on Slow Hauler |  | 0
Wait to Load, Bunching AVG |  | 0 | Bunching Calc | # of Trucks (hauler capabilities)
Total Cycle Time (MIN) |  | 24.05 | 21.6 | 8.8163
Cycles per 60 min Hour (CYCLES/HR) |  | 2.4948
Cat 777G Average Capacity (LCY) |  | 77
Hauler Potential Production Per Hour (LCY/HR) |  | 192.0998
6020B Passes per Hauler |  | 5 | 5.1333
Loader Cycle Time (MIN) |  | 0.7
Load Time Truck (MIN) |  | 3.5
Number of Trucks Required (EA) |  | 6.8714 | # of Trucks (loader capabilities)
Production Rate (LCY/MIN) |  | 22
Hourly Production (LCY/HR) |  | 1320
Efficiency Factor |  | 0.83
Availability |  | 0.9
Adjusted Hourly Production (LCY/HR) |  | 986.04
Hours Required (HR) |  | 2375.207
| Qty | Model | Hourly Cost Each Unit | Operating Hours | Total Cost | $ per Ton | $ per LCY
Loaders: | 1 | 6020B | 629.72 | 2375.207 | 1495715.3526 | 0.38705 | 0.63864
| 1 | Cat 980 | 194.39 | 2375.207 | 461716.4889 | 0.11948 | 0.19714
Haulers: | 6.8714 | 777D | 468.39 | 16321.0652 | 7644623.7518 | 1.9782 | 3.2641
| 3 | 740 | 249.65 | 7125.621 | 1778911.2833 | 0.46034 | 0.75955
Support: | 1 | 14H Motor Grader | 194.65 | 2375.207 | 462334.0427 | 0.11964 | 0.19741
| 1 | D8T | 332.61 | 2375.207 | 790017.6006 | 0.20444 | 0.33732
| 1 | 2,500 gal Water Truck | 105.45 | 2375.207 | 250465.5782 | 0.064814 | 0.10694
Fleet Totals | 14.8714 |  |  | 35322.7213 | 12883784.0981 | 3.334 | 5.5011
Spreading Alluvium
Hauling Hours (HR) |  | 2375.207
Equipment Cost | Cat D10T | 1183636.9047
| Total | 1183636.9047
Haul & Spread Alluvium (OP 00030A), Total Cost |  | 14067421.0028
Haul & Spread 6 inches of Topsoil (OP 00030A) Calculation
Since the topsoil stockpiles are close to the West Embankment, smaller equipment can be used
Assume a Cat 980G loader and three Cat 740 Articulating trucks are used to load and transfere the soil to the embankment
With respect to spreading the topsoil, assume one Cat 8T is with the hauling operation at twice the hauling hours
The estimated haul distance at a 0% grade (FT) |  | 10560 | (Moulton RoadTopsoil)
Haul 10,560 feet One Way, Total Resistance 5%
Cat Edition 45 p.1-24 Cat 740 Haul Truck Rimpull-Speed-Gradeability Curve Loaded Speed (MPH) |  |  |  | 20
Cat Edition 45 p.1-24 Cat 740 Haul Truck Rimpull-Speed-Gradeability Curve Empty Speed (MPH) |  |  |  | 20
Hauler Cycle Time (MIN)
Load with Exchange |  | 2.45
Haul |  | 6
Dump and Maneuver |  | 1.6
Return |  | 6
Potential Cycle Time |  | 16.05
Wait on Slow Hauler |  | 0
Wait to Load, Bunching AVG |  | 0 | Bunching Calc | # of Trucks (hauler capabilities)
Total Cycle Time (MIN) |  | 16.05 | 13.6 | 5.551
Cycles per 60 min Hour (CYCLES/HR) |  | 3.7383
Cat 740 Average Capacity (LCY) |  | 31
Hauler Potential Production Per Hour (LCY/HR) |  | 115.8879
Cat 980 Passes per Hauler |  | 4 | 4.4286
Loader Cycle Time (MIN) |  | 0.6
Load Time Truck (MIN) |  | 2.4
Number of Trucks Required (EA) |  | 6.6875 | 3 | Contractor only has 3 trucks available, see Inputs tab
Production Rate (LCY/MIN) |  | 5.7944
Hourly Production (LCY/HR) |  | 347.6636
Efficiency Factor |  | 0.83
Availability |  | 0.9
Adjusted Hourly Production (LCY/HR) |  | 259.7047
Hours Required (HR) |  | 1135.2767
| Qty | Model | Hourly Cost Each Unit | Operating Hours | Total Cost | $ per Ton | $ per LCY
Loaders: | 1 | 980 | 194.39 | 1135.2767 | 220686.4397 | 0.53465 | 0.7485
Haulers: | 3 | 740 | 249.65 | 3405.8301 | 850265.4921 | 2.0599 | 2.8839
Support: | 1 | 14H Motor Grader | 194.65 | 1135.2767 | 220981.6116 | 0.53536 | 0.74951
| 1 | D8T | 332.61 | 1135.2767 | 377604.3866 | 0.9148 | 1.2807
| 1 | 2,500 gal Water Truck | 105.45 | 1135.2767 | 119714.9291 | 0.29003 | 0.40604
Fleet Totals | 7 |  |  | 7946.937 | 1789252.8591 | 4.3347 | 6.0686
Spreading Alluvium & Topsoil
With respect to spreading the topsoil, assume one Cat 8T is with the hauling operation at twice the hauling hours
Hauling Hours (HR) |  | 1135.2767
Job Hours (HR) |  | 2270.5534
Equipment Cost | Cat D8T | 755208.7731
| Total | 755208.7731
Haul & Spread 6 inches Topsoil (OP 00030A), Total Cost |  | 2544461.6322
Haul & Spread Alluvium & Topsoil (OP 00030A), Total Cost |  |  | 16611882.635
Alluvium Testing & Amendment
Assumptions:
MR submitted a plan on 8/23 & 9/20/02 to DEQ for a 2002 reclamation program of the Woodville Dump
The plan was a modification to the Reclamation Plan and given minor revision number (MR 02-001)
MR's reclamation cover soil recipe can be found in Table 9-2 of the application
That recipe is used on the Yankee Doodle Tailings Impoundment reclamation
Based on the Application, very little soil has been stockpiled, therefore DEQ will assumes the Central Zone alluvium will be salvaged for reclamation material
DEQ assumes the following Central Zone alluvium sampling and analysis schedule
| Analyses | Volume of Soil (LCY) | Frequency (LCY) | Cost ($) | Shipping ($) | Total Cost ($)
| Paste pH | 2342049.1111 | 2500 | 0 | in house | 0
| Total Metals ICP Scan | 2342049.1111 | 30000 | 225 | 10 | 18346.0514
| Cu & Zn | 2342049.1111 | 10000 | 45 | 10 | 12881.2701
| Organic Content | 2342049.1111 | 2500 | 15 | 10 | 23420.4911
[5 empty] | Total | 54647.8126
And 1.5% organic matter by weight or 23 tons per acre is also require
Based on recent sampling data, the Central Zone alluvium will not required a lime amendment
Assume the compost would come Western Reclamation Inc. in Butte at a cost of $20/CY
The compost is stored at a central location, assume $5/CY extra to move it to where it will be spread
The Estimated Compost Cost
Area (AC) |  | 541
Density of Compost (LBS/CY) |  | 1000
Cost per CY delivered to Butte ($/CY) |  | 25
Total Cost of Compost |  | 622150
DEQ requests a qualified soils scientist (with a pickup truck) will be with the alluvium salvage operation full time for lab work, QA/QC and record keeping
The estimated cost for a qualified soil scientist (with a pickup), from a Consulting Firm, is $150 per hour
The number of work hours for the soil scientist is equal to the scheduled hours for the alluvium spreading operation
A portable soil testing trailer will be rented for laboratory space, sampling equipment storage, and record keeping
The estimated cost for a soil trailer rental is $200 per month
The Estimated Cost for Full Time Soils Scientist
Soil Scientist Hourly Rate ($/HR) |  | 150
Number of Hours (HR) |  | 2375.207
Total Cost of Soils Scientist |  | 356281.0501
The Estimated Cost for a Soils Trailer
Soils Trailer Monthly Rate ($/MO) |  | 200
Number of Months (MO) |  | 19.7934
Total Cost for Trailer |  | 3958.6783
To spread the compost, piles are built up around the beach so they can be spread with a D8T dozer
DEQ assume two-Cat D8T dozers will be used to spread the compost at a production rate of 1/4 acre per hour
After spreading, the compost will be incorporated into the top 4 inches using a harrow that is drag along behind the seeder
The Estimated Cost Spreading Compost
Area of Tailings Beach at Closure (AC) |  | 541
2 - Cat D8T Dozer Production (AC/HR) |  | 0.25
Job Hours - 2 Cat D8T (HR) |  | 2164
Total Cost D8T |  | 1439536.08
Alluvium Testing & Amendment, Total Cost |  |  | 2476573.6211
Establish Vegetation & Weed Control
Assumptions:
The estimated revegetation and weed spraying cost for a 5-year period is $1,500 per acre, which includes minor erosion repair and seeding, applying fertilizer, BMPs, etc.
The seeding is accomplished using a small dozer with a seeder attached to the front and a harrow pulled behind.
Area of Tailings Beach at Closure (AC) |  |  | 541
Estimated Vegetation & Weed Control Cost ($/AC) |  |  | 1500
Total Cost |  |  | 811500
Establish Vegetation & Weed Control, Total Cost |  |  | 811500
Task 4 Reclaim Tailings Beach (OP 00030A), Total Cost |  |  | 20399956.2561

## ITEM 3 Exploration
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
Item 3 Exploration Disturbance Rolled Into OP
Item 3 Cost Summary for Exploration Disturbances Rolled into Operating Permit
Direct Costs
| Task 1 West Ridge monitoring wells |  |  |  |  | 28465
|  | Item 3- Exploration Disturbances to OP Total Cost |  |  |  | 28465
|  | Pre-1974 Bond |  |  |  | -
*From Amendment 10 Bond Calculation- 2/11/2020
The areas shown in 2025 site plan map within OP 00041 (table below) are bonded under Exploration License 00711 (East Side disturbance)
These acres are not applied to the Operating Permit Bond
ACREAGES FROM 2025 SITE PLAN MAP
Feature |  |  | OP 00030A | OP 00041 | OP 00108 | OP 00030 | Grand Total
Exploration Permit |  |  |  | 1.3147 |  |  | 1.3147
Exploration Permit Partially Reclaimed/Released |  |  |  | 0.46489 |  |  | 0.46489
Assumptions:
The West Ridge Exploration disturbance was conducted under Exploration License #00711
The West Ridge monitoring wells from this project were added to OP 00030 through Amendment 010
Unreclaimed disturbances from this project will be bonded under the Operating Permit
The West Ridge wells occur within OP 00030A, but the adjacent road acres are accounted for under the Misc. tab
Here is a list of West Ridge Monitoring Wells that are being rolled into the Operating Permit
West Ridge Monitoring Wells (taken from Exploration License #00711 bond calculation)
Well depth information gathered from Table 4-1 in September 2017 OP Amendment Application
| Well Name | Depth (ft)
| MW 12-11 | 200
| MW 12-12 | 200
| MW 12-13 | 200
| MW 12-14 | 150
| MW 12-15 | 200
| MW 12-16 | 191
| MW 12-17 | 195
| MW 12-18 | 115
| MW 15-01 | 230
| MW 15-02 | 197
| MW 15-03 | 386
| MW 15-04 | 220
| MW 15-05 | 240
| MW 15-06 | 400
| MW 15-07 | 203
| MW 15-08 | 102
| MW 15-09 | 142
| MW 15-10 | 100
| MW 15-11 | 201
| MW 15-12 | 99
| MW 15-13 | 101
| MW 16-01 | 517
| MW 16-02D | 552
| MW 16-02S | 552
| TOTAL | 5693
At the end of post-closure monitoring, wells must be plugged and abandoned. Hole plugging rate includes equipment, personel, and materials to backfill hole.
Plugging includes bentonite from the bottom to within 5-10 feet of surface, then cement fill from top of bentonite to land surface, per MT ARM 17.24.106(2)
| Hole plugging rate ($/FT) | 5
| Total hole depth (FT) | 5693
| Total plugging cost | 28465
In addition to the list of monitoring wells, there are other 19 drillholes with vibrating wire piezometers installation
These piezometer monitoring points are included in the "Post Closure" tab
The Exploration License bond also included misc. disturbance associated with the West Ridge wells
These disturbances are accounted for as roads or misc. disturbance in the 2025 site plan map and the Misc. tab calculations
|  | Pads (acres) | Roads (acres)
| Existing | 0.4 | 0.7
| Pre-2015 | 0.5 | 0.1
| 2015 | 0.4 | 0.2
| Total | 1.3 | 1 | 2.3
Task 1 Exploration Disturbances |  |  | Total Cost |  | 28465

## ITEM 4 WED Water Treatment
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
Item 4 WED Water Treatment at Closure
Background Hydrology:
Bond Assumptions:
The information above was provided in the Amendment 010 Application and in the EIS.
Updates have since been provided by the company about estimates for pond elevations during operations:
Monitoring and Future Bond Evaluations:
Knight Piesold, "Projected Supernatant Pond Water Level Trends during 2020-2029" (2/6/2020)
"A new water management strategy was recently implemented at the site as part of a pilot project associated with the Butte Mine Flooding Operable Unit (BMFOU) of Superfund. The pilot project facilitates the treatment and release of up to 10 million gallons per day (MGPD) of water from the YDTI. The water is treated at a Polishing Plant and the effluent is released near the confluence of the Blacktail and Silver Bow Creeks.
One goal of the pilot project is to reduce the supernatant pond volume to approximately 15,000 to 20,000 acre-ft. The Polishing Plant began operating on September 30, 2019 and approximately 436 M gallons (~1,340 acre-ft) of water was removed from the YDTI during Q4 2019. Approximately 3 MGPD of Berkeley Pit water was treated and introduced into the system during the same time period. The removal of water from the YDTI in Q4 2019 decreased the pond elevation by approximately 0.2 ft, which is a significant change from the average elevation increase of 1.5 ft observed during the same period over the preceding five years."
"The reduction in water inventory stored within the YDTI due to the pilot project will significantly decrease the supernatant pond elevation (relative to conditions without the pilot project) over the next five-year period as shown on Figure 1. The magnitude of the decrease was estimated to be in excess of approximately 20 ft. The pond elevation is expected to remain below approximately EL. 6,370 ft over the next five years as the YDTI pond volume is reduced to between 15,000 and 20,000 acre-ft. The pond elevation will therefore remain below the lowest piezometric elevation of EL. 6,379 ft that was recorded at the Potentiometric Low in July 2015 and significantly lower than the piezometric elevation of over EL. 6,400 ft observed in this area more recently.
The supernatant pond elevation is expected to increase beyond the EL. 6,379 ft level in approximately 2026 based on the current knowledge of the impoundment and projections of future operating conditions. Therefore, the WED will not be needed for hydrodynamic containment and the WED could be plugged to prevent flow to the Extraction Pond in premature closure scenarios until 2026. These expected trends can be analyzed as part of on-going operations and projections can be periodically refined as more operating data becomes available."
This figure presents the forecasted supernatant pond elevations for the following scenarios:
• Operations continue following historical trends (i.e. no pilot project)
• The pilot project reduces the supernatant pond to a nominal volume of 20,000 acre-ft over 5 years
• The pilot project reduces the supernatant pond to a nominal volume of 15,000 acre-ft over 5 years
The following inputs and assumptions were used to develop the projected pond elevations for each of the scenarios described above:
• The operating pond volume at the end of Q3 2019 was 34,400 acre-ft, which was the pond volume estimated during the bathymetric survey conducted in July 2019
• The supernatant pond surface area was 774 acres, which was the surface area estimated during the bathymetric survey conducted in July 2019
• The supernatant pond surface area was assumed to remain the same as the pond decreases in volume, which is a conservative assumption to calculate the resulting pond elevation (i.e. if the pond decreases in area, then the pond elevation would be slightly lower than the estimated value)
• The pond elevation without discharge of water from the YDTI would continue to rise at a rate of 6.3 ft/yr, which is the average rate observed over the three years preceding the pilot project
• The discharge of YDTI water via the Polishing Plant reduces the pond volume
• The change in elevation of the pond due to the reduction in water inventory is equivalent to the change in pond volume divided by the surface area of the pond
The pond elevation would remain below 6380 ft in 2025, so it is assumed that pumping water from the WED Extraction Pond to the YDTI Pond during post-closure will not be needed in the next five years of operation, nor will water from the WED need to be treated with lime prior to discharge to the pond.
In the event of an unanticipated closure in the next five year period, the WED would be grouted or otherwise sealed upstream of the Extraction Pond and WED pumping would be terminated. The bonding for this component of reclamation is included in the "Post Closure" tab calculations.
"Plugging of the WED will likely include grouting the south end of the WED to cut off flow to the extraction pond. After plugging, the WED will become flooded and no longer act as a drain, and water levels within the west tailings beach and groundwater west of the West Embankment will re-equilibrate to pre-WED flow conditions. Once groundwater conditions re-equilibrate, the overall West Ridge groundwater flow pattern will be eastward from the West Ridge crest towards and into the impoundment, similar to current flow conditions." (Amendment Application, Section 10.2.4)
As provided above, the current water treatment pilot project being conducted under BMFOU has a significant effect on the volume and elevation of the YDTI pond. The determination to not include WED seepage treatment and pumpback in this bond calculation is contingent on the pond elevation remaining below 6380 ft (Anaconda datum) in the next five years.
Based on observations of groundwater elevations in the West Ridge, the WED was designed to intercept impoundment seepage and prevent impacts to adjacent groundwater systems. Even though the pond may be managed at a lower elevation during operations and the West Ridge groundwater elevations have increased since 2017, the pond elevation of 6380 ft was considered when establishing the "allowable hydraulic grade lines" for the WED design. Consequently, the 6380 ft elevation was the basis for DEQ's analysis of the the proposed closure plan with regard to hydrodynamic containment and protection of off-site water resources. If the pond elevation exceeds 6380 ft, then the closure plan requires that seepage collected in the WED will be treated and pumped back to the YDTI. This pumpback system would be used post-closure to manage water in the YDTI until the pond elevation decreases below 6380 ft and seepage rates dissipate to allow plugging the WED.
Based on future observations of pond elevation and groundwater elevations during operations, DEQ may determine that post-closure water management and treatment are requirements of the reclamation bond within the next five years. As provided in 82-4-338(3)(a), MCA: "The department shall conduct an overview of the amount of each bond annually and shall conduct a comprehensive bond review at least every 5 years. The department may conduct additional comprehensive bond reviews if, after modification of a reclamation or operation plan, an annual overview, or an inspection of the permit area, the department determines that an increase of the bond level may be necessary." The collection of representative monitoring data and timely submittals of the data to DEQ are crucial to ensure that reclamation bonding reflects site conditions.
Monitoring locations along the West Embankment and the West Ridge were incorporated into the operational monitoring network as part of this amendment. Data collected from these monitoring locations, in addition to surveys of the YDTI pond elevation and volume, will be regularly assessed by DEQ to determine if the objectives for hydrodynamic containment are being achieved and if the pond elevation is increasing as projected by recent models. The assessment of monitoring data will also inform DEQ's annual bond review and DEQ anticipates that the key monitoring locations for this evaluation may include, but are not limited to:
-- MW12-16, MW16-01, MW16-02D, DH15-14, DH16-01 (low groundwater elevations on West Ridge)
-- DH15-05, DH15-09, DH15-12, VWP-DP1, VWP-DP2, VWP-EB1 (monitoring around WED/drain pods)
-- YDTI pond elevation and volume
Some of the piezometers in the drain pod or extraction basin areas (VWP-DP1, -DP2, -EB1) have been proposed as additional Qualitative Performance Parameters (QPP) in 2020, which would be reported to DEQ quarterly. Data from the YDTI pond surveys are also currently included in quarterly monitoring reports, but many groundwater elevation data are reported only annually. DEQ requests that the groundwater monitoring data for other key sites (e.g. near WED, low elevations on West Ridge) also be included in the comparisons provided in the quarterly monitoring reports, with more thorough discussion and complete datasets to be provided in the annual report.
DEQ also requests to be notified if/when the YDTI dewatering efforts through BMFOU cease or are modified from the current conditions (i.e. up to 10 MGPD removed). DEQ may request additional modeling to predict the pond elevations that may result from these changes to the YDTI water balance, thus determining whether the bond adequately reflects the site conditions that would occur during an unanticipated closure.
In the scenario where it becomes necessary to include water pumpback and treatment in the bond calculation, see guidance and notes provided in previous drafts of Amendment 10 calculations.

## ITEM 5 Post Closure Reclamation
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
Item 5 Post-Closure Reclamation
Item 5 Cost Summary for Post Closure
Direct Cost
Task 1 Incrementally Reclaim Exposed Transition Zone Per 5 Year Period
|  | Monitor Tailings Surface During Drying Per 5 Year Period |  |  |  | 10000
|  | Dust Control Per 5 Year Period |  |  |  | 52000
|  | Reclaim Transition Zone Per 5 Year Period |  |  |  | 2587646.8366
2649646.8366
Task 2 Long Term Monitoring Sites Per Year
|  | Water Quality Monitoring |  |  |  | 80290.81
|  | Embankment Piezometer Monitoring |  |  |  | 25000
105290.81
| Task 3 Construct Spillway at Closure |  | See Item 15- Spillway |  |  | 0
| Task 4 Plug WED |  |  |  |  | 500000
Task 5 Site Maintenance Post Closure Per Year
|  | Repair or Clean out the Extraction Pond |  |  |  | 0 |  | *determined unnecessary in next 5 years
|  | Maintain Electrical System for Extraction Basin |  |  |  | 0 |  | *determined unnecessary in next 5 years
|  | Install Submersible Pumps in Extraction Basins |  |  |  | 0 |  | *determined unnecessary in next 5 years
|  | Maintaining and Periodically Replace Piezometers and Cellular Connection |  |  |  | 25000
25000
| Task 6 Purchase Terramac (from Task 1 - Dust Control) |  |  |  |  | 334866
Summarized for 30-year period, see NPV table below
|  | Item 5- Post Closure Total Cost |  |  |  | 15701235.023
|  | Pre-1974 Bond |  |  |  | 17000
ACREAGES FROM 2025 SITE PLAN MAP
Feature |  | OP 00030A | OP 00041 | OP 00108 | OP 00030 | Grand Total
YDTI North Transition Zone |  | 80.68 |  |  |  | 80.68
YDTI Pond |  | 83.8807 |  |  |  | 83.8807
YDTI Tailings Transition Zone |  | 369.5179 |  |  | 34.0652 | 403.5831
YDTI West Embankment WED |  | 4.5749 |  |  |  | 4.5749
| PRE-1974 BOND |  |  |  | 17000
| ACRES FOR BOND CALCULATIONS BELOW | 538.6536
Assume a 30-year period for incremental beach reclamation
inflation rate, I = | 2%
discount rate, r = | 3% | [5 empty] | Nominal | Present
| Year |  | Capital Costs | Annual O&M | 5 Year Periodic Costs | Annual Total | Value | Value
| 2026 |  | 334866 | 130290.81 |  | 465156.81 | 465156.81 | 465156.81
| 2027 |  |  | 130290.81 |  | 130290.81 | 132896.6262 | 129025.8507
| 2028 |  |  | 130290.81 |  | 130290.81 | 135554.5587 | 127773.1725
| 2029 |  |  | 130290.81 |  | 130290.81 | 138265.6499 | 126532.6563
| 2030 |  |  | 130290.81 | 2649646.8366 | 2779937.6466 | 3009093.9115 | 2673540.9663
| 2031 |  |  | 130290.81 |  | 130290.81 | 143851.5822 | 124087.6384
| 2032 |  |  | 130290.81 |  | 130290.81 | 146728.6138 | 122882.9041
| 2033 |  |  | 130290.81 |  | 130290.81 | 149663.1861 | 121689.8662
| 2034 |  |  | 130290.81 |  | 130290.81 | 152656.4498 | 120508.4111
| 2035 |  |  | 130290.81 | 2649646.8366 | 2779937.6466 | 3322282.8227 | 2546253.1449
| 2036 |  |  | 130290.81 |  | 130290.81 | 158823.7704 | 118179.8011
| 2037 |  |  | 130290.81 |  | 130290.81 | 162000.2458 | 117032.4244
| 2038 |  |  | 130290.81 |  | 130290.81 | 165240.2507 | 115896.1872
| 2039 |  |  | 130290.81 |  | 130290.81 | 168545.0557 | 114770.9815
| 2040 |  |  | 130290.81 | 2649646.8366 | 2779937.6466 | 3668068.6874 | 2425025.5222
| 2041 |  |  | 130290.81 |  | 130290.81 | 175354.276 | 112553.237
| 2042 |  |  | 130290.81 |  | 130290.81 | 178861.3615 | 111460.4872
| 2043 |  |  | 130290.81 |  | 130290.81 | 182438.5887 | 110378.3465
| 2044 |  |  | 130290.81 |  | 130290.81 | 186087.3605 | 109306.7121
| 2045 |  |  | 130290.81 | 2649646.8366 | 2779937.6466 | 4049844.2226 | 2309569.5709
| 2046 |  |  | 130290.81 |  | 130290.81 | 193605.2898 | 107194.5549
| 2047 |  |  | 130290.81 |  | 130290.81 | 197477.3956 | 106153.831
| 2048 |  |  | 130290.81 |  | 130290.81 | 201426.9435 | 105123.2113
| 2049 |  |  | 130290.81 |  | 130290.81 | 205455.4824 | 104102.5976
| 2050 |  |  | 130290.81 | 2649646.8366 | 2779937.6466 | 4471355.2621 | 2199610.5006
| 2051 |  |  | 130290.81 |  | 130290.81 | 213755.8839 | 102091.0006
| 2052 |  |  | 130290.81 |  | 130290.81 | 218031.0016 | 101099.8259
| 2053 |  |  | 130290.81 |  | 130290.81 | 222391.6216 | 100118.2741
| 2054 |  |  | 130290.81 |  | 130290.81 | 226839.4541 | 99146.2521
| 2055 |  | 500000 | 130290.81 |  | 630290.81 | 1119298.5883 | 474970.2843
15701235.023
Item 5 Post Closure Reclamation |  |  |  | Post Closure Total Cost |  |  |  | 15701235.023
Task 1 Incrementally Reclaim Exposed Tailings Beach Per 5 Year Period
Task 2 Long Term Monitoring Sites Per Year
Task 3 Construct Spillway at Closure
Task 4 Plug WED
Task 5 Site Maintenance Post Closure Per Year
Task 6- Purchase TerraMac
Task 1 Incrementally Reclaim Tailings Beach Per 5 Year Period
Assumptions:
The Reclamation Schedule from Amendment 010 application as shown in Table 9-5
The purpose of this segment of the bond is to capture all the costs in the Post Closure period according to the reclamation schedule
Task 1
Task 3
Task 4
Task 2
Following completion of the closure reclamation stage (years 2-5), as the pond recedes, the YDTI transition zone can be incrementally reclaimed over a 30 year period
The ultimate volume of the pond is forecasted to be between 500 and 2000 acre-feet, based on seasonal variability
The post closure beach and pond acreage will change following closure as the pond drains
The 2025 site plan map shows the following acreages:
|  | OP 00030A | OP 00030 | Total
Beach area in 2025 (reclaimed in years 2-5) (AC) |  | 541 | 478 | 1019
Pond area in 2025 (AC) |  | 365 |  | 365
Pond Area in Equilib (AC) |  | 84 |  | 84
Tailings Transition Zone in Equilib (AC) |  | 370 | 34 | 404
North Transition Zone in Equilib (AC) |  | 81 |  | 81 | 204 | Combined transition zones in 2025
*Pre-1974 bond applies to Transition Zone, Beach already accounted for in Item 2 tab
Area to be incrementally reclaimed (OP#00030A):
YDTI North Transition Zone (AC) |  | 81
YDTI Tailings Transition Zone (AC) |  | 370
Monitor Tailings Surface During Drying Per 5 Year Period
Assumptions:
Closure includes dewatering the impoundment via seepage to the WED and Horseshoe Bend, as well as evaporation
The tailings beach and Transition Zone would incrementally exposed by dewatering as the pond is reduced
Reclamation of beach and Transition Zone would be incrementally capping and revegetation as areas become accessible
To identify areas suitable for capping, ar Aerial Platform Mapping survey will be performed every 5 years
Inaddition to Aerial Platform (Drone) mapping, the Beach, Transition Zone, and water level are monitored monthly to assess the potential to disperse dust
If dust is detected, MR is required to implement it dust control plan (see Task 2)
Based on recent cost information, the estimated cost per survey is $10,000 per 5 year
The $10,000 includes post processing and map printing
Monitor Tailings Surface During Drying, Total Cost ($/5 YEAR) |  |  |  | 10000
Dust Control Per 5 Year Period
Assumptions:
Post closure period assumes that 1,019 acres have already been capped with 28 inches of alluvium and 6 inches of topsoil
As the pond recedes over a 30 year period the remaining transition zone acres can be reclaimed
So only a small area of tailings will be open and suscepable to wind erosion
To control the dust, inspections of the impoundment area throughout the day and if necessary safe application of dust suppressant
The meterological station will still be available to provide live-time data (rental rates are included)
If deemed applicable and safe, dust suppressant, such as Magnesium Chloride, will be applied using the Terramac RT9
Deployment of the Terramac, requires two operators to maneuver the machine
Dust suppressant is applied to the tailings beach surface at varying application rates
The hourly rate for the two operators are included under the Site Maintenance task
The Magnesium Chloride costs $5.00 per gallon and 1,600 gallons are applied at one time
Assume the Terramac is only deployed one time per year
Estimated Costs: | Terramac Purchase |  | 334866
MR provided a quote to purchase a new Terramac from Tri State Truck & Equipment. Amortization table. - see Task 6
The cost for a new one with all required options is $334,866. This cost is considered a upfront cost and will be corrected above
| Magnesium Chloride |  | 8000
| Meterological station |  | 2400
10400
Estimated First Year Cost: |  |  | 334866
Estimated 5 Year Cost: |  |  | 52000
Dust Control Per First Year, Total Cost ($) |  |  | 334866 | (moved to Task 6- TerraMac cost)
Dust Control Per 5 Year Period, Total Cost ($/5 YEARS) |  |  | 52000
Reclaim Transition zone Per 5 Year Period
Assumptions:
Post closure period assumes that 1,019 acres have already been capped with 28 inches of alluvium and 6 inches of topsoil
As the pond recedes over a 30 year period the remaining 370 acres of tailings and 81 acres of north shore can be reclaimed
The strips of transition zone (approx. 800 ft wide) would then incrementally become future "Reclaimed Beach"
|  | Year | Total Reclaimed Beach Area | Reclaimable Tailings Trans Zone | Reclaimable North Trans Zone
| closure | 2025 | 1019 | 0 | 0
|  | 2030 | 1080.6667 | 61.6667 | 13.5
|  | 2035 | 1142.3333 | 61.6667 | 13.5
|  | 2040 | 1204 | 61.6667 | 13.5
|  | 2045 | 1265.6667 | 61.6667 | 13.5
|  | 2050 | 1327.3333 | 61.6667 | 13.5
| equlibrium | 2055 | 1389 | 61.6667 | 13.5
|  |  | Total | 370 | 81
Haul & Spread Alluvium Per 5 Year Period
Assumptions:
Reclamation of the incremental exposed beach is similar to the initial beach acres but with contractor using smaller equipment
Assuming a local contractor wins the bid, and has available a Cat 345 Hydraulic Excavator and 2-Cat 740 articulating trucks to mine, load, and haul the alluvium
The capping material would be mined in the Certal Zone, then hauled up to the beach, probably from the West Side, and dumped into piles
Spreading the alluvium is accomplished with a Cat 8T - assume the operating hours equal to the truck hours hauling the alluvium
The exposed tailings beach would be covered with 28 inches of alluvium
The exposed north transition zone would not receive alluvium (excluded in this task), but the area will be seeded
Transition Zone at POST CLOSURE, soil thickness, and volume are as follows:
|  |  | Post Closure Acreage | Alluvium Thickness (Inches) | Topsoil Thickness (inches) | Volume of Alluvium (LCY)
Post Closure Transition Zone Alluvium (every 5 years) |  |  | 61.6667 | 28 |  | 232140.7407
Area of Transition zone to get alluvium during POST CLOSURE(AC) |  |  | 61.6667
The estimated volume of alluvium to cover transition zone (LCY) |  |  | 232140.7407
Contingency Volume (15% extra)(LCY) |  |  | 266961.8519
The density of the alluvium (LBS/LCY) |  |  | 3300
The estimated weight of alluvium to cover the embankment (TONS) |  |  | 440487.0556
The estimated haul distance at a 4% grade (FT) |  |  | 17400 | (Central Zone Alluvium)
Haul 17,400 feet One Way, Total Resistance 10%
Cat Edition 45 p.1-24 Cat 740 Haul Truck Rimpull-Speed-Gradeability Curve Loaded Speed (MPH) |  |  |  | 20
Cat Edition 45 p.1-24 Cat 740 Haul Truck Rimpull-Speed-Gradeability Curve Empty Speed (MPH) |  |  |  | 20
Hauler Cycle Time (MIN)
Load with Exchange |  | 4.5 | (.45 min cycle time)
Haul |  | 0.00010005
Dump and Maneuver |  | 1.6
Return |  | 9.8864
Potential Cycle Time |  | 15.9865
Wait on Slow Hauler |  | 0
Wait to Load, Bunching AVG |  | 0 | Bunching Calc | # of Trucks (hauler capabilities)
Total Cycle Time (MIN) |  | 15.9865 | 11.4865 | 2.5525
Cycles per 60 min Hour (CYCLES/HR) |  | 3.7532
Cat 740 Average Capacity (LCY) |  | 40
Hauler Potential Production Per Hour (LCY/HR) |  | 150.127
Cat 345D Excavator Passes per Hauler |  | 10 | 10
Loader Cycle Time (MIN) |  | 0.7
Load Time Truck (MIN) |  | 7
Number of Trucks Required (EA) |  | 2.2838 | # of Trucks (loader capabilities)
Contractor Truck Availability(EA) |  | 2
Production Rate (LCY/MIN) |  | 5.0042
Hourly Production (LCY/HR) |  | 300.254
Efficiency Factor |  | 0.83
Availability |  | 0.9
Adjusted Hourly Production (LCY/HR) |  | 224.2898
Hours Required (HR) |  | 1190.2543
| Qty | Model | Hourly Cost Each Unit | Operating Hours | Total Cost | $ per Ton | $ per LCY
Loaders: | 1 | Cat 345D | 329.27 | 1190.2543 | 391915.0455 | 0.88973 | 1.4681
Haulers: | 2 | 740 | 249.65 | 2380.5087 | 594293.9904 | 1.3492 | 2.2261
Support: | 1 | 14H Motor Grader | 194.65 | 1190.2543 | 231683.0067 | 0.52597 | 0.86785
| 1 | D8T | 332.61 | 1190.2543 | 395890.495 | 0.89876 | 1.4829
| 1 | 2,500 gal Water Truck | 105.45 | 1190.2543 | 125512.3198 | 0.28494 | 0.47015
Fleet Totals | 6 |  |  | 7141.526 | 1739294.8574 | 3.9486 | 6.5151
Spreading Alluvium
Hauling Hours (HR) |  | 1190.2543
Job Hours (HR) |  | 1190.2543
Equipment Cost | Cat D8T | 395890.495
| Total | 395890.495
Haul & Spread Alluvium Per 5 Year Period ($/5 YEARS) |  |  | 2135185.3523
Alluvium Testing & Amendment Per 5 Year Period
Assumptions:
MR submitted a plan on 8/23 & 9/20/02 to DEQ for a 2002 reclamation program of the Woodville Dump
The plan was a modification to the Reclamation Plan and given minor revision number (MR 02-001)
MR's reclamation cover soil recipe can be found in Table 9-2 of the application
That recipe is used on the Yankee Doodle Tailings Impoundment reclamation
Based on the Application, very little soil has been stockpiled, therefore DEQ will assumes the Central Zone alluvium will be salvaged for reclamation material
DEQ assumes the following Central Zone alluvium sampling and analysis schedule
| Analyses | Volume of Soil (LCY) | Frequency (LCY) | Cost ($) | Shipping ($) | Total Cost ($)
| Paste pH | 266961.8519 | 2500 | 0 | in house | 0
| Total Metals ICP Scan | 266961.8519 | 30000 | 225 | 10 | 2091.2012
| Cu & Zn | 266961.8519 | 10000 | 45 | 10 | 1468.2902
| Organic Content | 266961.8519 | 2500 | 15 | 10 | 2669.6185
[5 empty] | Total | 6229.1099
And 1.5% organic matter by weight or 23 tons per acre is also require
Based on recent sampling data, the Central Zone alluvium will not required a lime amendment
Assume the compost would come Western Reclamation Inc. in Butte at a cost of $20/CY
The compost is stored at a central location, assume $5/CY extra to move it to where it will be spread
The Estimated Compost Cost
Average Area of Tailings Beach During Post Closure (AC) (every 5 years) |  |  | 61.6667
Density of Compost (LBS/CY) |  |  | 1000
Cost per CY delivered to Butte ($/CY) |  |  | 25
Total Cost of Compost |  |  | 70916.6667
DEQ requests a qualified soils scientist (with a pickup truck) will be with the alluvium salvage operation full time for lab work, QA/QC and record keeping
The estimated cost for a qualified soil scientist (with a pickup), from a Consulting Firm, is $150 per hour
The number of work hours for the soil scientist is equal to the scheduled hours for the alluvium spreading operation
A portable soil testing trailer will be rented for laboratory space, sampling equipment storage, and record keeping
The estimated cost for a soil trailer rental is $200 per month
The Estimated Cost for Full Time Soils Scientist
Soil Scientist Hourly Rate ($/HR) |  | 150
Number of Hours (HR) |  | 1190.2543
Total Cost of Soils Scientist |  | 178538.1505
The Estimated Cost for a Soils Trailer
Soils Trailer Monthly Rate ($/MO) |  | 200
Number of Months (MO) |  | 9.9188
Total Cost for Trailer |  | 1983.7572
To spread the compost, piles are built up around the beach so they can be spread with a D8T dozer
DEQ assume one Cat D8T dozers will be used to spread the compost at a production rate of 1/4 acre per hour
After spreading, the compost will be incorporated into the top 4 inches using a harrow that is drag along behind the seeder
The Estimated Cost Spreading Compost
Average Area of Tailings Beach During Post Closure (AC) |  |  | 61.6667
Cat D8T Dozer Production (AC/HR) |  |  | 0.25
Job Hours - Cat D8T (HR) |  |  | 246.6667
Total Cost D8T |  |  | 82043.8
Alluvium Testing & Amendment Per 5 Year Period, Total Cost ($/5 YEARS) |  |  |  | 339711.4843
Establish Vegetation & Weed Control Per 5 Year Period
Assumptions:
The estimated revegetation and weed spraying cost for a 5-year period is $1,500 per acre, which includes minor erosion repair and seeding,
applying fertilizer, BMPs, etc.
The seeding is accomplished using a small dozer with a seeder attached to the front and a harrow pulled behind.
The exposed north transition zone would not receive alluvium, but the area will be seeded
Area of Tailings Transition Zone reclamation Post Closure (AC) |  |  | 61.6667 | per 5 years
Area of North Transition Zone reclamation Post Closure (AC) |  |  | 13.5 | per 5 years
Estimated Vegetation & Weed Control Cost ($/AC) |  |  | 1500
Total Cost |  |  | 112750
Establish Vegetation & Weed Control Per 5 Year Period ($/5 YEARS) |  |  |  | 112750
Reclaim Tailing Beach Per 5 Year Period, Total Cost ($/5 YEARS) |  |  |  | 2587646.8366
Task 1 Incrementally Reclaim Transition Zone Per 5 Year Period, Total Cost ($/5 YEARS) |  |  |  |  | 2649646.8366
Task 2 Long Term Monitoring Sites Per Year
Assumptions:
The long term monitoring sites include the Water Quality monitoring sites and Embankment Piezometers
Water Quality Monitoring Sites
Assumptions:
The 2018 ground water monitoring program includes water quality sampling at 24 sites
All wells are monitored during the spring (June) and fall (October) for a 20-year period (Amendment 010) (see Table 10-2)
A third party A&E firm would be hired to do the sampling and data reporting
Third Party Construction Management Cost Reconciliation is located under "Inputs"
Table 4-1 is a list of monitoring wells included in the program over 20 years
Surface water sites are listed below (from June 2020 Annual Progress Report)
Water Monitoring- Analytical Cost
Assumptions:
Groundwater aites (24) will be monitored twice per year
Surface water sites (12) will be monitored twice per year, as presented in current Annual Progress Reports
Sampling Frequency (Times/Year) |  |  | 2
Number of Sites (EA) |  |  | 36
Number of Samples per Year (Samples/Year) |  |  | 72
Estimated Cost per Sample ($/EA) |  |  | 300
Total Year Sampling Cost ($/YEAR) |  |  | 21600
Water Monitoring- Analytical Cost, Total Cost |  |  | 21600
Contract Admin Labor Breakdown
Assumptions:
A third party A&E firm would be hired to do the sampling and data reporting
Third Party Construction Management Cost Reconciliation is located under "Inputs"
| Rate | Quantity | Cost
Project Manager | 160.435 | 40 | 6417.4
Staff Scientist/Sr. Field Tech | 138.735 | 8 | 1109.88
Field Technician (2) | 123.6525 | 16 | 1978.44
Admin Support | 71.5525 | 8 | 572.42
CAD/Drafting | 62 | 0 | 0
10078.14
Contract Admin Labor Breakdown, Total Cost ($/YEAR) |  |  | 10078.14
Field Work Per Sampling Event
Assumptions:
Each sampling event will take 7 days at 10 hrs per day
This includes 10 hours of preparation and 10 hours of post sampling work
There are two sampling events per year
Project Manager | 160.435 | 16 | 2566.96
Staff Scientist/Sr. Field Tech | 138.735 | 16 | 2219.76
Field Technician (2) | 123.6525 | 140 | 17311.35
Admin Support | 71.5525 | 8 | 572.42
CAD/Drafting | 62 | 0 | 0
Supplies | 1000 | 1 | 1000
23670.49
Field Work, Total Cost ($/YEAR) |  |  | 23670.49
Sample Shipping
Assumptions:
All the samples from one event can fit into 4 coolers
The estimated cost to ship an cooler overnight to the lab is $100
There are two sampling events per year
Sample Shipping Cost ($/YEAR) |  | 100 | 8 | 800
Sample Shipping, Total Cost |  |  | 800
Report Preparation
Assumptions:
The technical staff requires 40 hours to prepare the final report per sampling event
Management requires 4 hours to review and edit the report per sampling event
There are two sampling events per year
Project Manager | 160.435 | 8 | 1283.48
Staff Scientist/Sr. Field Tech | 138.735 | 8 | 1109.88
Field Technician(2) | 123.6525 | 160 | 19784.4
Admin Support | 71.5525 | 8 | 572.42 | Report prep support 4 hours
CAD/Drafting | 62 | 16 | 992 | Report production 8 hours
Reproduction & graphics | 25 | 16 | 400 | Report production 8 hours
24142.18
| Report Preparation ($/YEAR) |  | 24142.18
Water Quality Monitoring Sites, Total Cost ($/YEAR) |  |  | 80290.81
Embankment Piezometer Monitoring
Assumptions:
MR and KP began implementation of a remote monitoring system in June 2018
Vibrating wire piezometer data is transmitted from the monitoring sites to an on-line system via cellular and radio connection
Data is viewable in live-time on Sensemetrics online system
The system allows for alerts to be programed for sites
Trigger elevations can be set and and email notifications can be sent to MR and KP
The system allows for live-time assessment of YDTI sites and West Ridge hydrodynamic containment
Select standpipes and VWP have been as Quantitative Performance Parameters (QPP) in the TOMS Manual and are used to assess the performance of the YDTI
According to the Q2 2019 Quarterly Piezometer Monitoring Report there are 100 active instruments located on the TDTI and in the West Ridge
This includes 39 standpipes piezometes/monitoring wells and 61 drillholes with vibrating wire piezometers (VWP) which are connected to the Remote Monitoring System
In Q1 2020, 9 more VWP will be added
During the POST CLOSURE period, besides DEQ and MR, a third party engineering firm will be needed to evaluate the transmitted data
The third party engineering firm would provide an analysis of monitoring data on a quarterly basis
Estimated yearly cost to retain a third party enginnering firm is $25,000 per year
Assume the monitoring program is for 20 years from 2025 to 2045
Embankment Piezometer Monitoring, Total Cost ($/YEAR) |  |  | 25000
Task 2 Long Term Monitoring Sites Per Year, Total Cost ($/YEAR) |  |  |  | 105290.81
Task 3 Construct Spillway at Closure
See Spillway tab calculations
Task 3 Construct Spillway at Closure, Total Cost |  |  | 0
Task 4 Plug WED
Assumptions:
After closure, seepage to a flow through the WED will steadly decrease as the impoundment drains down and the pond level decreases
Under the full extent of operations/filling in Amendment 010, the pond level was expected to approach the 6380 foot target level for maintaining hydrodynamic containment
After approximatelyt 20 years of draindown, the south end of the WED would be grouted or otherwise plugged to preclude drainage to the Extraction Pond
Based on modeling for the next 5 years, the pond is not predicted to reach 6380 feet, therefore pumpback is not required for flow containment
The WED is designed to transmit 4,500 gallons per minute
The cross sectional area is 300 Square Feet
The drain rock is approximately 7 feet thick and 43 feet wide
The depth to WED invert from embankment crest is 110 feet
According to the Reclamation Overview Design Document (page 10 of 15) the WED connection to the Extraction Pond will be decommissioned by
-grouting the section of the drain through the topographic boundary "Rocky Knob"
Based on data provided in RS Means (Section A10 Foundations) Cast-in-Place Concrete Piles
To stop the flow, 4 rows of Cast-in-Place piles 2 feet apart across the WED are necessary
A total of 80 piles are required
Based on cost data provided by RS Means, one row of Cast-in-Place piles will cost $125,000 each
Assuming 4 rows are required, the total cost is $500,000
Task 4 Plug WED, Total Cost |  | 500000
Task 5 Site Maintenance Post Closure Per Year
Repair or Clean out the Extraction Pond
Assumptions:
The Extraction Pond may become damaged or require maintenance
The Extraction Basins with two installed wells would remove seepage from the WED and return to the YDTI, while the pond is repaired
The nature and extent of the repair or clean out work is unknown, so a yearly cost of $50,000 is assumed
It is assumed that the pond elevation will not exceed 6380 feet in the next 5 years, see "Water Treatment" tab
Therefore, hydrodynamic containment through use of the WED and other contingency features would not be required.
The Extraction Pond would not be needed to contain water prior to treatment and being pumped back to the YDTI pond
The WED would be plugged in the case of an unforeseen closure in the next 5 year period.
Repair or Clean out the Extraction Pond Per Year, Total Cost ($/YEAR) |  |  |  | 0
Maintain Electrical System for Extraction Basin
Assumptions:
The electrical systems need to be maintained on the west side to run the two subermersible pumps in the Extraction Basin
Assume a yearly cost of $10,000 to maintain the electrical systems on the west side
It is assumed that the pond elevation will not exceed 6380 feet in the next 5 years, see "Water Treatment" tab
Therefore, hydrodynamic containment through use of the WED and other contingency features (extraction basins) would not be required.
The WED would be plugged in the case of an unforeseen closure in the next 5 year period.
Maintain Electrical System for Extraction Basin Per Year, Total Cost ($/YEAR) |  |  |  | 0
Install Submersible Pumps in Extraction Basins
Assumptions:
The WED was designed to operate with continious pumping at the Extraction Pond at a design flow of 4,500 gpm
The Extraction Basin was in the designed to have an operations ready alternative pumping option
The Extraction Basin pump intake assemble is operational but the pumps have not been purchased
The Extraction Basin discharge pipeline assemble has NOT been installed
The Extraction Basin pumping system, two 2,250 gpm submersible pumps, have NOT been purchased
Based on cost data obtained from RS Means (22 14 2100) one submersible pump cost approximately $16,000
The discharge pipeline with a pressure transducer, air release valve, and flow meter is estimated to cost another $10,000 each
Electrical Costs estimated at $10,000 per year
The estimated total cost is | 53000
It is assumed that the pond elevation will not exceed 6380 feet in the next 5 years, see "Water Treatment" tab
Therefore, hydrodynamic containment through use of the WED and other contingency features (extraction basins) would not be required.
The WED would be plugged in the case of an unforeseen closure in the next 5 year period.
Install Submersible Pumps in Extraction Basins Per Year, Total Cost ($/YEAR) |  |  |  | 0
Maintaining and Periodically Replace Piezometers and Cellular Connection
Assumptions:
Vibrating wire piezometer data is transmitted from the monitoring sites to an on-line system via cellular and radio connection
Data is viewable in live-time on Sensemetrics online system
Annual repair, maintainace, replacement, and upgrade of the system would be necessary
The nature and extent of the work repair/replace/upgrade work is unknown, so an annual cost of $25,000 is assumed
Maintaining and Periodically Replace Piezometers and Cellular Connection Per Year, Total Cost ($/YEAR) |  |  |  |  | 25000
Task 5 Site Maintenance Post Closure, Total Cost Per Year ($/YEAR) |  |  |  | 25000
Task 6 Purchase Terramac (from Task 1 - Dust Control) |  |  |  | 334866
2019 Final EIS: "Final reclamation would include a partial wet closure with a reclaimed beach and Transition Zone, and a pond volume of approximately 1,000 acre-feet." Reclamation would be accomplished incrementally as the tailings water recedes, exposing more Transition Zone for reclamation until the pond volume reaches approximately 1,000 acre-feet at equilibrium.
9/22/2020 KP Spillway Memo: "The 95th percentile result indicates that under unusually wet conditions the post-closure pond volume will be approximately 2,000 ac-ft once the pond has reached a ‘steady-state’ condition. The 95th percentile volume was adopted for this conceptual design as a conservative measure." “The pond in Year 2025 is expected to have a volume of 15,000 ac-ft and be at approximately elevation 6,376 ft; therefore, the minimum crest elevation is anticipated to be 6,398 ft, which is below the currently constructed embankment elevation of 6,400 ft.”
10/2/2020 Response from MR: "The tailings beach surface modelled for the “Projected 2025 Disturbance Areas” map assumed an operating pond of 15,000 ac-ft, which would cover a total of 365 acres in 2025. The 15,000 ac-ft pond-beach interface/elevation in 2025 is delineated on the map, but the acreage has not been added to the Excel table to avoid duplication. The beach area between the 2025 15,000 acft operating pond elevation and the post-closure steady-state pond is the transition zone, which will be progressively reclaimed in five-year post-closure time steps as the pond recedes.
A 15,000 ac-ft operating pond was selected for the 2025 model based on the estimated pond volume reduction that will occur as a result of the Berkeley Pit Pilot Project. The Pilot Project is designed to facilitate the discharge of up to 10 MGD from site and has achieved an approximate net deficit of 2.4 MGD from the YDTI pond through one year of operation. Based upon extrapolating this deficit, as well as a conservative loss, the pond volume is estimated to reach the target operating volume of 15,000 ac-ft in Q4 2024 or Q1 2025."

## ITEM 6 Interim Management
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
Item 6 Interim Management
Assumptions:
Based on DEQ's experience with previous operation bankruptcy, approximately a one-year period of interim maintenance is needed
This tab represents the cost to maintain the essential operations while the agency gets the bond
A third party A&E firm would be hired to monitor the site during the interim period
Third Party Construction Management Cost Reconciliation is located under "Inputs"
The interim site maintenance activities that were identified mainly deal with controlling dust off the impoundment,
erosion control, and weed spraying.
Dust control for closure year 1 is included in Post-Closure tab, not duplicated here
Water monitoring is covered under Post Closure tab, not duplicated here.
Fluids from the Concentrator and Precipitation Plant are exempt (pre-1971), so no reclamation cost can be bonded.
Assume that 8 employees would be needed to monitor the earthwork contractor and implement the reclamation plan
The 8 people would be needed to cover the mine site 24 hours a day, 7 days a week
The 8 key people include:
|  |  | Hourly Rate | Annual Salary
| 1 - Site Manager |  | 160.435 | 333704.8
| 1 - Site Engineer |  | 138.735 | 288568.8
| 2 - Site Security Officers |  | 40 | 83200
| 1 - Administrative Aide |  | 71.5525 | 148829.2
| 2 - Laborer (surface) |  | 124 | 257920
| 1 - Mechanic |  | 46 | 95680
Total Personnel | 8 |  |  | 1207902.8
The staffing schedule for the interim period would be as follows:
|  | Interim Period | Annual Salary | Total Site A&E Management Cost
1/2 - Site Manager |  | 0.5 | 333704.8 | 166852.4
1 - Site Engineer |  | 1 | 288568.8 | 288568.8
2 - Site Security Officers |  | 2 | 83200 | 166400
1 - Administrative Aide |  | 1 | 148829.2 | 148829.2
2 - Laborer (surface) |  | 0.5 | 257920 | 128960
1 - Mechanic |  | 0.25 | 95680 | 23920
|  |  | 1207902.8 | 923530.4
Other costs include: |  |  |  | Total 1 Year A&E Other Costs
4 - Site Pickup Trucks (including fuel & maintenance) ($/YR) |  |  |  | 50400
Electrical Cost per Year ($/YR) |  |  |  | 20000
Heavy Equipment Rental |  |  |  | 4800
Site Maintenance Supplies |  |  |  | 60000
Office Space, Operating Supplies & Misc |  |  |  | 10000
| Total Annual Cost ($/YR) |  |  | 145200
Item 6 Interim Management, Total Cost |  |  |  | 1068730.4

## ITEM 7 A&E-ClosureMgmt
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
Item 7 A&E Closure Reclamation Management
Assumptions:
It is assumed the during the closure period reclamation would start in earnest beginning in year 2026 and take approximately 4 years to complete
A third party A&E firm would be hired to implement the approved reclamation plan
Third Party Construction Management Cost Reconciliation is located under "Inputs"
Assume that 8 employees would be needed to monitor the earthwork contractor and implement the reclamation plan
The 8 people would be needed to cover the mine site 24 hours a day, 7 days a week
The 8 key people include:
|  |  | Hourly Rate | Annual Salary
| 1 - Site Manager |  | 160.435 | 333704.8
| 1 - Site Engineer |  | 138.735 | 288568.8
| 2 - Site Security Officers |  | 40 | 83200
| 1 - Administrative Aide |  | 71.5525 | 148829.2
| 2 - Laborer (surface) |  | 124 | 257920
| 1 - Mechanic |  | 46 | 95680
Total Personnel | 8 |  |  | 1207902.8
The staffing schedule for year 2 through year 5 would be as follows:
|  | Year 2 (yr 2026) | Year 3-5 (yr 2027-2029) | Total | Annual Salary | Total Site A&E Management Cost
1/2 - Site Manager |  | 0.5 | 1.5 | 2 | 333704.8 | 667409.6
1 - Site Engineer |  | 1 | 3 | 4 | 288568.8 | 1154275.2
2 - Site Security Officers |  | 2 | 6 | 8 | 83200 | 665600
1 - Administrative Aide |  | 1 | 3 | 4 | 148829.2 | 595316.8
2 - Laborer (surface) |  | 0.5 | 1.5 | 2 | 257920 | 515840
1 - Mechanic |  | 0.25 | 0.75 | 1 | 95680 | 95680
|  |  |  | Total | 1207902.8 | 3694121.6
Other costs include: |  |  |  | Annual Cost | Total 4 Years A&E Other Costs
4 - Site Pickup Trucks (including fuel & maintenance) ($/YR) |  |  |  | 50400 | 201600
Electrical Cost per Year ($/YR) |  |  |  | 20000 | 80000
Heavy Equipment Rental |  |  |  | 4800 | 19200
Site Maintenance Supplies |  |  |  | 60000 | 240000
Office Space, Operating Supplies & Misc |  |  |  | 10000 | 40000
| Total Annual Cost ($/YR) |  |  | 145200 | 580800
Item 7 A&E Closure Reclamation Management, Total Cost |  |  |  |  | 4274921.6

## ITEM 8 A&E-PostClosureMgmt
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
Item 8 A&E Post Closure Management
Assumptions:
A third party A&E firm would be hired to implement the post closure reclamation plan
Third Party Construction Management Cost Reconciliation is located under "Inputs"
It is assumed the "Post Closure" period would begin five years after "Closure" begins (so year 2030)
These A&E calculations apply to management and oversight for activities conducted from 2030-2055 (25 years) (see Post-Closure Reclamation tab)
Assume that 5 employees would be needed to maintain the mine site and deal with environmental problems
The 5 people would be needed to cover the mine site 24 hours a day, 7 days a week
The 5 key people include:
|  |  | Hourly Rate | Annual Salary
| 1 - Site Manager |  | 160.435 | 333704.8
| 1- Site Security Officers |  | 40 | 83200
| 1 - Administrative Aide |  | 71.5525 | 148829.2
| 1 - Laborer (surface) |  | 124 | 257920
Total Personnel | 4 |  |  | 823654
The staffing schedule for year 2030 through 2055 would be as follows:
|  | Staffing Year 2030-2055 | Annual Salary | Total Site A&E Management Cost
1/2 - Site Manager |  | 0.5 | 333704.8 | 166852.4
1 - Site Security Officers |  | 1 | 83200 | 83200
1 - Administrative Aide |  | 0.5 | 148829.2 | 74414.6
1 - Laborer (surface) |  | 0.5 | 257920 | 128960
|  |  | 823654 | 453427
Other costs include: |  |  |  | Total 25 Years A&E Other Costs
2 - Site Pickup Trucks (including fuel & maintenance) ($/YR) |  |  |  | 25200 |  |  | Monthly | Annual
Electrical Cost per Year ($/YR) |  |  |  | 20000 |  | Example for commercial customer | 1563.55 | 18762.6
Heavy Equipment Rental |  |  |  | 4800 |  |  | Rounded | 20000
Site Maintenance Supplies |  |  |  | 20000
Office Space, Operating Supplies & Misc |  |  |  | 10000
Total Annual Cost ($/YR) |  |  |  | 80000
Post-closure electrical costs are assumed to include office space and equipment, lighting/security around the facility, any hard-wired monitoring systems
Electrical usage related to water treatment would apply to Superfund remedy costs, water management (WED) would not be needed in next 5 year period
inflation rate, I = | 2%
discount rate, r = | 3%
|  |  |  | Nominal | Present
| Year |  | Annual O&M | Value | Value
| 2026 |  | Accounted for in "Closure" timeframe
| 2027 |  | Accounted for in "Closure" timeframe
| 2028 |  | Accounted for in "Closure" timeframe
| 2029 |  | Accounted for in "Closure" timeframe
| 2030 |  | 533427 | 577398.5398 | 513011.1241
| 2031 |  | 533427 | 588946.5106 | 508030.4336
| 2032 |  | 533427 | 600725.4408 | 503098.0993
| 2033 |  | 533427 | 612739.9496 | 498213.6517
| 2034 |  | 533427 | 624994.7486 | 493376.626
| 2035 |  | 533427 | 637494.6436 | 488586.5616
| 2036 |  | 533427 | 650244.5365 | 483843.0028
| 2037 |  | 533427 | 663249.4272 | 479145.4979
| 2038 |  | 533427 | 676514.4157 | 474493.5999
| 2039 |  | 533427 | 690044.7041 | 469886.8659
| 2040 |  | 533427 | 703845.5981 | 465324.8575
| 2041 |  | 533427 | 717922.5101 | 460807.1404
| 2042 |  | 533427 | 732280.9603 | 456333.2847
| 2043 |  | 533427 | 746926.5795 | 451902.8644
| 2044 |  | 533427 | 761865.1111 | 447515.458
| 2045 |  | 533427 | 777102.4133 | 443170.6477
| 2046 |  | 533427 | 792644.4616 | 438868.0201
| 2047 |  | 533427 | 808497.3508 | 434607.1655
| 2048 |  | 533427 | 824667.2978 | 430387.6785
| 2049 |  | 533427 | 841160.6438 | 426209.1573
| 2050 |  | 533427 | 857983.8567 | 422071.2043
| 2051 |  | 533427 | 875143.5338 | 417973.4257
| 2052 |  | 533427 | 892646.4045 | 413915.4312
| 2053 |  | 533427 | 910499.3326 | 409896.8348
| 2054 |  | 533427 | 928709.3192 | 405917.2539
| 2055 |  | 533427 | 947283.5056 | 401976.3097
11838562.1964
Item 8 A&E Post Closure Management, Total Cost |  |  |  |  | 11838562.1964
Note on G50: Garrett Smith: This assumes the bond was received and invested in 2025, although not needed until 2030. This row has been adjusted for inflation and growth from 2026 to 2030

## ITEM 9 Dump Areas
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
Item 9 Cost Summary for Earthwork - Dump Areas
Direct Costs
Task 1 Reclaim East Dump Complex
| Item 1 | Item 2 | Item 3
| East Dump | Hillcrest Dump | North East Dump
Reslope Dump Slopes and Top | 613388.1313 | Released | Released
Construct Surface Water Collection Ditches | 57375.225 | 272863.25 | Released
Haul & Spread Alluvium | 2838407.4356 | Released | Released
Alluvium Testing & Amendment | 359417.8008 | Released | Released
Establish Vegetation & Weed Control | 246090.4234 | 35078.3379 | 28299.5601
Total | 4114679.0161 | 307941.5879 | 28299.5601
Task 2 Reclaim Pittsmont and Other Dumps
| Item 1 | Item 2 | Item 3 | Item 4 | Item 5 | Item 6
| Access Dump | Woodville Dump | Great Northern Dump | Nalley Valley Dump | S. Continental Pit Dump | Pittsmont Dump
Reslope Dump Slopes and Top | 75400.6512 | Released | Pre-1974 | 294035.4637 | 51369.8497 | 454664.1166
Construct Surface Water Collection Ditches | 3825.015 | Released | - | 3825.015 | 2486.2598 | 26775.105
Haul & Spread Alluvium | 427434.5937 | Released | - | 523918.3181 | 466151.8663 | 1348671.7338
Alluvium Testing & Amendment | 60786.6796 | Released | - | 108073.2368 | 81770.691 | 281417.675
Establish Vegetation & Weed Control | 29234.0371 | 3267.1138 | - | 53347.4476 | 38765.4376 | 136336.2684
Total | 596680.9765 | 3267.1138 | 0 | 983199.4812 | 640544.1044 | 2247864.8988
|  | Item 9 Earthwork - Dump Areas Total Cost |  | 8922476.7389
|  | Pre-1974 Bond |  | 78500
ACREAGES FROM 2025 SITE PLAN MAP
Feature | OP 00030A | OP 00041 | OP 00108 | OP 00030 | Grand Total
RDS East |  | 11.3901 | 37.7439 |  | 49.134
RDS East Partially Reclaimed/Released |  | 12.8588 | 73.6069 |  | 86.4657
RDS East Crest |  | 23.2692 | 16.7231 |  | 39.9924
RDS Hillcrest Partially Reclaimed/Released |  |  | 47.5128 |  | 47.5128
RDS North East Partially Reclaimed/Released |  | 32.205 | 0.013236 |  | 32.2183
RDS Pittsmont | 64.138 |  |  | 19.4215 | 83.5595
RDS Pittsmont Crest | 23.3856 |  |  | 5.0759 | 28.4614
RDS Access | 18.8664 |  |  | 16.545 | 35.4113
RDS Woodville Partially Reclaimed/Released |  |  | 2.1781 |  | 2.1781
RDS Nalley Valley | 33.7909 |  |  | 49.3405 | 83.1314
RDS South Continental Pit | 3.1791 | 7.5987 |  |  | 10.7778
RDS South Continental Pit Crest | 6.1391 | 8.3681 |  |  | 14.5073
RDS Great Northern |  |  |  | 66.7961 | 66.7961
TOTAL | 149.4991 | 95.69 | 177.7781 | 157.179 | 580.1462
PRE-1974 BOND |  |  |  | 78500
ACRES FOR BOND CALCULATIONS BELOW | 422.9672
The permit boundaries do not affect the cost estimates, so the acreages are being grouped in the following manner in the calculations:
Feature | Acres in 00030A, 00041, and 00108
RDS East | 49.134
RDS East Partially Reclaimed/Released | 86.4657
RDS East Crest | 39.9924
RDS Hillcrest Partially Reclaimed/Released | 47.5128
RDS North East Partially Reclaimed/Released | 32.2183
RDS Pittsmont | 64.138
RDS Pittsmont Crest | 23.3856
RDS Access | 18.8664
RDS Woodville Partially Reclaimed/Released | 2.1781
RDS Nalley Valley | 33.7909
RDS South Continental Pit | 10.7778
RDS South Continental Pit Crest | 14.5073
Item 9 Earthwork - Dump Areas- ONLY OP# 00030A, 00041, 00108
Task 1 Reclaim East Dump Complex
Feature | Acres in 00030A, 00041, and 00108 | 2008 Release Acres
RDS East | 47.5128
RDS East Crest | 64.138
RDS East Partially Reclaimed/Released | 32.2183 | 52
RDS Hillcrest Partially Reclaimed/Released | 23.3856 | 46
RDS North East Partially Reclaimed/Released | 18.8664 | 68
Some areas of previous reclamation have been disturbed by D-East Pushback
Reslope Dump Slopes and Top
Assumptions:
Only the East Dump (not partially reclaimed/released) needs resloping
Based on 2025 Site Plan Map, the East Dump acreage is:
Feature | Acres | Corrected for slope
Item 1 East Dump | 47.5128 | 50.0072
Item 1 East Dump Crest | 64.138 | -
The reclamation of the East Dump would include:
Resloping the east side (along the Clearwater Ditch) and south side (near Hillcrest Dump) to a 3H:1V slope
Reslope the west side (along the Continental Pit) to a 2.7H:1V slope
Blend the north end to the North East Dump reclamation and southwest end to the Hillcrest Dump reclamation
Reslope the top of the dump to keep the water from ponding by providing drainage swales
The existing dump slope angle are at angle of repose, approximately 40 degrees
The East Dump northern segment final top elevation is 6,300 feet
The East Dump southern segment final top elevation is 6100 feet
With respect to the dump-slope bulldozer work:
Contour Interval | Bench Height | East Side Crest Length | West Side Crest Length | East Side Volume (cut & fill AOR to 3H:1V slope) | West Side Volume (cut & fill AOR to 2.7H:1V slope)
5780 | 20 | Regraded | 250 | 0 | 1445
5800 | 20 | Regraded | 400 | 0 | 2312
5820 | 20 | Regraded | 850 | 0 | 4913
5840 | 20 | 1200 | 1100 | 8064 | 6358
5860 | 20 | 1000 | 1400 | 6720 | 8092
5880 | 20 | 800 | 1600 | 5376 | 9248
5900 | 20 | 1800 | 1650 | 12096 | 9537
5920 | 20 | 1600 | 1300 | 10752 | 7514
5940 | 20 | 3000 | 1250 | 20160 | 7225
5960 | 20 | 3800 | 1200 | 25536 | 6936
5980 | 20 | 3800 | 4400 | 25536 | 25432
6000 | 20 | 3600 | 4400 | 24192 | 25432
6020 | 20 | 4800 | 4500 | 32256 | 26010
6040 | 20 | 5800 | 4600 | 38976 | 26588
6060 | 20 | 6000 | 4800 | 40320 | 27744
6080 | 20 | 5800 | 4600 | 38976 | 26588
6100 | 20 | 5600 | 4400 | 37632 | 25432
6120 | 20 | 2600 | 2000 | 17472 | 11560
6140 | 20 | 2600 | 2000 | 17472 | 11560
6160 | 20 | 2400 | 2000 | 16128 | 11560
6180 | 20 | 2200 | 1800 | 14784 | 10404
6200 | 20 | 2000 | 1800 | 13440 | 10404
6220 | 20 | 1900 | 1900 | 12768 | 10982
6240 | 20 | 1800 | 1800 | 12096 | 10404
6260 | 20 | 1700 | 1700 | 11424 | 9826
6280 | 20 | 1700 | 1700 | 11424 | 9826
6300 | 20 | 1750 | 1750 | 11760 | 10115
Total |  | 69250 | 61150 | 465360 | 353447
The total cut, fill, and rehandle volume (LCY) |  | 818807
The cut, fill, and rehandle volume assumes every particle of waste rock is handled twice
With respect to dump-top bulldozer work:
The top of the dump is regraded to keep the water from ponding by providing drainage swales
Since the volume of regrade is unknown, DEQ assumes a two-Cat D10 dozer production of 1/4 acre per hour each
East Dump Dozer Production Calculation
Machine Properties
| Machine | D10T
| Blade | SU
| Dual Tilt | Yes
| % Availability | 90%
| Wt (LBS) | 146950
| Shoe Width (IN) | 28
| Density (LBS/LCY) | 2800
| Dozeability | 1
Derating Factors
| Attitude | 6450
| Visibility | 1
| Job Efficiency | 83%
| Skill Level | 75%
Input Values
| Push Distance (FT) | 100
| Push Slope | 0%
| Volume of Material (LCY) | 818807
Output Values
| Productivity (LCY/HR) | 1500
| Adjusted Productivity (LCY/HR) | 840.375
| Total Hours (1 machine) | 974.3353
| Total Hours (2 machines) | 487.1676
| Total Cost (2 machines) | 485540.4936
East Dump-Top Dozer Production Calculation
Area of East Dump Top (AC) |  | 64.138
2 - Cat D10T Dozer Production (AC/HR) |  | 0.5
Job Hours - 2 Cat D10T (HR) |  | 128.2761
Total Cost D10T |  | 127847.6377
Item 1
East Dump
Reslope Dump Slopes and Tops, Total Cost |  | 613388.1313
Construct Surface Water Collection Ditches
Assumptions:
After the slopes are recontoured to the final configuration, a survey party will locate the surface water ditches
To construct the ditches along the slope, a D8T dozer would walk back out to the slopes, and using the blade push the muck downslope creating a berm with a "U" bottom
Based on discussion with another mining company, a D8T dozer can cut, shape, and finish blading 100 feet of ditch per hour
A survey party fee of 15% is also included
|  | Item 1 | Item 2
|  | East Dump | Hillcrest Dump
Estimated Length of Surface Water Ditches (FT) |  | 15000 | 11000
D8T Production Rate (FT/HR) |  | 100 | 100
Job Hours (HR) |  | 150 | 110
Total Construction Cost |  | 49891.5 | 36587.1
15% Survey Party Fee |  | 7483.725 | 5488.065
Total Cost |  | 57375.225 | 42075.165
Construct Surface Water Collection Ditches, Total Cost |  | 57375.225 | 42075.165
Construct Rip Rap Channel Protection
Without a surface water design for the Hillcrest Dump, to estimate reclamation cost DEQ makes the following assumptions:
Approximately 11,000 feet of ditches will need to be constructed across the Hillcrest Dump
The upper portion of the diches will be grassy swales, while the lower portions will be rip rap lined with a plunge pools
At the lower end, the ditches will be trapezoid shape, approximately 20 feet wide, so a 20 ton articulating truck and hydraulic excavator can place rip rap
The rip rap will be lined with locally derived material
A portable screening and crushing plant will be necessary to manufacture bedding material
Large size rip rap can be taken from onsite stockpiles
The equipment necessary to accomplish this task includes:
Cat 950 Loader
Cat 740 Articulating Truck
Cat 720 Articulating Truck
Cat 320 Excavator
DEQ would have to hire a 3rd party engineering firm to design the system
Since the soils are so erosive, assume 30% of the 11,000 feet of ditch will require rip rap lining
Based on the 2020 Black Butte Copper Mine bond estimate, the estimated cost for a completed rip rap lined ditches is $60 per foot
Engineering fee of 15% is also included
Item 2
Hillcrest Dump
Estimated Length of Surface Water Collection Ditches (LF) |  |  | 11000
Estimated Length Requiring Rip Rap Lining (FT) |  |  | 3300
Average Construction Cost per Foot ($/FT) |  |  | 60
Total Construction Cost |  |  | 198000
15% Engineering Fee |  |  | 29700
Total Cost |  |  | 227700
|  | Item 1 | Item 2
|  | East Dump | Hillcrest Dump
Construct Surface Water Collection Ditches, Total Cost |  | 57375.225 | 272863.25
Haul & Spread Alluvium
Assumptions:
According to the application the Central Zone alluvium will be salvaged for reclamation material
The slopes of the East Dump will be covered with 20 inches of alluvium, while the top get covered with 28 inches of alluvium
Item 1
The estimated volume of alluvium to cover the East Dump is: |  |  | East Dump
Area | Acres (Slope corrected) | Cover Soil (IN) | Volume of Soil Required (LCY)
East Dump Slopes | 50.0072 | 20 | 134463.7642
East Dump Tops | 64.138 | 28 | 241444.088
Total | 114.1452 |  | 375907.8522
The estimated volume of alluvium to cover slopes and top of East Dump (LCY) |  |  | 375907.8522
Contingency Volume (15% extra)(LCY) |  |  | 432294.0301
The density of the alluvium (LBS/LCY) |  |  | 3300
The estimated weight of alluvium (TONS) |  |  | 713285.1496
The estimated haul distance at 4% grade (FT) |  |  | 13200
DEQ assumes that the Cat 6020B Hydraulic Excavator and 10-Cat 777 Haul Trucks will be used to mine, load, and haul the alluvium
Assume two Cat 10T are with the hauling operation, spreading the alluvium takes twice the hauling hours
Haul 13,200 feet One Way, Total Resistance 10%
Cat Edition 45 p.10-55 Cat 777G Haul Truck Rimpull-Speed-Gradeability Curve Loaded Speed (MPH) |  |  | 12
Cat Edition 45 p.10-55 Cat 777G Haul Truck Rimpull-Speed-Gradeability Curve Empty Speed (MPH) |  |  | 20
Item 1
Hauler Cycle Time (MIN) | East Dump
Load with Exchange | 2.45
Haul | 12.5
Dump and Maneuver | 1.6
Return | 7.5
Potential Cycle Time | 24.05
Wait on Slow Hauler | 0
Wait to Load, Bunching AVG | 0 | Bunching Calc | # of Trucks (hauler capabilities)
Total Cycle Time (MIN) | 24.05 | 21.6 | 8.8163
Cycles per 60 min Hour (CYCLES/HR) | 2.4948
Cat 777G Average Capacity (LCY) | 77
Hauler Potential Production Per Hour (LCY/HR) | 192.0998
6020B Passes per Hauler | 5 | 5.1333
Loader Cycle Time (MIN) | 0.7
Load Time Truck (MIN) | 3.5
Number of Trucks Required (EA) | 6.8714 | # of Trucks (loader capabilities)
Production Rate (LCY/MIN) | 22
Hourly Production (LCY/HR) | 1320
Efficiency Factor | 0.83
Availability | 0.9
Adjusted Hourly Production (LCY/HR) | 986.04
Hours Required (HR) | 438.4143
Item 1 | East Dump
| Qty | Model | Hourly Cost Each Unit | Operating Hours | $ Total | $ per Ton | $ per LCY
Loaders: | 1 | 6020B | 629.72 | 438.4143 | 276078.249 | 0.38705 | 0.63864
Haulers: | 6.8714 | 777D | 468.39 | 3012.5325 | 1411040.0992 | 1.9782 | 3.2641
Support: | 1 | 14H Motor Grader | 194.65 | 438.4143 | 85337.3422 | 0.11964 | 0.19741
| 1 | D8T | 332.61 | 438.4143 | 145820.9782 | 0.20444 | 0.33732
| 1 | 2,500 gal Water Truck | 105.45 | 438.4143 | 46230.7873 | 0.064814 | 0.10694
Fleet Totals | 10.8714 |  |  | 4766.1897 | 1964507.4558 | 2.7542 | 4.5444
Spreading Alluvium
Assume two Cat 10T are with the hauling operation, spreading the alluvium takes twice the hauling hours
Hauling Hours (HR) |  | 438.4143
Job Hours (HR) |  | 876.8286
Equipment Cost | Cat D10T | 436949.9899
| Cat D10T | 436949.9899
| Total | 873899.9797
Item 1
East Dump
Haul & Spread Alluvium, Total Cost |  | 2838407.4356
Alluvium Testing & Amendment
Assumptions:
MR submitted a plan on 8/23 & 9/20/02 to DEQ for a 2002 reclamation program of the Woodville Dump
The plan was a modification to the Reclamation Plan and given minor revision number (MR 02-001)
MR's reclamation cover soil recipe can be found in Table 9-2 of the Amendment 10 Application
DEQ assumes that this is used on the East Dump reclamation
Based on the 2020 Annual Report, very little soil has been stockpiled, therefore DEQ will assumes the Central Zone alluvium will be salvaged for reclamation material
DEQ assumes the following Central Zone alluvium sampling and analysis schedule | [5 empty] | Item 1
East Dump
| Analyses | Volume of Soil (LCY) | Frequency (LCY) | Cost ($) | Shipping ($) | Total Cost ($)
| Paste pH | 432294.0301 | 2500 | 0 | in house | 0
| Total Metals ICP Scan | 432294.0301 | 30000 | 225 | 10 | 3386.3032
| Cu & Zn | 432294.0301 | 10000 | 45 | 10 | 2377.6172
| Organic Content | 432294.0301 | 2500 | 15 | 10 | 4322.9403
[5 empty] | Total | 10086.8607
And 1.5% organic matter by weight or 23 tons per acre is also require
Based on recent sampling data, the Central Zone alluvium will not required a lime amendment
Assume the compost would come Western Reclamation Inc. in Butte at a cost of $20/CY
The compost is stored at a central location, assume $5/CY extra to move it to where it will be spread
The Estimated Compost Cost
Area (AC) |  | 114.1452
Density of Compost (LBS/CY) |  | 1000
Cost per CY delivered to Butte ($/CY) |  | 25
Total Cost of Compost |  | 131267.0087
DEQ requests a qualified soils scientist (with a pickup truck) will be with the alluvium salvage operation full time for lab work, QA/QC and record keeping
The estimated cost for a qualified soil scientist (with a pickup), from a Consulting Firm, is $150 per hour
The number of work hours for the soil scientist is equal to the scheduled hours for the alluvium spreading operation
A portable soil testing trailer will be rented for laboratory space, sampling equipment storage, and record keeping
The estimated cost for a soil trailer rental is $200 per month
The Estimated Cost for Full Time Soils Scientist
Soil Scientist Hourly Rate ($/HR) |  | 150
Number of Hours (HR) |  | 438.4143
Total Cost of Soils Scientist |  | 65762.144
The Estimated Cost for a Soils Trailer
Soils Trailer Monthly Rate ($/MO) |  | 200
Number of Months (MO) |  | 2.1921
Total Cost for Trailer |  | 438.4143
To spread the compost, piles are built up along the dump crest and pushed down slope with a D8T dozer
DEQ assume two-Cat D8T dozers will be used to spread the compost at a production rate of 1/4 acre per hour
After spreading, the compost will be incorporated into the top 4 inches using a harrow that is drag along behind the seeder
The Estimated Cost Spreading Compost
Area of East Dump (AC) |  | 114.1452
2 - Cat D8T Dozer Production (AC/HR) |  | 0.5
Job Hours - 2 Cat D8T (HR) |  | 228.2904
Total Cost D8T |  | 151863.3731
Item 1
East Dump
Alluvium Testing & Amendment, Total Cost |  | 359417.8008
Establish Vegetation & Weed Control
Assumptions:
The estimated revegetation and weed spraying cost for a 5-year period is $1,500 per acre, which includes minor erosion repair and seeding,
applying fertilizer, BMPs, etc.
The seeding is accomplished using a small dozer with a seeder attached to the front and a harrow pulled behind.
Includes partially released areas
|  | Item 1 | Item 2 | Item 3
|  | East Dump | Hillcrest Dump | North East Dump
Area of East Dump (AC) |  | 146.3635 | 23.3856 | 18.8664
Estimated Vegetation & Weed Control Cost ($/AC) |  | 1500 | 1500 | 1500
Total Cost |  | 219545.2234 | 35078.3379 | 28299.5601
Hillcrest Soil Hot Spots
Assumptions:
To fix the hot spots, DEQ assumes a small track loader would be used to dig up the poor quality soil, spread lime, and good quality soil
This calculation assumes a small Cat 725 Articulating dump truck is stationed on a haul road below each hot spot
A small Cat excavator traverses the dump scrapes-up the poor soil and piles it next to the hot spots
A skidsteer loader (w/rubber track) drives up from below and scoops up the poor soil and returns to the waiting dump truck
After disposing of the poor soil, good quality soil and bags of lime are loaded into the skidsteer loader for a return trip back up the hill to the hotspot
The good soil and lime spread using the loader and handwork
The reclaimed hot spot is then seeded and weed sprayed for 5-years afterwards.
The job hours per hot spot is estimated at 4 hour total. |  | Item 2
Hillcrest Dump
Estimated Job Hours per Hot Spot (HR) |  | 4
Number of Hot Spots (EA) |  | 10
Total Job Hours (HR) |  | 40
Cat 300 Series Excavator Cost |  | 7521.2
Cat Skidsteer w/Track |  | 4800
Cat 725 Articulating Truck |  | 7746.4
2-Laborers w/PU |  | 6477.6
Total Cost |  | 26545.2
|  | Item 1 | Item 2 | Item 3
|  | East Dump | Hillcrest Dump | North East Dump
Establish Vegetation & Weed Control, Total Cost |  | 246090.4234 | 35078.3379 | 28299.5601
|  | Item 1 | Item 2 | Item 3
|  | East Dump | Hillcrest Dump | North East Dump
Task 1 Reclaim East Dump Complex |  | 4114679.0161 | 307941.5879 | 28299.5601
Task 2 Reclaim Pittsmont and Other Dumps
| Acres in 00030A, 00041, and 00108 | Dump Top Acres | Corrected Slope Acres
Item 1 Access Dump | 18.8664 | 7 | 12.4894
Item 2 Woodville Dump- Partially Released | 2.1781 | 0.5 | 1.6781 | Top estimated from imagery, slope correction not needed
Item 3 Great Northern Dump | All Pre-1974 | All Pre-1974 | All Pre-1974
Item 4 Nalley Valley Dump | 33.7909 | Shown as Leach Pad | 35.565
Item 5 South Continental Pit Dump | 10.7778 | - | 11.3436
Item 5 South Continental Pit Dump Crest | 14.5073 | 14.5 | -
Item 6 Pittsmont Dump | 64.138 | - | 67.5053
Item 6 Pittsmont Dump Crest | 23.3856 | 23.3856 | -
(0-20% slope) (factor of 1.0)
(20-40% slope) (factor of 1.0525)
In 2008, MR requested bond release for resloping, soil placement, and vegetation establishment of the Woodville Dump (28 acres)
Based on field inspection, the slope angle are satisfactory, approximately 2.5 to 3H:1V slope.
To achieve full bond release in the future, DEQ recommended the following:
Fix erosion gullies by fixing source problems, installing temporary BMP's, replace lost soil, seed, and weed spray (2-3x per year)
Note: Portions of this dump were later removed for the D East Pushback
The remaining Woodville Dump area (2.2 acres) will only be bonded for minor erosion repair, seeding, and weed control
Reslope Dump Slopes and Tops
Both the top and sides of the dump required extensive resloping and regrading
The existing dump slope angle are approximately 40 degrees
The reclamation of dumps will include resloping the waste rock to a 2.7H:1V slope, covering with growth media, and establishing vegetation
With respect to the dump-slope bulldozer work:
|  | Item 1 | Item 4 | Item 5 | Item 6
|  | Access | Nalley Valley | S. Cont. Pit | Pittsmont
The height of the dump (FT) |  | 80 | 175 | 60 | 100 | Estimated from topography in 2025 Site plan Map
The crest length of the dump is approximately (FT) |  | 2000 | 2000 | 1300 | 8500 | Estimated from aerial imagery
The cut, fill, and rehandle volume per foot of crest length (LCY/FT) |  | 92.48 | 442.5312 | 52.02 | 144.5
The total cut, fill, and rehandle volume is (LCY) |  | 184960 | 885062.5 | 67626 | 1228250
The cut, fill, and rehandle volume assumes every particle of waste rock is handled twice
With respect to dump-top bulldozer work:
The top of the dump is regraded to keep the water from ponding by providing drainage swales
Since the volume of regrade is unknown, DEQ assumes a two-Cat D10 dozer production rate of 1/4 acre per hour each
Slope Dozer Production Calculation |  | Item 1 | Item 4 | Item 5 | Item 6
Machine Properties |  | Access | Nalley Valley | S. Cont. Pit | Pittsmont
| Machine | D10T | D10T | D10T | D10T
| Blade | SU | SU | SU | SU
| Dual Tilt | Yes | Yes | Yes | Yes
| % Availability | 90% | 90% | 90% | 90%
| Wt (LBS) | 146950 | 146950 | 146950 | 146950
| Shoe Width (IN) | 28 | 28 | 28 | 28
| Density (LBS/LCY) | 2800 | 2800 | 2800 | 2800
| Dozeability | 1 | 1 | 1 | 1
Derating Factors
| Attitude | 5600 | 5600 | 5600 | 5600
| Visibility | 1 | 1 | 1 | 1
| Job Efficiency | 83% | 83% | 83% | 83%
| Skill Level | 75% | 75% | 75% | 75%
Input Values
| Push Distance (FT) | 100 | 100 | 100 | 100
| Push Slope | 0% | 0% | 0% | 0%
| Volume of Material (LCY) | 184960 | 885062.5 | 67626 | 1228250
Output Values
| Productivity (LCY/HR) | 1500 | 1500 | 1500 | 1500
| Adjusted Productivity (LCY/HR) | 840.375 | 840.375 | 840.375 | 840.375
| Total Hours (1 machine) | 123.3067 | 590.0417 | 45.084 | 818.8333
| Total Hours (2 machines) | 61.6533 | 295.0208 | 22.542 | 409.4167
| Total Cost (2 machines) | 61447.4112 | 294035.4637 | 22466.7097 | 408049.215
Dump-Top Dozer Production Calculation |  | Item 1 | Item 4 | Item 5 | Item 6
|  | Access | Nalley Valley | S. Cont. Pit | Pittsmont
Area of Dump Top (AC) |  | 7 | Leach pad- tab | 14.5 | 23.3856 | Access top estimated from aerial imagery
2 - Cat D10T Dozer Production (AC/HR) |  | 0.5 | 0.5 | 0.5 | 0.5
Job Hours - 2 Cat D10R (HR) |  | 14 | 0 | 29 | 46.7711
Total Cost D10R |  | 13953.24 | 0 | 28903.14 | 46614.9016
|  | Item 1 | Item 4 | Item 5 | Item 6
|  | Access | Nalley Valley | S. Cont. Pit | Pittsmont
Reslope Dump Slopes and Top, Total Cost |  | 75400.6512 | 294035.4637 | 51369.8497 | 454664.1166
Construct Surface Water Collection Ditches
Assumptions:
After the slopes are recontoured to the final configuration, a survey party will locate the surface water ditches
To construct the ditches along the slope, a D8T dozer would walk back out to the slopes, and using the blade push the muck downslope creating a berm with a "U" bottom
Based on current maps, approximately 1,000 feet of ditches would need to be constructed across the Access Dump
Based on discussion with another mining company, a D8T dozer can cut, shape, and finish blading 100 feet of ditch per hour
A survey party fee of 15% is also included
|  | Item 1 | Item 4 | Item 5 | Item 6
|  | Access | Nalley Valley | S. Cont. Pit | Pittsmont
Estimated Length of Surface Water Ditches (FT) |  | 1000 | 1000 | 650 | 7000
D8T Production Rate (FT/HR) |  | 100 | 100 | 100 | 100
Job Hours (HR) |  | 10 | 10 | 6.5 | 70
Total Construction Cost |  | 3326.1 | 3326.1 | 2161.965 | 23282.7
15% Survey Party Fee |  | 498.915 | 498.915 | 324.2948 | 3492.405
Total Cost |  | 3825.015 | 3825.015 | 2486.2598 | 26775.105
Construct Surface Water Collection Ditches, Total Cost |  | 3825.015 | 3825.015 | 2486.2598 | 26775.105
Haul & Spread Alluvium
Assumptions:
According to the application the Central Zone alluvium will be salvaged for reclamation material
The slopes of the will be covered with 20 inches of alluvium, while the top get covered with 28 inches of alluvium
The estimated volume of alluvium:
|  | Item 1 | Item 4 | Item 5 | Item 6
| Cover Thickness (IN) | Access | Nalley Valley | S. Cont. Pit | Pittsmont
Area of Dump Top (AC) | 28 | 7 | Leach Pad tab | 14.5 | 23.3856
Area of Dump Slope (AC) (Corrected for slope) | 20 | 12.4894 | 35.565 | 11.3436 | 67.5053
Volume of Alluvium Required - Dump Top (LCY) |  | 26351.1111 | - | 54584.4444 | 88033.6361
Volume of Alluvium Required - Dump Slope (LCY) |  | 33582.496 | 95630.2394 | 30501.7475 | 181514.2162
| Total Alluvium (LCY) | 59933.6072 | 95630.2394 | 85086.1919 | 269547.8523
Contingency Volume (15% extra)(LCY) |  | 68923.6482 | 109974.7753 | 97849.1207 | 309980.0301
The density of the alluvium (LBS/LCY) |  | 3300 | 3300 | 3300 | 3300
The estimated weight of alluvium (TONS) |  | 113724.0196 | 181458.3792 | 161451.0492 | 511467.0496
The estimated haul distance at 4% grade (FT) |  | 11000 | 3500 | 3500 | 2000
DEQ assumes that the Cat 6020B Hydraulic Excavator and 10-Cat 777 Haul Trucks will be used to mine, load, and haul the alluvium
Assume two Cat 10T are with the hauling operation, spreading the alluvium takes twice the hauling hours
Cat Edition 45 p.10-55 Cat 777G Haul Truck Rimpull-Speed-Gradeability Curve Loaded Speed (MPH) |  |  | 12
Cat Edition 45 p.10-55 Cat 777G Haul Truck Rimpull-Speed-Gradeability Curve Empty Speed (MPH) |  |  | 20
|  | Item 1 | Item 4 | Item 5 | Item 6
Hauler Cycle Time (MIN) |  | Access | Nalley Valley | S. Cont. Pit | Pittsmont
Load with Exchange |  | 2.45 | 2.45 | 2.45 | 2.45
Haul |  | 10.4167 | 3.3144 | 3.3144 | 1.8939
Dump and Maneuver |  | 1.6 | 1.6 | 1.6 | 1.6
Return |  | 6.25 | 1.9886 | 1.9886 | 1.1364
Potential Cycle Time |  | 20.7167 | 9.353 | 9.353 | 7.0803
Wait on Slow Hauler |  | 0 | 0 | 0 | 0
Wait to Load, Bunching AVG |  | 0 | 0 | 0 | 0
Total Cycle Time (MIN) |  | 20.7167 | 9.353 | 9.353 | 7.0803
Cycles per 60 min Hour (CYCLES/HR) |  | 2.8962 | 6.415 | 6.415 | 8.4742
Bunching Calc |  | 18.2667 | 6.903 | 6.903 | 4.6303
# of Trucks (hauler capabilities) |  | 7.4558 | 2.8176 | 2.8176 | 1.8899
Cat 777G Average Capacity (LCY) |  | 77 | 77 | 77 | 77
Hauler Potential Production Per Hour (LCY/HR) |  | 223.0088 | 493.9576 | 493.9576 | 652.5144
6020B Passes per Hauler |  | 5.1333 | 5.1333 | 5.1333 | 5.1333
Loader Cycle Time (MIN) |  | 0.7 | 0.7 | 0.7 | 0.7
Load Time Truck (MIN) |  | 3.5933 | 3.5933 | 3.5933 | 3.5933
Number of Trucks Required (EA) |  | 5.7653 | 2.6029 | 2.6029 | 1.9704
Production Rate (LCY/MIN) |  | 21.4286 | 21.4286 | 21.4286 | 21.4286
Hourly Production (LCY/HR) |  | 1285.7143 | 1285.7143 | 1285.7143 | 1285.7143
Efficiency Factor |  | 0.83 | 0.83 | 0.83 | 0.83
Availability |  | 0.9 | 0.9 | 0.9 | 0.9
Adjusted Hourly Production (LCY/HR) |  | 960.4286 | 960.4286 | 960.4286 | 960.4286
Hours Required (HR) |  | 71.7634 | 114.5059 | 101.8807 | 322.7518
Item 1 | Access
| Qty | Model | Hourly Cost Each Unit | Operating Hours | Total Cost | $ per Ton | $ per LCY
Loaders: | 1 | 6020B | 629.72 | 71.7634 | 45190.8669 | 0.39737 | 0.65567
Haulers: | 5.7653 | 777D | 468.39 | 413.7381 | 193790.8076 | 1.704 | 2.8117
Support: | 1 | 14H Motor Grader | 194.65 | 71.7634 | 13968.7516 | 0.12283 | 0.20267
| 1 | D8T | 332.61 | 71.7634 | 23869.2343 | 0.20989 | 0.34631
| 1 | 2,500 gal Water Truck | 105.45 | 71.7634 | 7567.4537 | 0.066542 | 0.10979
Fleet Totals | 9.7653 |  |  | 700.7919 | 284387.1141 | 2.5007 | 4.1261
Item 4 | Nalley Valley
| Qty | Model | Hourly Cost Each Unit | Operating Hours | Total Cost | $ per Ton | $ per LCY
Loaders: | 1 | 6020B | 629.72 | 114.5059 | 72106.6798 | 0.63405 | 1.0462
Haulers: | 2.8176 | 777D | 468.39 | 322.6277 | 151115.6077 | 1.3288 | 2.1925
Support: | 1 | 14H Motor Grader | 194.65 | 114.5059 | 22288.581 | 0.19599 | 0.32338
| 1 | D8T | 332.61 | 114.5059 | 38085.8203 | 0.3349 | 0.55258
| 1 | 2,500 gal Water Truck | 105.45 | 114.5059 | 12074.6513 | 0.10618 | 0.17519
Fleet Totals | 6.8176 |  |  | 780.6515 | 295671.3401 | 2.5999 | 4.2898
Item 5 | S. Cont. Pit
| Qty | Model | Hourly Cost Each Unit | Operating Hours | Total Cost | $ per Ton | $ per LCY
Loaders: | 1 | 6020B | 629.72 | 101.8807 | 64156.3049 | 0.56414 | 0.93083
Haulers: | 2.8176 | 777D | 468.39 | 287.0553 | 134453.8263 | 1.1823 | 1.9508
Support: | 1 | 14H Motor Grader | 194.65 | 101.8807 | 19831.0753 | 0.17438 | 0.28773
| 1 | D8T | 332.61 | 101.8807 | 33886.5346 | 0.29797 | 0.49165
| 1 | 2,500 gal Water Truck | 105.45 | 101.8807 | 10743.3182 | 0.094468 | 0.15587
Fleet Totals | 6.8176 |  |  | 694.578 | 263071.0594 | 2.3132 | 3.8168
Item 6 | Pittsmont
| Qty | Model | Hourly Cost Each Unit | Operating Hours | Total Cost | $ per Ton | $ per LCY
Loaders: | 1 | 6020B | 629.72 | 322.7518 | 203243.2503 | 1.7872 | 2.9488
Haulers: | 1.9704 | 777D | 468.39 | 635.95 | 297872.6291 | 2.6193 | 4.3218
Support: | 1 | 14H Motor Grader | 194.65 | 322.7518 | 62823.6338 | 0.55242 | 0.9115
| 1 | D8T | 332.61 | 322.7518 | 107350.4692 | 0.94396 | 1.5575
| 1 | 2,500 gal Water Truck | 105.45 | 322.7518 | 34034.1751 | 0.29927 | 0.4938
Fleet Totals | 5.9704 |  |  | 1926.9571 | 705324.1575 | 6.2021 | 10.2334
Spreading Alluvium
Assume two Cat 10T are with the hauling operation, spreading the alluvium takes twice the hauling hours
|  | Item 1 | Item 4 | Item 5 | Item 6
|  | Access | Nalley Valley | S. Cont. Pit | Pittsmont
Hauling Hours (HR) |  | 71.7634 | 114.5059 | 101.8807 | 322.7518
Job Hours (HR) |  | 143.5269 | 229.0119 | 203.7614 | 645.5036
Equipment Cost | Cat D10T | 71523.7398 | 114123.489 | 101540.4035 | 321673.7881
| Cat D10T | 71523.7398 | 114123.489 | 101540.4035 | 321673.7881
| Total | 143047.4796 | 228246.978 | 203080.8069 | 643347.5762
|  | Item 1 | Item 4 | Item 5 | Item 6
|  | Access | Nalley Valley | S. Cont. Pit | Pittsmont
Haul & Spread Alluvium, Total Cost |  | 427434.5937 | 523918.3181 | 466151.8663 | 1348671.7338
Alluvium Testing & Amendment
Assumptions:
MR submitted a plan on 8/23 & 9/20/02 to DEQ for a 2002 reclamation program of the Woodville Dump
The plan was a modification to the Reclamation Plan and given minor revision number (MR 02-001)
MR's reclamation cover soil recipe can be found in Table 9-2 of the Amendment 10 Application
DEQ assumes that this is used on the Access Dump reclamation
Based on the 2020 Annual Report, very little soil has been stockpiled, therefore DEQ will assumes the Central Zone alluvium will be salvaged for reclamation material
DEQ assumes the following Central Zone alluvium sampling and analysis schedule
|  | Item 1 | Item 4 | Item 5 | Item 6
|  | Access | Nalley Valley | S. Cont. Pit | Pittsmont
| Analyses | Volume of Alluv. (LCY) |  |  |  | Frequency (LCY) | Cost ($) | Shipping ($)
| Paste pH | 68923.6482 | 109974.7753 | 97849.1207 | 309980.0301 | 2500 | 0 | in house
| Total Metals ICP Scan | 68923.6482 | 109974.7753 | 97849.1207 | 309980.0301 | 30000 | 225 | 10
| Cu & Zn | 68923.6482 | 109974.7753 | 97849.1207 | 309980.0301 | 10000 | 45 | 10
| Organic Content | 68923.6482 | 109974.7753 | 97849.1207 | 309980.0301 | 2500 | 15 | 10
|  | 1608.2185 | 2566.0781 | 2283.1461 | 7232.8674
And 1.5% organic matter by weight or 23 tons per acre is also require
Based on recent sampling data, the Central Zone alluvium will not required a lime amendment
Assume the compost would come Western Reclamation Inc. in Butte at a cost of $20/CY
The compost is stored at a central location, assume $5/CY extra to move it to where it will be spread
|  | Item 1 | Item 4 | Item 5 | Item 6
The Estimated Compost Cost |  | Access | Nalley Valley | S. Cont. Pit | Pittsmont
Area (AC) |  | 19.4894 | 35.565 | 25.8436 | 90.8908
Density of Compost (LBS/CY) |  | 1000 | 1000 | 1000 | 1000
Cost per CY delivered to Butte ($/CY) |  | 25 | 25 | 25 | 25
Total Cost of Compost |  | 22412.7617 | 40899.7098 | 29720.1689 | 104524.4724
DEQ requests a qualified soils scientist (with a pickup truck) will be with the alluvium salvage operation full time for lab work, QA/QC and record keeping
The estimated cost for a qualified soil scientist (with a pickup), from a Consulting Firm, is $150 per hour
The number of work hours for the soil scientist is equal to the scheduled hours for the alluvium spreading operation
A portable soil testing trailer will be rented for laboratory space, sampling equipment storage, and record keeping
The estimated cost for a soil trailer rental is $200 per month
The Estimated Cost for Full Time Soils Scientist
Soil Scientist Hourly Rate ($/HR) |  | 150 | 150 | 150 | 150
Number of Hours (HR) |  | 71.7634 | 114.5059 | 101.8807 | 322.7518
Total Cost of Soils Scientist |  | 10764.5144 | 17175.8908 | 15282.1027 | 48412.7669
The Estimated Cost for a Soils Trailer
Soils Trailer Monthly Rate ($/MO) |  | 200 | 200 | 200 | 200
Number of Months (MO) |  | 0.35882 | 0.57253 | 0.5094 | 1.6138
Total Cost for Trailer |  | 71.7634 | 114.5059 | 101.8807 | 322.7518
To spread the compost, piles are built up along the dump crest and pushed down slope with a D8T dozer
DEQ assume two-Cat D8T dozers will be used to spread the compost at a production rate of 1/4 acre per hour
After spreading, the compost will be incorporated into the top 4 inches using a harrow that is drag along behind the seeder
The Estimated Cost Spreading Compost
Area (AC) |  | 19.4894 | 35.565 | 25.8436 | 90.8908
2 - Cat D8T Dozer Production (AC/HR) |  | 0.5 | 0.5 | 0.5 | 0.5
Job Hours - 2 Cat D8T (HR) |  | 38.9787 | 71.1299 | 51.6873 | 181.7817
Total Cost D8T |  | 25929.4215 | 47317.0521 | 34383.3926 | 120924.8166
|  | Item 1 | Item 4 | Item 5 | Item 6
|  | Access | Nalley Valley | S. Cont. Pit | Pittsmont
Alluvium Testing & Amendment, Total Cost |  | 60786.6796 | 108073.2368 | 81770.691 | 281417.675
Establish Vegetation & Weed Control
Assumptions:
The estimated revegetation and weed spraying cost for a 5-year period is $1,500 per acre, which includes minor erosion repair and seeding,
applying fertilizer, BMPs, etc.
The seeding is accomplished using a small dozer with a seeder attached to the front and a harrow pulled behind.
|  | Item 1 | Item 2 | Item 4 | Item 5 | Item 6
|  | Access | Woodville | Nalley Valley | S. Cont. Pit | Pittsmont
Area of Access Dump (AC) |  | 19.4894 | 2.1781 | 35.565 | 25.8436 | 90.8908
Estimated Vegetation & Weed Control Cost ($/AC) |  | 1500 | 1500 | 1500 | 1500 | 1500
Total Cost |  | 29234.0371 | 3267.1138 | 53347.4476 | 38765.4376 | 136336.2684
Establish Vegetation & Weed Control, Total Cost |  | 29234.0371 | 3267.1138 | 53347.4476 | 38765.4376 | 136336.2684
Task 2 Reclaim Pittsmont and Other Dumps, Total Cost |  | 596680.9765 | 3267.1138 | 983199.4812 | 640544.1044 | 2247864.8988
Bond Release (2008) Discussion:
In 2008, bond release was requested for resloping, soil placement, and vegetation establishment on multiple areas. Based on field inspection, the slope angles are satisfactory, approximately 2.5 to 3H:1V slope. The existing vegetation is a mixture of desirable grasses, forbs, and noxious weeds.
East and North East Dumps:
To achieve full bond release in the future, DEQ recommended the following for the East and North East Dumps:
Fix erosion gullies by fixing source problems, installing temporary BMP's, replace lost soil, seed, and weed spray (2-3x per year)
For the East and North East Dumps (Partially Reclaimed/Released) in the 2025 map, only the costs of revegetation, erosion repair, and weed control will apply
Hillcrest Dump:
No surface water collection ditches or slope break features were built on the Hillcrest slope (400-500 ft long) In addition, there exists three "hot spots" without vegetation, indicating poor soil quality.
To achieve full bond release in the future, DEQ recommended the following for the Hillcrest Dump:
Construct main surface water collection ditches to help prevent erosion, Fix all hot spots by selectively digging out the existing soil, re-apply lime and good quality soil, seed, and weed spray, Fix all erosion gullies by correcting the source problem, installing temporary BMPs, replace lost soil, seed, and weed spray (2-3x a time)
For the Hillcrest Dump (Partially Reclaimed/Released) in the 2025 map, the costs of constructing storm water channels, repairing hot spots, revegetation, erosion repair, and weed control will apply

## ITEM 10 Leach Pads
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
Item 10 Cost Summary for Earthwork - Leach Pads
Direct Cost
Reclaim Leach Pads
|  | Reslope Dump Slopes and Top |  | 17939.88
|  | Construct Surface Water Collection Ditches |  | 0
|  | Haul & Spread Alluvium |  | 226176.8268
|  | Alluvium Testing & Amendment |  | 29199.6284
|  | Establish Vegetation & Weed Control |  | 13500
| Item 10- Leach Pads Total Cost |  |  | 286816.3352
| Pre-1974 Bond |  |  | 81000
ACREAGES FROM 2025 SITE PLAN MAP
Feature | OP 00030A | OP 00041 | OP 00108 | OP 00030 | Grand Total
Leach Pad | 8.9833 |  |  | 161.6074 | 170.5908
PRE-1974 BOND |  |  |  | 81000
ACRES FOR BOND CALCULATIONS BELOW | 8.9833
Item 10 Earthwork - Leach Pads
Reslope Leach Pads
Assumptions:
ACREAGES FROM 2025 SITE PLAN MAP
|  | Total Disturbed | Pre-1974 | Post-1974
| Leach Pad Area | 171 | 162 | 9
The leach pads are not rinsed with water, they are just regraded and capped with alluvium
Both the top and sides of the leach pads require extensive resloping and regrading
Only 9 acres (top area) are not contained within OP#00030, thus 162 acres are limited to bonding at $500/acre
The underlying rock slope is bonded as the Nalley Valley dump (see Dump Areas tab)
With respect to Leach Pad - top bulldozer work:
The top of the leach pads are regraded to keep the water from ponding by providing drainage swales
Since the volume of regrade is unknown, DEQ assumes a two-Cat D10 dozer production of 1/4 acre per hour each
Leach Pad -Top Dozer Production Calculation
Area of Leach Pad Top (AC) | 9
2 - Cat D10T Dozer Production (AC/HR) | 0.5
Job Hours - 2 Cat D10T (HR) | 18
Total Cost D10T | 17939.88
Reslope Leach Pads, Total Cost | 17939.88
Construct Surface Water Collection Ditches
Collection ditches are not required for the 9 acres (tops) of leach pads in OP 00030A
Construct Surface Water Collection Ditches, Total Cost |  | 0
Haul & Spread Alluvium
Assumptions:
According to the application the Central Zone alluvium will be salvaged for reclamation material
The slopes of the Leach Pad will be covered with 20 inches of alluvium, while the top get covered with 28 inches of alluvium
The estimated volume of alluvium to cover the Leach Pad is:
Area | Acres | Cover Soil (IN) | Volume of Soil Required (LCY)
Leach Pad Slopes | 0 | 20 | 0
Leach Pad Tops | 9 | 28 | 33880
Total | 9 |  | 33880
The estimated volume of alluvium to cover top of Leach Pad (LCY) |  | 33880
Contingency Volume (15% extra)(LCY) |  | 38962
The density of the alluvium (LBS/LCY) |  | 3300
The estimated weight of alluvium (TONS) |  | 64287.3
The estimated haul distance at 4% grade (FT) |  | 9500
Haul 9,500 feet One Way, Total Resistance 4%
Cat Edition 45 p.10-55 Cat 777G Haul Truck Rimpull-Speed-Gradeability Curve Loaded Speed (MPH) |  |  | 12
Cat Edition 45 p.10-55 Cat 777G Haul Truck Rimpull-Speed-Gradeability Curve Empty Speed (MPH) |  |  | 20
Hauler Cycle Time (MIN)
Load with Exchange | 2.45
Haul | 8.9962
Dump and Maneuver | 1.6
Return | 5.3977
Potential Cycle Time | 18.4439
Wait on Slow Hauler | 0
Wait to Load, Bunching AVG | 0 | Bunching Calc | # of Trucks (hauler capabilities)
Total Cycle Time (MIN) | 18.4439 | 15.9939 | 6.5281
Cycles per 60 min Hour (CYCLES/HR) | 3.2531
Cat 777G Average Capacity (LCY) | 77
Hauler Potential Production Per Hour (LCY/HR) | 250.4888
6020B Passes per Hauler | 5 | 5.1333
Loader Cycle Time (MIN) | 0.7
Load Time Truck (MIN) | 3.5
Number of Trucks Required (EA) | 5.2697 | # of Trucks (loader capabilities)
Production Rate (LCY/MIN) | 22
Hourly Production (LCY/HR) | 1320
Efficiency Factor | 0.83
Availability | 0.9
Adjusted Hourly Production (LCY/HR) | 986.04
Hours Required (HR) | 39.5136
| Qty | Model | Hourly Cost Each Unit | Operating Hours | Total Cost | $ per Ton | $ per LCY
Loaders: | 1 | 6020B | 629.72 | 39.5136 | 24882.5105 | 0.38705 | 0.63864
Haulers: | 5.2697 | 777D | 468.39 | 208.2248 | 97530.3911 | 1.5171 | 2.5032
Support: | 1 | 14H Motor Grader | 194.65 | 39.5136 | 7691.3242 | 0.11964 | 0.19741
| 1 | D8T | 332.61 | 39.5136 | 13142.6218 | 0.20444 | 0.33732
| 1 | 2,500 gal Water Truck | 105.45 | 39.5136 | 4166.7102 | 0.064814 | 0.10694
Fleet Totals | 9.2697 |  |  | 366.2792 | 147413.5577 | 2.293 | 3.7835
Spreading Alluvium
Hauling Hours (HR) |  | 39.5136
Job Hours (HR) |  | 79.0272
Equipment Cost | Cat D10T | 39381.6345
| Cat D10T | 39381.6345
| Total | 78763.2691
Haul & Spread Alluvium, Total Cost |  | 226176.8268
Alluvium Testing & Amendment
Assumptions:
MR submitted a plan on 8/23 & 9/20/02 to DEQ for a 2002 reclamation program of the Woodville Dump
The plan was a modification to the Reclamation Plan and given minor revision number (MR 02-001)
MR's reclamation cover soil recipe can be found in Table 9-2 of the Amendment 10 Application
DEQ assumes that recipe is used for the Leach Pad reclamation
Based on the 2020 Annual Report, very little soil has been stockpiled, therefore DEQ will assumes the Central Zone alluvium will be salvaged for reclamation material
DEQ assumes the following Central Zone alluvium sampling and analysis schedule
| Analyses | Volume of Soil (LCY) | Frequency (LCY) | Cost ($) | Shipping ($) | Total Cost ($)
| Paste pH | 38962 | 2500 | 0 | in house | 0
| Total Metals ICP Scan | 38962 | 30000 | 225 | 10 | 305.2023
| Cu & Zn | 38962 | 10000 | 45 | 10 | 214.291
| Organic Content | 38962 | 2500 | 15 | 10 | 389.62
[5 empty] | Total | 909.1133
And 1.5% organic matter by weight or 23 tons per acre is also require
Based on recent sampling data, the Central Zone alluvium will not required a lime amendment
Assume the compost would come Western Reclamation Inc. in Butte at a cost of $20/CY
The compost is stored at a central location, assume $5/CY extra to move it to where it will be spread
The Estimated Compost Cost
Area (AC) | 9
Density of Compost (LBS/CY) | 1000
Cost per CY delivered to Butte ($/CY) | 25
Total Cost of Compost | 10350
DEQ requests a qualified soils scientist (with a pickup truck) will be with the alluvium salvage operation full time for lab work, QA/QC and record keeping
The estimated cost for a qualified soil scientist (with a pickup), from a Consulting Firm, is $150 per hour
The number of work hours for the soil scientist is equal to the scheduled hours for the alluvium spreading operation
A portable soil testing trailer will be rented for laboratory space, sampling equipment storage, and record keeping
The estimated cost for a soil trailer rental is $200 per month
The Estimated Cost for Full Time Soils Scientist
Soil Scientist Hourly Rate ($/HR) | 150
Number of Hours (HR) | 39.5136
Total Cost of Soils Scientist | 5927.0415
The Estimated Cost for a Soils Trailer
Soils Trailer Monthly Rate ($/MO) | 200
Number of Months (MO) | 0.19757
Total Cost for Trailer | 39.5136
To spread the compost, piles are built up along the dump crest and pushed down slope with a D8T dozer
DEQ assume two-Cat D8T dozers will be used to spread the compost at a production rate of 1/4 acre per hour
After spreading, the compost will be incorporated into the top 4 inches using a harrow that is drag along behind the seeder
The Estimated Cost Spreading Compost
Area of Leach Pads (AC) | 9
2 - Cat D8T Dozer Production (AC/HR) | 0.5
Job Hours - 2 Cat D8T (HR) | 18
Total Cost D8T | 11973.96
Alluvium Testing & Amendment, Total Cost |  | 29199.6284
Establish Vegetation & Weed Control
Assumptions:
The estimated revegetation and weed spraying cost for a 5-year period is $1,500 per acre, which includes minor erosion repair and seeding,
applying fertilizer, BMPs, etc.
The seeding is accomplished using a small dozer with a seeder attached to the front and a harrow pulled behind.
Area of Leach Pads (AC) | 9
Estimated Vegetation & Weed Control Cost ($/AC) | 1500
Total Cost | 13500
Establish Vegetation & Weed Control, Total Cost |  | 13500
Item 11 Earthwork - Leach Pads, Total Cost |  | 286816.3352

## ITEM 11 Pit
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
Item 11 Cost Summary for Earthwork - Continental Pit
Direct Cost
Task 1 Reclaim Continental Pit
|  | Reslope Pit Benches |  | 340575.606
|  | Haul & Spread Alluvium |  | 4069016.9715
|  | Alluvium Testing & Amendment |  | 554441.8844
|  | Establish Vegetation & Weed Control |  | 256287.7054
5220322.1673
| Task 2 Reclaim South Continental Pit Dump |  |  | See Dump Area tab
|  | Item 11 Earthwork - Continental Pit Total Cost |  | 5220322.1673
|  | Pre-1974 Bond |  | 29500
ACREAGES FROM 2025 SITE PLAN MAP
Feature | OP 00030A | OP 00041 | OP 00108 | OP 00030 | Grand Total
Continental Pit - Reclaimable Bench Area | 30.2972 | 112.8353 | 27.726 | 22.2613 | 193.1198
Continental Pit - Highwall (unreclaimed) | 65.6282 | 233.112 | 47.9682 | 37.3341 | 384.0425
Continental Pit Water 5410'/5466' (BMFOU) | 103.7573 | 194.9103 | 1.8885 | 3.4125 | 303.9686
PRE-1974 BOND |  |  |  | 29500
ACRES FOR CALCULATIONS BELOW | 170.8585 |  |  | BMFOU not included
Task 1 Reclaim Continental Pit
Reslope Pit Benches
Assumptions:
All of the slopes within the Continental Pit are reclaimed as talus slopes and highwall features
According to the 1998 bond calculation, small areas above the 5,410 elevation will get revegetated
Areas below the 5,410 ft elevation are subject to pit-lake flooding, and would be managed under BMFOU (Superfund)
The D East Pushback is located between the main Continental Pit and Interstate highway I-15
The 2025 site plan map shows the flat/bench areas that can be reclaimed
These areas get regraded, ripped, and covered with 28 inches of alluvium, seeded, and weed sprayed.
Since the volume of regrading and area to be ripped is unclear, DEQ assumes two-Cat D10R dozers will be used at a production rate of 1/2 acre per hour
The Estimated Cost Regrading & Ripping
Area of Pit Reclamation (AC) | 170.8585
2 - Cat D10T Dozer Production (AC/HR) | 0.5
Job Hours - 2 Cat D10T (HR) | 341.7169
Total Cost D10T | 340575.606
Reslope Pit Benches | 340575.606
Haul & Spread Alluvium
Assumptions:
Based on the 2020 Annual Report, very little soil has been stockpiled, therefore DEQ will assumes the Central Zone alluvium will be salvaged for reclamation material
The estimated volume of alluvium to cover the reclaimable area is:
Site | Acres | Cover Soil (IN) | Volume of Soil Required (LCY)
Pit Area | 171 | 28 | 643720
Contingency Volume (15% extra)(LCY) |  | 740278
Density of the alluvium (LBS/LCY) |  | 3300
Weight of alluvium required to cover the Pit Area Reclamation (TONS) |  | 1221458.7
Estimated haul distance at 10% grade (FT) |  | 8000
Haul distance is 8,000 feet One Way, Total Resistance 4%
Cat Edition 45 p.10-55 Cat 777G Haul Truck Rimpull-Speed-Gradeability Curve Loaded Speed (MPH) |  |  | 12
Cat Edition 45 p.10-55 Cat 777G Haul Truck Rimpull-Speed-Gradeability Curve Empty Speed (MPH) |  |  | 20
Hauler Cycle Time (MIN)
Load with Exchange | 2.45
Haul | 7.5758
Dump and Maneuver | 1.6
Return | 4.5455
Potential Cycle Time | 16.1712
Wait on Slow Hauler | 0
Wait to Load, Bunching AVG | 0 | Bunching Calc | # of Trucks (hauler capabilities)
Total Cycle Time (MIN) | 16.1712 | 13.7212 | 5.6005
Cycles per 60 min Hour (CYCLES/HR) | 3.7103
Cat 777G Average Capacity (LCY) | 77
Hauler Potential Production Per Hour (LCY/HR) | 285.6929
6020B Passes per Hauler | 5 | 5.1333
Loader Cycle Time (MIN) | 0.7
Load Time Truck (MIN) | 3.5
Number of Trucks Required (EA) | 4.6203 | # of Trucks (loader capabilities)
Production Rate (LCY/MIN) | 22
Hourly Production (LCY/HR) | 1320
Efficiency Factor | 0.83
Availability | 0.9
Adjusted Hourly Production (LCY/HR) | 986.04
Hours Required (HR) | 750.7586
| Qty | Model | Hourly Cost Each Unit | Operating Hours | Total Cost | $ per Ton | $ per LCY
Loaders: | 1 | 6020B | 629.72 | 750.7586 | 472767.6992 | 0.38705 | 0.63864
Haulers: | 4.6203 | 777D | 468.39 | 3468.7647 | 1624734.6924 | 1.3302 | 2.1948
Support: | 1 | 14H Motor Grader | 194.65 | 750.7586 | 146135.1595 | 0.11964 | 0.19741
| 1 | D8T | 332.61 | 750.7586 | 249709.8146 | 0.20444 | 0.33732
| 1 | 2,500 gal Water Truck | 105.45 | 750.7586 | 79167.4933 | 0.064814 | 0.10694
Fleet Totals | 8.6203 |  |  | 6471.799 | 2572514.8591 | 2.1061 | 3.4751
Spreading Alluvium
Hauling Hours (HR) |  | 750.7586
Job Hours (HR) |  | 1501.5172
Equipment Cost | Cat D10T | 748251.0562
| Cat D10T | 748251.0562
| Total | 1496502.1124
Haul & Spread Alluvium | 4069016.9715
Alluvium Testing & Amendment
Assumptions:
MR submitted a plan on 8/23 & 9/20/02 to DEQ for a 2002 reclamation program of the Woodville Dump
The plan was a modification to the Reclamation Plan and given minor revision number (MR 02-001)
MR's reclamation cover soil recipe can be found in Table 9-2 of the Amendment 10 Application
DEQ assumes that this is used for the Continental Pit reclamation
Based on the 2020 Annual Report, very little soil has been stockpiled, therefore DEQ will assumes the Central Zone alluvium will be salvaged for reclamation material
DEQ assumes the following Central Zone alluvium sampling and analysis schedule
| Analyses | Volume of Soil (LCY) | Frequency (LCY) | Cost ($) | Shipping ($) | Total Cost ($)
| Paste pH | 740278 | 2500 | 0 | in house | 0
| Total Metals ICP Scan | 740278 | 30000 | 225 | 10 | 5798.8443
| Cu & Zn | 740278 | 10000 | 45 | 10 | 4071.529
| Organic Content | 740278 | 2500 | 15 | 10 | 7402.78
[5 empty] | Total | 17273.1533
And 1.5% organic matter by weight or 23 tons per acre is also require
Based on recent sampling data, the Central Zone alluvium will not required a lime amendment
Assume the compost would come Western Reclamation Inc. in Butte at a cost of $20/CY
The compost is stored at a central location, assume $5/CY extra to move it to where it will be spread
The Estimated Compost Cost
Area (AC) | 170.8585
Density of Compost (LBS/CY) | 1000
Cost per CY delivered to Butte ($/CY) | 25
Total Cost of Compost | 196487.2408
DEQ requests a qualified soils scientist (with a pickup truck) will be with the alluvium salvage operation full time for lab work, QA/QC and record keeping
The estimated cost for a qualified soil scientist (with a pickup), from a Consulting Firm, is $150 per hour
The number of work hours for the soil scientist is equal to the scheduled hours for the alluvium spreading operation
A portable soil testing trailer will be rented for laboratory space, sampling equipment storage, and record keeping
The estimated cost for a soil trailer rental is $200 per month
The Estimated Cost for Full Time Soils Scientist
Soil Scientist Hourly Rate ($/HR) | 150
Number of Hours (HR) | 750.7586
Total Cost of Soils Scientist | 112613.7885
The Estimated Cost for a Soils Trailer
Soils Trailer Monthly Rate ($/MO) | 200
Number of Months (MO) | 3.7538
Total Cost for Trailer | 750.7586
To spread the compost, piles are built up along the dump crest and pushed down slope with a D8T dozer
DEQ assume two-Cat D8T dozers will be used to spread the compost at a production rate of 1/4 acre per hour
After spreading, the compost will be incorporated into the top 4 inches using a harrow that is drag along behind the seeder
The Estimated Cost Spreading Compost
Area of Pit reclamation (AC) | 170.8585
2 - Cat D8T Dozer Production (AC/HR) | 0.5
Job Hours - 2 Cat D8T (HR) | 341.7169
Total Cost D8T | 227316.9432
Alluvium Testing & Amendment, Total Cost |  | 554441.8844
Establish Vegetation & Weed Control
Assumptions:
The estimated revegetation and weed spraying cost for a 5-year period is $1,500 per acre, which includes minor erosion repair and seeding,
applying fertilizer, BMPs, etc.
The seeding is accomplished using a small dozer with a seeder attached to the front and a harrow pulled behind.
Area of Pit Reclamation (AC) | 170.8585
Estimated Vegetation & Weed Control Cost ($/AC) | 1500
Total Cost | 256287.7054
Establish Vegetation & Weed Control, Total Cost |  | 256287.7054
Task 1 Reclaim Continental Pit, Total Cost |  | 5220322.1673

## ITEM 12 Pre-Law Areas
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
ACREAGES FROM 2025 SITE PLAN MAP
| Feature | OP 00030A | OP 00041 | OP 00108 | OP 00030 | Grand Total
| Road | 61.237 | 1.8261 | 0.98616 | 65.5324 | 129.5817
| Precipitation Plant RR | 0.87204 | 0.11921 |  | 1.0538 | 2.0451 | See Misc. tab
| Berkeley Pit (BMFOU) |  |  |  | 237.6357 | 237.6357
| Berkeley Pit Water (BMFOU) |  |  |  | 446.348 | 446.348
| Concentrator Area (EXEMPT) |  |  |  | 75.7872 | 75.7872
| Concentrator Area Partially Reclaimed (EXEMPT) |  |  |  | 19.3481 | 19.3481
| HB Water Treatment Plant (BMFOU) | 1.9567 |  |  | 6.9449 | 8.9016
| Historic Preservation (GMMIA) |  |  |  | 16.9238 | 16.9238
| Precipitation Plant Area (EXEMPT) |  |  |  | 73.1102 | 73.1102
| Primary Crusher (EXEMPT) |  |  |  | 30.4857 | 30.4857
| Primary Crusher Partially Reclaimed (EXEMPT) |  |  |  | 13.7476 | 13.7476
Item 12 Pre-Law Areas
Assumptions:
Exempt Facilites: |  |  |  | Area (ac)
| Concentrator |  |  | 95.1352
| Primary Crusher |  |  | 44.2333
| Precipitation Plant |  |  | 73.1102
|  |  | Total | 212.4787
Other facilities in OP#00030:
Area (ac)
| Berkeley Pit (238 acres above 5410' water level, 446 acres below water) |  |  | 684
| Powder Magazine and Explosive Storage Area |  |  | Not reported, small feature
| Railroad to Precipitation Plant |  |  | 2
| Water Management Structures |  |  | Not reported, small feature
| Roads associated with exempt facilities (in OP#00030) |  |  | 65.5324 | (See Misc tab)
| Fuel Bays |  |  | Not reported, small feature
| Tailings and Return Water Pipeline |  |  | Not reported, small feature
| Tailings Booster Stations (McQueens, No. 2 & No. 3) |  |  | Not reported, small feature
| Horseshoe Bend Capture System- Booster Station + Roads (GMMIA) |  |  | 17
| Horseshoe Bend Water Treatment Plant Area |  |  | 9
|  |  | Permit Area | Applicable Bond |  | Notes
| Concentrator, Crusher, Precipitation Plant (Exempt Areas) |  | Exempt | 0 |  | Exempt from permit and bonding
| Berkeley Pit |  | Exempt | 0 |  | Managed/reclaimed under Superfund
| Powder Magazine and Explosive Storage Area |  | 00030 | 0 | $500/acre in Misc tab | Underlying misc. area OP#00030, bonded at $500/acre
| Railroad to Precipitation Plant |  | 00030+30A+41 | 1000 | $500/acre in Misc tab | Underlying area OP#00030 for continuous feature, bonded at $500/acre
| Water Management Structure |  | 00030 | 0 |  | Managed/used/reclaimed under Superfund
| Road Associated with Pre-law Facilities |  | 00030 | 32750 | $500/acre in Misc tab | Underlying misc. area OP#00030, bonded at $500/acre
| Fuel Bays |  | 00030 | 0 |  | Underlying misc. area OP#00030, bonded at $500/acre
| Horseshoe Bend Capture System- Booster Station + Roads |  | 00030 | 0 |  | Historic mining area (GMMIA), reclaimed under Superfund
| Horseshoe Bend Water Treatment Plant Area |  | 00030+30A | 0 |  | Managed/used/reclaimed under Superfund
| Tailings and Return Water Pipeline |  | 00030+30A | 0 |  | Managed/used/reclaimed under Superfund
| Tailings Booster Stations (McQueens, No. 2 & No. 3) |  | 00030 | 0 |  | Managed/used/reclaimed under Superfund
0
The classification of some areas as being “grandfathered,” "pre-1971,"pre-law," or “pre-1974” acres may have been confused through previous DEQ and MR correspondence and bond calculations. The following information is based on a current review of historic documents and on-going discussions with MR; conclusions are subject to change during the bond review.
Areas of mining disturbance existed prior to the date the MMRA took effect (3/9/1971). Additional amendments affecting bonding practices took effect on 7/1/1974. An opinion from the Attorney General in 1977 established that “The concentrator and precipitation plant operated by the Anaconda Company in Butte, Montana, are exempted from regulation under the Hard Rock Act by section 50-1219, R.C.M. 1947, since these facilities were constructed prior to enactment.” These facilities have been referred to by many terms (see above), though it may be helpful to refer to them as "exempt" areas. Site maps often show these as shaded areas within the Permit 00030 boundary, though they are exempt from the permit. Reclamation bond is not held for these areas ($0/acre).
The permit exemption seems to have applied only to processing facilities, although this is not expicit in the MMRA or Attorney General's Opinion. Other areas of pre-1971 disturbance (e.g. tailings impoundment, leach pads, dumps, roads, Berkeley Pit) were incorporated into Permit 00030, included in the Operating and Reclamation Plan, and bonded accordingly. The bonding level for the Permit 00030 area has been limited to $500/acre, based on bonding levels applied between 1971 and 1974. Other permit areas (post-1974; Permits 00030A, 00041, and 00108) are bonded at the estimated current cost of completing reclamation.
The Annual Report from June 2020 (Table 6.1) lists the pre-law areas as 210 acres, which includes the Concentrator, Precipitation Plant, and Primary Crusher (42 acres).The acreage was updated to 44 acres with new mapping in Sept 2020. (see 10/2/2020 Response)
After discussion with MR and review of historic photos, DEQ has determined that the Primary Crusher should be considered as a pre-1971 processing facility. This means the 44-acre area is also exempt from the permit, even though this facility was not mentioned specifically in the Attorney General's Opinion and it was mistakenly ommitted from the list of exempt facilities in historic permit documents.
The consolidated Operating Plan (2019) and 2015 5-year bond determination also listed other facilities as being pre-law, but that terminology may not be correct. These facilities occur within Permit 00030 acres. This means that these features apply to the total acreage and disturbance area of Permit 00030 and they do not need to be depicted as isolated exclusion areas within the permit. This also means that the pre-1974 bond limit of $500/acre is applied to these areas, unless other considerations are needed (see below).
The full costs for removal and reclamation of these facilities or structures may not be applied to the total obligated bond because they are located within Permit 00030, thus the bond limit of $500/acre has already been applied for that location. This might give the impression that the facilities themselves are exempt from bonding, but it should not be interpreted that the facilities are exempt from the permit ("pre-law").
Another distinction can be made for some features within Permit 00030 that may not be bonded because the long-term operation, reclamation, and/or removal of facilities will be managed under Superfund activities (within Butte Mine Flooding Operable Unit). These would include the Berkeley Pit and other features associated with water management and water treatment. This might give the impression that the facilities themselves are exempt from bonding, but it should not be interpreted that the facilities are exempt from the permit ("pre-law").
In 2004, 109 acres of OP#00030 were removed from the permit area and transferred to the Butte Priority Soils Operable Unit (BPSOU) and the Granite Mountain Memorial Interpretive Area (GMMIA). Revision MR20-001 (approved 8/26/2020) incorporated 17 acres (out of the 109-acre area) back into OP#00030. This area includes the Horseshoe Bend Capture System booster pump station and associated infrastructure (pipeline, access roads, powerline). This pump station was planned, approved, and constructed as part of the Berkeley Pit and Discharge Pilot Project. As part of the remedial activities within the Butte Mine Flooding Operable Unit (BMFOU), this facility will continue to be operated and will be decommissioned, if ever, under Superfund (EPA) jurisdiction.
The “new” 17 acres are subject to the current law regarding the performance bond and not the pre-1974 level. “All bonds required in accordance with the provisions of this section must be based upon reasonably foreseeable activities that the applicant may conduct in order to comply with conditions of an operating permit” 82-4-338(6), Montana Code Annotated (MCA). Any associated bond amount would reflect the reclamation standards to be achieved, which must take into account the comparable utility and stability of adjacent areas and previously approved post-mining land use (82-4-336(9), MCA).
However, under the conditions of the GMMIA to preserve the historic mining landscape, regrading, soil placement, or revegetation would not occur in the 17 acres. It is appropriate for the reclamation of this area to match the post-mining land use of adjacent areas for historic preservation. As noted above, any potential decommissioning of the booster pump station and associated infrastructure would be conducted under EPA’s jurisdiction within the BMFOU. The 2020 BPSOU boundary includes this area, but excludes the "Sludge Repository" and "Walkerville Landfill" areas identified within the GMMIA. boundary

## ITEM 13 Miscellaneous
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
Item 13 Cost Summary for Miscellaneous Areas
Direct Cost
Task 1- Roads | Reslope Area |  | 4090.2716
| Construct Surface Water Collection Ditches Along Roads |  | 181764.7128
| Construct Rip Rap Channel Protection |  | 1639440
| Haul & Spread Alluvium |  | 706641.2145
| Alluvium Testing & Amendment |  | 120769.1481
| Establish Vegetation & Weed Control |  | 57501.4746
2710206.8215
Task 2- Alluvium AND Soil Stockpiles | Rip Area |  | 2305.0809
| Establish Vegetation & Weed Control |  | 65570.7695
67875.8504
Task 3- McQueen Townsite | Establish Vegetation & Weed Control |  | 33961.4347
Task 4- Misc | Reslope Area |  | 201387.7592
| Haul & Spread Alluvium |  | 4345543.1953
| Alluvium Testing & Amendment |  | 659144.8963
| Establish Vegetation & Weed Control |  | 303093.9726
5509169.8233
Task 5- Misc Partially Reclaimed | Establish Vegetation & Weed Control |  | 21738.8418
| Item 13 Miscellaneous Areas Total Cost |  | 8342952.7718
| Pre-1974 Bond |  | 185500
ACREAGES FROM 2025 SITE PLAN MAP
Feature | OP 00030A | OP 00041 | OP 00108 | OP 00030 | Grand Total
Road | 61.237 | 1.8261 | 0.98616 | 65.5324 | 129.5817
RDS Pittsmont Road | 10.6583 |  |  | 1.6461 | 12.3044
Alluvium Stockpile |  | 10.4504 | 8.6964 |  | 19.1467
Soil Stockpile | 24.5671 |  |  | 1.6458 | 26.2129
McQueen Townsite | 22.641 |  |  | 10.0971 | 32.7381
Misc | 154.6127 | 18.4419 | 23.8396 | 262.551 | 459.4451
Misc Partially Reclaimed/Released |  | 10.7816 | 3.7109 | 22.4164 | 36.9089 | UNDISTURBED- NO BOND
Undisturbed (No Bond Required) | 343.4335 | 33.6947 | 162.5227 |  | 539.6509
Misc Berkeley Pit Overlook |  |  |  | 2.9349 | 2.9349
Office |  |  |  | 1.8159 | 1.8159
Precipitation Plant RR** | 0.87204 | 0.11921 |  | 1.0538 | 2.0451
**During review of historic features, DEQ and MR agreed that the Precip Plant Rail Road is pre-1971 infrastructure, however the permit exemption is limited to processing facilities
Slightly more than half of this narrow, continuous feature is contained within Permit 00030. Shorter segments are contained within 00030A and #00041.
For continuity, DEQ and MR agreed to apply the pre-1974 bond level to the full length of the feature (2 acres @ $500/acre)
|  | Pre-1974 Bond Areas |  | 370.6846
185500
Item 13 Miscellaneous Areas - ONLY Permits 00030A, 00041, AND 00108
Assumptions:
The Miscellaneous areas are shown on the 2025 Site Plan Map and Acreage Table
The Central Zone is included in this area along with the Lunch Room Stockpile
Pre-law Facilities are not included in this task, see Pre-Law Areas tab
The permit boundaries do not affect the cost estimates, so the acreages are being grouped in the following manner in the calculations:
Acres in 00030, 00041, and 00108
Task 1- Roads | 74.7076
Task 2- Alluvium AND Soil Stockpiles | 43.7138
Task 3- McQueen Townsite | 22.641
Task 4- Misc | 196.8942
Task 5- Misc Partially Reclaimed | 14.4926
Task 1- Roads
Reclamation Components:
Reslope/Rip
Cap with 24 inches of alluvium
Revegetate
Road area in 2025 (AC) | 74.7076
Road area to be reclaimed (AC) | 37.3538
Road Reclaimed (0-20% slope) (factor of 1.0) | 18.6769
Road Reclaimed (20-40% slope) (factor of 1.0525) | 19.6574
Total Corrected Road Area | 38.3343
Task 2- Alluvium and Soil Stockpiles
Reclamation Components:
Rip
Revegetate
Stockpile area to be reclaimed (AC) | 43.7138
Task 3- McQueen Townsite
Reclamation Components:
Revegetate
McQueen Townsite to be reclaimed (AC) | 22.641
Task 4- Misc.
Reclamation Components:
Reslope/Rip
Cap with 28 inches of alluvium
Revegetate
Misc. areas to be reclaimed (AC) | 196.8942
Misc. area (0-20% slope) (factor of 1.0) | 98.4471
Misc. area (20-40% slope) (factor of 1.0525) | 103.6156
Total Corrected Misc. Area | 202.0626
Task 5- Misc Partially Reclaimed
Reclamation Components:
Revegetate
Misc Partially Reclaimed areas (AC) | 14.4926
Reslope/Rip Areas
Assumptions:
The volume of resloping is unknown, therefore two-Cat D10T dozers will be used at a production rate of 1/4 acre per hour
The Estimated Cost Regrading/Ripping
| Task 1 | Task 2 | Task 4
| Roads | Stockpiles | Misc
Area of Misc Reclamation (AC) | 38.3343 | 43.7138 | 202.0626
2 - Cat D10R Dozer Production (AC/HR) | 0.5 | 0.5 | 0.5
Job Hours - 2 Cat D10T (HR) | 76.6686 | 87.4277 | 404.1253
Total Cost D10T | 4090.2716 | 2305.0809 | 201387.7592
Reslope/Rip Areas, Total Cost | 4090.2716 | 2305.0809 | 201387.7592
Construct Surface Water Collection Ditches
Assumptions:
After the slopes are recontoured to the final configuration, a survey party will locate the surface water ditches
To construct the ditches along the slope, a D8T dozer would walk back out to the slopes, and using the blade push the muck downslope creating a berm with a "U" bottom
The exact amount (length) of ditches is unknown
For the purpose of this calculation, assume 9 miles of ditches (along the roads) would need to be constructed
Based on discussion with another mining company, a D8T dozer can cut, shape, and finish blading 100 feet of ditch per hour
A survey party fee of 15% is also included
Task 1
Roads
Length of Surface Water Ditches (FT) | 47520
D8T Production Rate (FT/HR) | 100
Job Hours (HR) | 475.2
Total Construction Cost | 158056.272
15% Survey Party Fee | 23708.4408
Total Cost | 181764.7128
Construct Water Collection Ditches, Total Cost | 181764.7128
Construct Rip Rap Channel Protection
Assumptions:
In the absence of a design for surface water channel protection, DEQ assumes the following:
The channel protection is placed along collector ditches located mainly along the roads
Approximately 1/2 of the 9 miles of roads (listed above) will require riprap lined channel protection
The ditches are trapazoid shape and average 10 feet wide at the top
The lower portions where the gradent is steeper and more water is collected plunge pools will be constructed
To place the riprap a 20T articulating truck and hydraulic excavator will be used
The rip rap comes from locally derived on-site source
A portable screening and crushing plant will be necessary to manufacture both the bedding material and riprap
Large size rip rap can be taken from onsite stockpiles
The equipment necessary to accomplish this task includes:
Cat 950 Loader
Cat 740 Articulating Truck
Cat 720 Articulating Truck
Cat 330 Excavator
DEQ would have to hire a 3rd party engineering firm to design the drainage system
Based on the 2020 Black Butte Copper Mine bond estimate, the estimated cost for a completed rip rap lined ditches is $60 per foot
Engineering fee of 15% is also included
Task 1
Roads
Estimated Length of Surface Water Collection Ditches (LF) |  | 47520
Estimated Length Requiring Rip Rap Lining (FT) |  | 23760
Average Construction Cost per Foot ($/FT) |  | 60
Total Construction Cost |  | 1425600
15% Engineering Fee |  | 213840
Total Cost |  | 1639440
Construct Rip Rap Channel Protection, Total Cost |  | 1639440
Haul & Spread Alluvium
Assumptions:
According to the Reclamation Plan, the Central Zone alluvium will be used for reclamation material
Estimated volumes of alluvium to cover the Misc. Areas:
| Task 1 | Task 4
| Roads | Misc
Areas to receive alluvium cover (AC) | 38.3343 | 202.0626
Thickness of alluvium cover (IN) | 24 | 28
Estimated volume of alluvium (LCY) | 123692.0609 | 760653.6142
Contingency Volume (15% extra)(LCY) | 142245.8701 | 874751.6563
The density of the alluvium (LBS/LCY) | 3300 | 3300
The estimated weight of alluvium (TONS) | 234705.6856 | 1443340.2329
The estimated haul distance at 4% grade (FT) | 5000 | 5000
Haul 5000 feet One Way, Total Resistance 4%
Cat Edition 45 p.10-55 Cat 777G Haul Truck Rimpull-Speed-Gradeability Curve Loaded Speed (MPH) |  |  | 12
Cat Edition 45 p.10-55 Cat 777G Haul Truck Rimpull-Speed-Gradeability Curve Empty Speed (MPH) |  |  | 20
| Task 1 | Task 4
Hauler Cycle Time (MIN) | Roads | Misc
Load with Exchange | 2.45 | 2.45
Haul | 4.7348 | 4.7348
Dump and Maneuver | 1.6 | 1.6
Return | 2.8409 | 2.8409
Potential Cycle Time | 11.6258 | 11.6258
Wait on Slow Hauler | 0 | 0
Wait to Load, Bunching AVG | 0 | 0
Total Cycle Time (MIN) | 11.6258 | 11.6258
Cycles per 60 min Hour (CYCLES/HR) | 5.161 | 5.161
Bunching Calc | 9.1758 | 9.1758
# of Trucks (hauler capabilities) | 3.7452 | 3.7452
Cat 777G Average Capacity (LCY) | 77 | 77
Hauler Potential Production Per Hour (LCY/HR) | 397.3935 | 397.3935
6020B Passes per Hauler | 5.1333 | 5.1333
Loader Cycle Time (MIN) | 0.7 | 0.7
Load Time Truck (MIN) | 3.5933 | 3.5933
Number of Trucks Required (EA) | 3.2354 | 3.2354
Production Rate (LCY/MIN) | 21.4286 | 21.4286
Hourly Production (LCY/HR) | 1285.7143 | 1285.7143
Efficiency Factor | 0.83 | 0.83
Availability | 0.9 | 0.9
Adjusted Hourly Production (LCY/HR) | 960.4286 | 960.4286
Hours Required (HR) | 148.1067 | 910.793
Task 1 | Roads
| Qty | Model | Hourly Cost Each Unit | Operating Hours | Total Cost | $ per Ton | $ per LCY
Loaders: | 1 | 6020B | 629.72 | 148.1067 | 93265.7274 | 0.39737 | 0.65567
Haulers: | 3.2354 | 777D | 468.39 | 479.1796 | 224442.9487 | 0.95627 | 1.5779
Support: | 1 | 14H Motor Grader | 194.65 | 148.1067 | 28828.9618 | 0.12283 | 0.20267
| 1 | D8T | 332.61 | 148.1067 | 49261.7569 | 0.20989 | 0.34631
| 1 | 2,500 gal Water Truck | 105.45 | 148.1067 | 15617.8475 | 0.066542 | 0.10979
Fleet Totals | 7.2354 |  |  | 1071.6063 | 411417.2424 | 1.7529 | 2.8923
Task 4 | Misc.
| Qty | Model | Hourly Cost Each Unit | Operating Hours | Total Cost | $ per Ton | $ per LCY
Loaders: | 1 | 6020B | 629.72 | 910.793 | 573544.5919 | 2.4437 | 4.0321
Haulers: | 3.2354 | 777D | 468.39 | 2946.7511 | 1380228.7619 | 5.8807 | 9.7031
Support: | 1 | 14H Motor Grader | 194.65 | 910.793 | 177285.8648 | 0.75535 | 1.2463
| 1 | D8T | 332.61 | 910.793 | 302938.8724 | 1.2907 | 2.1297
| 1 | 2,500 gal Water Truck | 105.45 | 910.793 | 96043.1259 | 0.40921 | 0.67519
Fleet Totals | 7.2354 |  |  | 6589.9233 | 2530041.2168 | 10.7796 | 17.7864
| Task 1 | Task 4
Spreading Alluvium | Roads | Misc
Hauling Hours (HR) | 148.1067 | 910.793
Job Hours (HR) | 296.2133 | 1821.5861
Equipment Cost (Cat D10T x 2) | 295223.9721 | 1815501.9785
Total | 295223.9721 | 1815501.9785
| Task 1 | Task 4
| Roads | Misc
Haul & Spread Alluvium, Total Cost | 706641.2145 | 4345543.1953
Alluvium Testing & Amendment
Assumptions:
MR submitted a plan on 8/23 & 9/20/02 to DEQ for a 2002 reclamation program of the Woodville Dump
The plan was a modification to the Reclamation Plan and given minor revision number (MR 02-001)
MR's reclamation cover soil recipe can be found in Table 9-2 of the Amendment 10 Application
DEQ assumes this recipe is used for the Miscellaneous Areas
Based on the 2020 Annual Report, very little soil has been stockpiled, therefore DEQ will assumes the Central Zone alluvium will be salvaged for reclamation material
DEQ assumes the following Central Zone alluvium sampling and analysis schedule
| Task 1 | Task 4
| Roads | Misc
Analyses | Volume of Alluv. (LCY) | Volume of Alluv. (LCY) | Frequency (LCY) | Cost ($) | Shipping ($)
Paste pH | 142245.8701 | 874751.6563 | 2500 | 0 | in house
Total Metals ICP Scan | 142245.8701 | 874751.6563 | 30000 | 225 | 10
Cu & Zn | 142245.8701 | 874751.6563 | 10000 | 45 | 10
Organic Content | 142245.8701 | 874751.6563 | 2500 | 15 | 10
Total Analytical Cost | 3319.0703 | 20410.872
And 1.5% organic matter by weight or 23 tons per acre is also require
Based on recent sampling data, the Central Zone alluvium will not required a lime amendment
Assume the compost would come Western Reclamation Inc. in Butte at a cost of $20/CY
The compost is stored at a central location, assume $5/CY extra to move it to where it will be spread
| Task 1 | Task 4
The Estimated Compost Cost | Roads | Misc
Area (AC) | 38.3343 | 202.0626
Density of Compost (LBS/CY) | 1000 | 1000
Cost per CY delivered to Butte ($/CY) | 25 | 25
Total Cost of Compost | 44084.4639 | 232372.0457
DEQ requests a qualified soils scientist (with a pickup truck) will be with the alluvium salvage operation full time for lab work, QA/QC and record keeping
The estimated cost for a qualified soil scientist (with a pickup), from a Consulting Firm, is $150 per hour
The number of work hours for the soil scientist is equal to the scheduled hours for the alluvium spreading operation
A portable soil testing trailer will be rented for laboratory space, sampling equipment storage, and record keeping
The estimated cost for a soil trailer rental is $200 per month
The Estimated Cost for Full Time Soils Scientist
Soil Scientist Hourly Rate ($/HR) | 150 | 150
Number of Hours (HR) | 148.1067 | 910.793
Total Cost of Soils Scientist | 22215.9993 | 136618.9557
The Estimated Cost for a Soils Trailer
Soils Trailer Monthly Rate ($/MO) | 200 | 200
Number of Months (MO) | 0.74053 | 4.554
Total Cost for Trailer | 148.1067 | 910.793
To spread the compost, piles are built up along the dump crest and pushed down slope with a D8T dozer
DEQ assume two-Cat D8T dozers will be used to spread the compost at a production rate of 1/4 acre per hour
After spreading, the compost will be incorporated into the top 4 inches using a harrow that is drag along behind the seeder
The Estimated Cost Spreading Compost
Size of Miscellaneous Area (AC) | 38.3343 | 202.0626
2 - Cat D8T Dozer Production (AC/HR) | 0.5 | 0.5
Job Hours - 2 Cat D8T (HR) | 76.6686 | 404.1253
Total Cost D8T | 51001.5079 | 268832.2299
| Task 1 | Task 4
| Roads | Misc
Alluvium Testing & Amendment, Total Cost | 120769.1481 | 659144.8963
Establish Vegetation & Weed Control
Assumptions:
The estimated revegetation and weed spraying cost for a 5-year period is $1,500 per acre, which includes minor erosion repair and seeding,
applying fertilizer, BMPs, etc.
The seeding is accomplished using a small dozer with a seeder attached to the front and a harrow pulled behind.
| Task 1 | Task 2 | Task 3 | Task 4 | Task 5
| Roads | Stockpiles | McQueen | Misc | Misc Partial
Size of Miscellaneous Areas (AC) | 38.3343 | 43.7138 | 22.641 | 202.0626 | 14.4926
Estimated Vegetation & Weed Control Cost ($/AC) | 1500 | 1500 | 1500 | 1500 | 1500
Total Cost | 57501.4746 | 65570.7695 | 33961.4347 | 303093.9726 | 21738.8418
Establish Vegetation & Weed Control, Total Cost | 57501.4746 | 65570.7695 | 33961.4347 | 303093.9726 | 21738.8418
Item 14 Miscellaneous Areas |  |  | 8342952.7718
As shown in the 2025 Site Plan map, these areas occur in many locations around the site.
Without identifying the slope and reclamation method for every polygon, DEQ and MR agreed to a general approach of applying a slope acreage adjustment to half of the areas. This assumes 50% of area has slopes from 20-40 percent (factor of 1.0525), and the other 50% of the area has slopes between 0 and 20 percent (factor of 1.0).
Consistent with previous bond calculations for miscellaneous areas, reclamation will include grading, rippineg, capping with 28 inches of alluvium, and revegetating.
Reclamation of stockpile footprints would not require grading and soil placement.
"Once all soil has been removed, stockpile storage areas will be ripped to relieve compaction. Revegetation will be conducted as described in Section 9.0" (Section 8.2 of 2018 Amendment Application)
Only ripping and revegetation costs will be applied for these areas.
Access routes will be needed across the site during reclamation and post-closure. For roads-- “Reclamation will consist of grading to blend into adjacent areas, ripping compacted surfaces, capping with 24 inches of alluvium, and revegetating (as described in Section 9.0). Stable road cuts in rock will not be graded. Grading will be conducted to minimize surface flow over fill slopes, and with non-noxious, nonflammable, noncombustible solids.” (Section 8.5 of 2018 Amendment Application).
Without identifying every road segment that may be retained, it will be assumed that the road acreage will be reduced by 50% through reclamation. This can be visualized as reducing the existing road widths in half (to ~50 ft). Like other misc. disturbance acres, it is assumed that half of the reclaimed road acreage will need to be corrected for slope area.
Much of this area is relatively flat and currently vegetated. Remnants of historic structures exist, the area has little active mine disturbance. Portions of this area may be excavated as part of removing reclamation material from the Central Zone alluvium. Following alluvium removal, only revegetation would be needed.
These areas consist of previously reclaimed and revegetated surfaces located to the west of the Hillcrest Dump (near Fickler Oil) and to the east of the Continental Pit, along an old access road/powerline corridor.
Although these areas have been vegetated for years, no bond release has been requested for these acres. The standard cost for revegetation and weed control will be applied to these areas.

## ITEM 14 Clearwater Ditch
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
Item 14 Improve Clearwater Ditch
Assumptions:
The Upper Clearwater Ditch is an eroding, unlined channel along the toe of the East Dump and the embankment of Interstate 15
The length of the eroding channel is 840 feet at which point the water enters an existing 24 inch culvert
In October 2010, Water & Environmental Techologies, PC (WET) completed a proposed underground drainage infrastructure design
for the Upper Clearwater Ditch.
The proposed design includes capturing all existing surface flows and directing them into a buried 24 inch HDPE culvert for
the entire length of the eroding channel.
The design includes the addition of five manholes and five sections of 24 inch HDPE Pipe (840 feet of pipe total)
The design also includes, slope reinforement mats, and rip rap lined channels, and a trash,grate to minimize clogging
and mainenance
According to the design provided by WET, the estimated material quantites are:
(1) 840 feet of 24 inch HDPE pipe
(2) 5 Concrete Manholes with entry trash grate
(3) rip rap
(4) slope reinforement mat
Based on cost data provided by RS Means, the material cost are:
(1) 840 feet of 24 inch HDPE pipe @ $30 per foot | 21420
(2) 5-Concrete Manholes @ $3,400 each | 17000
(3) rip rap @ $60 per foot installed | 6000
(4) slope reinforement mat @ $9.00 per square yard | 900
Excavation & Backfill
Pipe Excavation & Backfill @ $10 per foot | 8400
Manhole Excavation & Backfill @ $800 each | 4000
Total Cost | 57720
Item 14 Improve Clearwater Ditch |  | 57720

## ITEM 15 Spillway
MONTANA RESOURCES, LLP
OPERATING PERMIT
PROPOSED 5-YEAR BOND CALCULATION
NOVEMBER 2020
ACREAGES FROM 2025 SITE PLAN MAP
Feature | OP 00030A | OP 00041 | OP 00108 | OP 00030 | Grand Total
Spillway Cut | 4.7359 |  |  |  | 4.7359
Item 15 Construct Spillway at Closure
Assumptions
The company provided a conceptual post closure spillway design as part of the permit application
A detailed design will be undertaken once the facility closure is imminent and closure conditions are available
The design is located in KP's Reclamation Overview Design Document, Appendix B
The spillway was modeled as a trapezoid channel cut into bedrock on the left abutment of the YDTI embankment
The excavated channel will extend 5,000 feet southward to a point where local topography creates a flow path to the Continental Pit
The conceptual spillway intake and channel are as follows:
Inputs
Invert Elevation (ft) |  | 6387.5
Max Discharge (CFS) |  | 330
Base Width (ft) |  | 10
Flow Depth (ft) |  | 4.5
Minimum Grad (%) |  | 1
Cut Slope into Rampart Mountain |  | 1H:0.58V
Cut Slope into Fill |  | 1H:1.35V
Spillway Channel Length (ft) |  | 2539
Total Spillway Cut Volume (BCY) |  | 150000
Total Spillway Cut Volume (LCY) |  | 187500
Armored Swale Length (ft) |  | 730
Unarmored Swale Length (ft) |  | 7450
Total Rip Rap Volume (LCY) |  | 1489.2 | Approx. 55 ft^3 riprap per foot length of armored swale
Haul Distance to N-S Embankment (mi) |  | 2
Rock Swell Factor |  | 1.25
Rip Rap Cost
Rip Rap Unit Rate ($/LCY) |  | 100
Total Rip Rap Cost |  | 148920
Drill and Blast
Drill and Blast Unit Rate ($/BCY) |  | 18.55
Total Drill and Blast Cost |  | 2782500
Swale Grading Cost
Total Swale Length (ft) |  | 8180 |  | Dozing Distance |  | 100 | ft
Production Rate (l.c.y/hr) |  | 375 |  | Production Rate (max) |  | 375 | lcy/hr
Derating Factors (rock type, operator, grade) |  | 0.747 |  | Correction Factors |  | 0.747
Availability |  | 0.9 |  | Average Operator, Loose stockpile, 50 mins/hr efficiency
Corrected Production Factor |  | 252.1125
Volume of Swale (ft3) |  | 743737.87 |  | Corrected Production Rate |  | 280.125
Volume of Swale (l.c.y.) |  | 34432.3088
Hours of Work (h) |  | 136.5752
D6 Dozer Unit Cost ($/hr) |  | 194.45 | [5 empty] | Assumptions:
Total |  | 26557.0428 | [5 empty] | Soil Density of 2300 lb per l.c.y
Power-shift machines with 0.05-min fixed time
Using D6M-6SU Dozer (Line G)
Hauler Cycle Time (Min.) | [7 empty] | References: http://nheri.ucsd.edu/facilities/docs/Performance_Handbook_416C.pdf
Haul 10,560 feet One Way, Total Resistance 10%
Cat Edition 45 p.1-21 Cat 753C Haul Truck Rimpull-Speed-Gradeability Curve Loaded Speed (MPH) |  |  |  | 10
Cat Edition 45 p.1-21 Cat 735C Haul Truck Rimpull-Speed-Gradeability Curve Empty Speed (MPH) |  |  |  | 20
Load with Exchange |  | 1.5 | Estimated time for loading alluvium was 2.45. This is a much smaller excavator but calc needs to be completed.
Haul |  | 12
Dump and Maneuver |  | 1.6
Return |  | 6
Potential Cycle Time |  | 21.1
Wait on Slow Hauler |  | 0
Wait to Load, Bunching AVG |  | 0 | Bunching Calc | # of Trucks (Hauler Capabilities)
Total Cycle Time |  | 21.1 | 19.6 | 13.0667
Cycles per Hour |  | 2.8436
CAT 735C Heaped Capacity (LCY) |  | 25
Hauler Potential Production (LCY/HR) |  | 71.09
385C Passes per Hauler |  | 5 | 5 | 390F capacity
Loader Cycle Time (Min.) |  | 0.7
Load Time Truck (Min.) |  | 3.5
Number of Trucks Required |  | 6.0286
Production Rate (LCY/Min.) |  | 7.1429
Hourly Production (LCY/Hr) |  | 428.5714
Efficiency Factor |  | 0.83
Availability |  | 0.9
Adjusted Hourly Production (LCY/Hr) |  | 320.1429
Hours Required (Hr) |  | 468.5408
| Qty | Model | Hourly Cost Each Unit | Operating Hours | $ Total
Loaders: | 2 | 385C | 389.22 | 937.0817 | 364730.9237
Haulers: | 6.0286 | 735C | 234.63 | 2824.6319 | 662743.3735
Support: | 1 | D6T | 194.45 | 468.5408 | 91107.7644
Fleet Totals | 9.0286 |  |  | 4230.2544 | 1118582.0616
Item 15 Construct Spillway at Closure, Total Cost |  |  | 4076559.1044
Note on C45: Mitchell Flynn: Unit rate based on 2020 RSMeans Heavy Construction, Drilling and Blasting Rock, assuming blasting mats are required, over 1,500 CY
Note on B94: Mitchell Flynn: Only one loader required for the basic task of loading the hauler. One additional loader used for ripping surface prior to loading.